## Adopters
Noise HPD Tracking Report_ Adopters
NO | Group | Mine | Resp person | Request | Establishing of mine adoption team | Conduct mm interview | Customise LB and BC plans
1 | Xstrata Alloys | Kroondal | Themba Nkosi | 2012-09-18 | In Progress | To be done | To be done
2 | Impala Platinum | Rustenburg | James Van Rensburg | 2012-08-12 | In Progress | To be done | To be done
3 | Dortsfontein Coal | Total | Arnold Theron | 2012-06-01 | In Progress | To be done | To be done
4 | Sasol Coal | Secunda | Inus Labushagne | 2012-03-01 | In Progress | Interviews conducted | To be done
5 | Anglo Gold Ashanti |  | Koos Havenga | 2011-03-01 | Completed | Completed | Completed
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
85 | GEE NOISE Training
Note on C3: Hgumede: ???????????

## Partial adopters
Noise HPD Tracking _ Partial adopters
NO | Group | Mine | Resp person | Request | Establishing of mine adoption team | Conduct mm interview | Customis LB and BC plans
1 | Xstrata Alloys | Waterval - Rustenburg | Themba Nkosi | 2012-09-05 | To be done-Await the way forward from Thembe Nkosi
2 | Xstrata Alloys | Rietvlei - Rustenburg | Themba Nkosi | 2012-09-05 | To be done-Await the way forward from Thembe Nkosi
3 | Xstrata Alloys | Kroondal - Rustenburg | Themba Nkosi | 2012-09-05 | To be done-Await the way forward from Thembe Nkosi
4 | Xstrata Alloys | Throncliffe - Mpumalanga | Amu Modau | 2012-09-12 | To be done- Rodney Mondela
5 | Xstrata Alloys | Helena - Mpumalanga | Amu Modau | 2012-09-12 | To be done- Rodney Mondela
6 | Xstrata Alloys | Magareng - Mpumalanga | Amu Modau | 2012-09-12 | To be done- Rodney Mondela
7 | Xstrata Platinum | Borwa - Mpumalanga | Rodney Mondela | 2012-09-12 | To be done- Rodney Mondela
8 | Xstrata Platinum | Mototolo - Mpumalanga | Rodney Mondela | 2012-09-12 | To be done- Rodney Mondela
9 | Xstrata Platinum | Eland - Brits | Gert Jv Rensburg | 2012-11-11 | To be followed up-JDB
10 | Xstrata Rhovan | Brits | JJ van der Merwe | 2012-11-11 | To be followed up-JDB
11 | Xstrata Lydenburg Smelter | Lydenburg | Elzaane Moodie | 2012-11-11 | To be followed up-JDB
12 | Xstrata Lion | Steelpoort | Frans Germishuizen | 2012-11-11 | To be followed up-JDB
13 | Xstrata Rustenburg Smelter | Rustenburg | Daan prinsloo | 2012-11-11 | To be followed up-JDB
14 | Xstrata Boshoek | Rustenburg | Chantelle Koekemoer | 2012-11-11 | To be followed up-JDB
15 | Petra Diamonds | Lime Acres | Jacques Oosthuizen | 2012-05-12 | To be done- Jacques Oosthuizen
16 | Petra Diamonds | Cullinan | Jacques Oosthuizen | 2012-05-12 | To be done- Jacques Oosthuizen
17 | ARM | Nkomati | Lourens grobler | 2012-06-12 | To be done Tsietse Letana | Interviews conducted
18 | ARM | Two Rivers | Johan Marias | 2012-06-12 | To be done Tsietse Letana | Interviews conducted
19 | PPC | Mooiplaas | Grant Skews | 2012-03-01 | To be done- await feedback from Grant
20 | PPC | Hercules | Grant Skews | 2012-03-01 | To be done- await feedback from Grant
21 | PPC | Jupiter | Grant Skews | 2012-03-01 | To be done- await feedback from Grant
22 | PPC | Dwaalboom | Grant Skews | 2012-03-01 | To be done- await feedback from Grant
23 | PPC | Riebeeck | Grant Skews | 2012-03-01 | To be done- await feedback from Grant
24 | PPC | De Hoek | Grant Skews | 2012-03-01 | To be done- await feedback from Grant
25 | PPC | Beestekraal | Grant Skews | 2012-03-01 | To be done- await feedback from Grant
26 | PPC | Lime Acres | Grant Skews | 2012-03-01 | To be done- await feedback from Grant
27 | Lonmin | Rustenburg | Dave Mellet | 2012-06-12 | Have established an internaladoption team

## Implementers
Noise HPD Tracking _ Implementors
NO | Group | Mine | Resp person | Request | Info requested | Follow-up | Outcome
1 | PPC | Aggregates | Grant Skews | 2012-06-01 | HPD, DVD's and training | Sep/Oct 2012 | All being trained in HPD_TAS_Tool. Await comfirmatiom ito adopters, partial adopters and implementers
2 | Modikwa | Mpumalanga | Dirk Fouche | 2012-04-01 | HPD, DVD's and training | 2012-09-01 | Not implemented yet
3 | Afrimat | Glen Douglas Gauteng | Voice Reza | 2012-02-12 | HPD, DVD's and training | 2012-09-01 | All being trained in HPD_TAS_Tool.Await feedback on their progress made
4 | Afrimat | Glen Douglas Cape | Monte Colemen | 2012-02-12 | HPD, DVD's and training | 2012-09-01 | All being trained in HPD_TAS_Tool.Await feedback on their progress made
5 | Northam Platinum | Rustenburg | Bonginhlanlha | 2012-05-12 | HPD, DVD's and training | 2012-09-01 | All being trained in HPD_TAS_Tool.Busy implementing
6 | Khutahla | Colliery | Paul Redelinghuys | 2012-05-12 | HPD, DVD's and training | 2012-09-01 | All being trained in HPD_TAS_ToolAwait feedback on their progress made
7 | Shaft Sinkers | Rustenburg | Dirk Bleeker | 2012-07-12 | HPD, DVD's and training | 2012-09-01 | Await feedback on their progress made
8 | SAMREC | Ceramics | Hunadi Setati | 2012-08-12 | HPD, DVD's and training | 2012-09-01 | All being trained in HPD_TAS_ToolAwait feedback on their progress made
9 | Foskor | Phalaborwa | Adolf delport | 2012-07-12 | HPD, DVD's and training | 2012-09-01 | All being trained in HPD_TAS_Tool.Await feedback on their progress made
10 | Sasol | Syferfontein | Inus Labuschagne | 2012-03-12 | HPD, DVD's and training | 2012-09-01 | All being trained in HPD_TAS_Tool.Await feedback on their progress made
11 | Sasol | Bosjesfontein | Inus Labuschagne | 2012-03-12 | HPD, DVD's and training | 2012-09-01 | Await feedback on their progress made
12 | Dwarsrivier | Chrome | Johan Vermeulen | 2012-09-12 | HPD, DVD's and training | 2012-10-08 | All being trained in HPD_TAS_Tool.Want to adopt, but need estblishment of internal team and the steps that needs to be followed until adoption is completed
13 | Winder Controls | OEM/Shaft Sinkers | Claude Oosthuizen | 2012-10-02 | HPD, DVD's and training |  | All being trained in HPD_TAS_Tool.Consider implementation
14 | Solstech | OEM/Shaft Sinkers | Steven Smith | 2012-10-09 | HPD, DVD's and training | 2012-10-09 | All being trained in HPD_TAS_Tool.Consider implementation
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
85 | GEE NOISE Training