5 Hollard Street

Johannesburg 2001

PO Box 61809

Marshalltown 2107

Telephone: (011) 498-7100

Telefax: (011) 834-1884

Web: http://www. chamberofmines.org.za

E-mail: info@chamberofmines.org.za

13 May 2014

- Presentations

| Action: Winch Cover | Responsible | When |
| --- | --- | --- |
| Presentation to be given to the Interest Group | C du Plessis | 10 June 2014 |
| Discuss influencing factors that could have a negative effect on winch covers. | T Webb/N Dikgale | 10 June 2013 |

- Documentation

| Action: web-site access | Responsible | When |
| --- | --- | --- |
| Provide login details to each member | A Banyini L Masilo | 10 June 2014 |

  - Up-dated versions of SLP briefs

| Action: web-site information | Responsible | When |
| --- | --- | --- |
| Populate relevant documentation onto web-site for access by members | A Banyini L Masilo G Pienaar | 10 June 2014 |

- Progress reporting

  - Draft reporting template

| Action: Draft reporting template | Responsible | When |
| --- | --- | --- |
| Revise the current reporting template | M van Deventer | - May 2014 |

  - Feedback on progress per operation (both SLP’s)

Multi-stage filtration systems – Adopters

| Group | Mine/Shaft | No. units identified | No of units installed | % Compliance | Budget provided |  | Expected completion date |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Yes | No |  |
| AGA | Tautona | 41 | 39 | 95.1 | x | - | Aug’14 |
| Harmony | Target 3 | 2 | 0 | 0 | - | x | Jun’14 |
|  | Kusasalethu | 10 | 5 | 50 | x | - | Dec’14 |
|  | Target 1 | 1 | 0 | 0 | x | - | Sep’14 |
|  | Tshepong | 2 | 0 | 0 | x | - | Dec’14 |
| Sibanye | Beatrix | 39 | 39 | 100 | x | - | n/a |

Winch covers – Adopters

| Group | Mine/Shaft | No. of winches to be covered | No of winches covered | % Compliance | Budget provided |  | Expected completion date |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Yes | No |  |
| AGA | Tautona | 123 | 4 | 3.3 | x | - | Apr’14 |
| Harmony | Masimong | 80 | 0 | 0 | x | - | Dec’14 |
|  | Target 3 | 100 | 2 | 2 | - | x | Sep’14 |
|  | Phakisa | 144 | 0 | 0 | x | - | Feb’15 |
|  | Kusasalethu | 160 | 4 | 2.5 | - | x | n/a |
|  | Target 1 | 35 | 0 | 0 | x | - | Jun’14 |
|  | Tshepong | 286 | 0 | 0 | x | - | Aug’14 |

Once the new version is finalized the above information will be transferred and previous input updated.

- General

For some members it was the first attendance and they requested to have some more information on the following:

- SLP adoption process

- SLP briefs

- Sharing in lessons learnt from other operations

| Action: SLP adoption process | Responsible | When |
| --- | --- | --- |
| - Re-present the background session given at the first meeting | G Pienaar | - June 2014 |