ADOPTION PROCESS

1. Facilitate adoption decision

The mine must properly investigate the case for adoption the leading practice  – a  check-box investigation  process  is  provided.  The decision  must  be  endorsed  by  the  general  manager  and  the completed form sent to the MOSH Adoption Team Manager. More

2. Secure widespread support for adoption

The  support  of  regional  and mine level  union representatives must

be  secured  as  soon  as  possible  and  a  mine-wide  briefing  note

issued to advise of the decision to adopt the leading practice. More

3. Establish an effective adoption team

A  suitable  person  must  be  tasked  with  leading  the  mine  adoption

team,  and  another  to  assist  in  overseeing  customisation  of  the

behavioural  plans  that form  part  of the  leading  practice.  Training  of

these  persons  should  be  discussed  /  arranged  through  the  MOSH

Adoption  Team  Manager.  The  Mine  Adoption  Team Manager must

ensure  establishment  of  a  multi-disciplinary  team  with  the

competencies required for successful adoption of the practice. More

4. Prepare first version adoption plan

The Mine Adoption  Team Manager must  arrange  a team workshop

to  ensure  that  all team members have  a common understanding  of

the  adoption  process  and  to  prepare  an  initial  adoption  plan.  An

example  plan and  process  check-list is  provided.  At  this  stage  the

team  must  select  the  piloting  area  for  the  practice,  schedule

acquisition  of  the  practice  and  agree  the  critical  enablers  for

successful adoption. The MOSH Adoption Team Manager can assist

with this workshop. More

5. Initiate monitoring programme

The key measurements needed to quantify performance and impacts

must be identified at an early stage collection of the necessary base-

line data must be initiated as soon as possible. More

6. Establish effective relationship with COPA

A  meeting  with  the  MOSH  Adoption  Team  Manager  should  be

arranged  as  soon  as  possible  after  the  decision  to  adopt  to  set up

appropriate  COPA  membership  and  arrangements  for  obtaining

support,  training  and  other  assistance  through  the  COPA  and  its

members. More

7. Update key stakeholders on progress

Arrangements  for  keeping  key  stakeholders  informed  of  progress,

challenges  and  key  developments must  be  established  at  an  early

stage  to  pave  the  way  for  eager  adoption.  This  should  include  top

management at the mine and the COPA. More

8. Plan and conduct direct enquires

A  common  expert  understanding  of  the  risk  situation  must  be

established as a datum for identifying any gaps or misunderstanding

at  the  mine.  The  generic  expert  risk  summary must  therefore  be

reviewed and updated. Key persons involved in adopting the practice

must be  identified  and about  30  people from  all  levels identified for

direct  enquiry  interviews  – Worksheet. Most  importantly,  suitable

persons  must  be  selected,  trained  and  properly  briefed  to  conduct

the  interviews. Only  then  should the  interviews  be  conducted  using

the questions provided. More

9. Customise generic behavioural plans

Suitable  persons must  be  selected  to  analyse  the  interview  results

using  the  guidance  provided  in  an  analysis  worksheet. The  results

must then be compared to the updated expert risk summary, the

generic  mental  models  report,  and  the  generic  behavioural

communication and  leadership  behaviour plans  to  identify  any

adjustments  needed.  Having  made  the  identified  adjustments  the

new communication requirements  should  be identified. The updated

behavioural  plans should then be  presented to top management for

approval. More

10. Harmonise practice with mine standards

The  technical  elements  of  the  leading  practice must  also  be

reviewed  and  adjusted to ensure that the  practice does not result in

undue  disruption.  Adjustments  needed  to  harmonise  the  practice

with mine  standards  should  be  identified  and  introduced,  provided

that they do not compromise the core-elements of the practice. More

11. Develop approved mine-wide adoption plan

Having  customised  the  three  legs  of  the  leading  practice  to  take

account  of  mine  specific  circumstances,  the  adoption  team  must

conduct  a  detailed  risk  assessment  of  the  planned  changes.

Identified  risks must  be  addressed  and mine-wide  roll-out  planned.

The  initial  adoption  plan  should  then  be  reviewed,  updated  and

finalised for sign-off by top management. More

12. Develop training and communication materials

The  customised  behavioural  plans  and  technical  elements  and

supplier documents must be reviewed  to  carefully  identify  and plan

the  required  training  and  both  worker  and  supervisory  levels.  The

training  schedules  should  then  be  established  and  the  training

documentation  and  training  lesson  plans  prepared.  Arrangements

must  be  made to  develop  the  required  behavioural communication

material  and  to  prepare  any  special  documentation  of  signage

needed for successful adoption. More

13. Brief and train key mine persons

Prior to implementing  the  training  programme  all  supervisory  levels

and  the workers  should  be  briefed  about  the  training  and  adoption

programme. Aspects of the behavioural communication not included

in  the  training  programme  should  be  implemented  in  these  briefing

sessions and In other activities as appropriate. The required training

should then be provided as planned. More

14. Pilot adoption of the practice

Access  to  intellectual  property  and  purchase  of  the  required

equipment must be  arranged  as early in  the  adoption  process as is

reasonably  possible  to minimise  delays  due to  long  delivery  times.

The necessary maintenance infrastructure / arrangements must also

be set up in good time so that adoption of the practice is not delayed.

Adoption  at the  piloting site should commence on completion  of the

briefing and training. More

15. Monitor, evaluate and report on performance and impacts

Procedures schedules and responsibilities for making, recording and

reporting on the necessary measurements to monitor and determine

the  performance  of  the  practice  must  be  set  up  and  implemented.

The  performance  and  impact  of  the  leading  practice  should  be

written up and presented to management and to the COPA. More

16. Finalise and implement mine-wide roll-out plans

Once  the  leading  practice  has  been  successfully  adopted  at  the

piloting site the mine adoption team need to  test  and document any

refinements  to  the  practice  considered  necessary,  and then finalise

and  implement  the  plans  for  mine-wide  roll-out  of  the  leading

practice. More

MOSH Falls of Ground Adoption Process

Community of Practice for Adoption of a Leading Practice

Registration of Interest to form part of the COPA for the Triggered Action Response Plan

A Community of Practice for Adoption (COPA) is in essence a group of people who voluntarily agree to interact with each other in a relatively informal way to share information helpful in overcoming implementation problems, and for bringing about continuous performance improvements”

The COPA will initially be managed through the MOSH FOG Adoption Team with the main objective of ensuring a successful and speedy roll-out of the leading practice for the Triggered Action Response Plan to prevent uncontrolled falls of ground.

Should you wish to form a part of this COPA, please supply your details below and we will ensure your incorporation into this COPA.

| First Name |  |
| --- | --- |
| Surname |  |
| Occupation / Position |  |
| E-mail Address |  |
| Contact Number |  |
| Mining Company |  |
| Mine |  |
| Signature |  |

G1. Facilitate adoption decision

G1.1. Prepare and present case for adopting the leading practice at the mine:

 The relevant specialist at the mine should evaluate the case for adopting the

leading practice. (This is an implicit requirement of both the Mine Health and

Safety Act and the Mining Charter). A check box style process flow diagram for

such an assessment is provided in Appendix A3.

 The mine specific benefit and value of adopting  the  leading practice, or lack

thereof, should be clearly identified and documented. The generic value case

prepared by the MOSH Adoption Team should be consulted in undertaking this

assessment. It is available on MOSH website at www.mosh.co.za.

G1.2. Obtain top management decision about adoption of the practice:

 Top  management  at  the  mine  need  to  be fully  aware  of  what  the  MOSH

Leading  Practice and  the  adoption  process  entail, before  deciding  about  whether  or  not  to  adopt. To achieve  a  fully  successful  outcome  they  must  be

supportive  of  both  the  practice  and  the  adoption process.

 The simple  explanation  and  diagram  presented earlier, and the brochure about the adoption system presented in Appendix 4 are provided to assist in the preparation  of  a  brief  explanation  of  the  MOSH Adoption System to top management.  A 15 minute explanatory DVD is also available from the MOSH Secretariat.

 Should additional assistance be required in preparing or presenting the case to

top management, the MOSH Adoption Team Manager should be contacted.

 The  Senior  General  Manager  at  the  mine  should  record  the  decision  about

adoption on the assessment form of Appendix A3 and arrange for the signed

form to be returned to the MOSH Adoption Team Manager.

G2. Secure support for adoption

G2.1. Secure support of regional and mine-level union representatives:

 Regional and mine-level  Union  Representatives  should be  engaged  as  soon

as possible to secure their understanding, buy-in and support for the leading

practice. This is crucial. The extent of  the support  provided, or withheld, can

greatly facilitate or inhibit the adoption process.

G2.2. Issue written mine-wide briefing note advising of decision to adopt:

 A  mine-wide  briefing  note  should  be  issued  by  management  to  inform

employees  of  the  intention  to  adopt  the  leading  practice  at  the  mine. This

should be done as soon as possible after engaging the unions, and preferably

with their support.

 The note  should  advise  that  the  adoption  process  will  involve  detailed

discussions  with  various employees at  all  levels  to  get  their  input  into  the

adoption  process.  (These  discussions  are  the  one-on-one  direct  enquiry

interviews described under G8.)

G3. Establish an effective mine adoption team

G3.1. Identify and appoint a suitable project leader / champion:

 An  important  aspect  of  top  management’s  decision  to  adopt  the  leading

practice must be that a suitable person will be assigned the task of leading the

project and championing the leading practice and the adoption process at the

mine. This is crucial to the success of the adoption process.

 The selected person must have time to properly fulfil the role of adoption team

manager,  and leading practice champion. This  is not an understatement and

the mistake of overloading a competent person must not be made.

 Systematic execution of the adoption process and successful adoption of the

leading  practice  should become  a  key  performance  criterion in  the  selected

person’s performance contract with the mine.

 The  attributes  of  an  ideal  leading  practice  adoption  team  manager  and

champion are provided below to assist the mine making this selection.

Attributes of a Leading Practice Adoption Team Manager / Champion 

1 Credibility: An essential requirement is that the champion should be credible.

This  individual  should  preferably  be  someone  linked  directly  to  the  specific

discipline  and  should  be  at  an  appropriately  high  level  in  the  organisation.

He/she  should  have  good  levels  of  knowledge,  energy,  leadership,

communication skills and personal credibility.



2 Involvement: Having  selected  an  individual  with  the  right  potential,  it  is

essential  that  he/she  has  sufficient  time  available  to  adequately  perform  the

functions  of  project management and  championship.    To do  this,  the  person

needs to become deeply involved in the details of the technology as well as the

people  components  of  the  leading  practice,  to  appreciate  the  issues  and

problems, and to assist in, or be knowledgeable about their solution.



3 Leadership: An important role of the person selected will be that of providing

leadership in overcoming implementation problems that arise, including that of

energising lagging aspects of the process.  It will also include the provision of

insightful input into the development of strategies and plans for the progressive

adoption of the leading practice across the mine.



4 Communication: A  particularly  key  role  will  be  that  of  being  an  effective

spokesperson  for  the  leading  practice  being  championed.    To  do  this

effectively, the champion should accumulate key data and prepare appropriate

documents and presentations to communicate such performance and technical

data to interested parties, initially at the mine, but in due course on behalf of

the mine at industry workshops, conferences, and so on.



G3.2. Identify a person to oversee customisation of behavioural plans:

 A  specific  person  needs  to  be  identified  and  allocated  the  responsibility  for

overseeing  the process of customising  the generic behavioural plans to  take

account  of  mine  specific  circumstances  and  then  integrating  them  into  the

mine’s  adoption  plan.  To  gain  the  people  related  benefits  of  the  MOSH

adoption  process  it  is  essential  that  this  process  is  properly  carried  out. A

behavioural plans overseer is required to ensure that this is the case.

 The generic  behavioural  communication  and  leadership  behaviour  plans  are

provided  in  Part 3,  in sections  P3.2 and  P3.3 respectively. They are integral

parts of the MOSH Leading Practice – they address the knowledge gaps and

other identified barriers to successful adoption, and help ensure the behaviours

needed at all levels for a sustainable adoption. They must be customised  to

take  account  of  mine  specific  circumstances  and  then  implemented  for

adoption of the MOSH Leading Practice to be complete.

 To  assist  in  clarifying  what  needs  to  be  overseen,  and  why  oversight

responsibility needs to be allocated to a specific person, an outline of the eight-

step  process  for  customising  the behavioural  plans  is  presented  in  a  single

document  in  Appendix  A5.  Relevant  details  are  however  presented  at  the

appropriate point in this part of the guide.

 Given  that  the mine may in  future  adopt  other MOSH leading  practices with

similar  customisation  requirements,  consideration  should  be  given  to

identifying a person well  placed to  assist future adoption teams  at the mine.

The nature of the work suggests that such a Behavioural Plans Overseer could

well be drawn from the Human Resources department.

 For  other  MOSH  leading  practices  this  responsibility  has  sometimes  been

allocated to the Mine Adoption Team Manager but this has not worked well.

G3.3. Train project leader and behavioural plans overseer:

 The project leader (the  Mine  Adoption Team Manager) should liaise  with the

MOSH Adoption Team Manager and  the Group Adoption Coordinator,  (if his

mining company has appointed one) to identify suitable training arrangements

for himself and the identified behavioural plans overseer.

 No formal training courses are yet available and at this stage one of the MOSH

Adoption Team Managers or one of the Learning Hub Specialists may need to

provide the necessary training and mentorship.

 An alternative that  should also be explored with the  MOSH  Adoption  Team  Manager  is  that  of arranging for the two mine persons to spend time with their equivalents at a mine that has already successfully  worked  through  an adoption

process.

G3.4. Secure establishment of an appropriate adoption team at the mine:

 In  addition  to  the  Mine  Adoption  Team  Manager and  the  Behavioural  Plans

Overseer, the mine adoption team should include:

- a person from the training department,

- the  line  manager  of  the  section  in  which  the  adoption  process  is  to  be

initiated,

- a person representing labour,

- a mine safety specialist, and

- a specialist in the area of the leading practice.

 All of the persons in the Mine Adoption Team must have sufficient time available to fulfil their role and responsibilities on  the  adoption  team,  and  this should  be  appropriately  reflected  as  a  key performance  area  in  their  performance  contracts with the mine.

G3.5. Provide adoption team with copies of leading practice adoption guide:

 This should be done at least  a few clear days  before holding a workshop  to

review  and  initiate  the  adoption  process.  Team  members  should  familiarise

themselves with the guide before the workshop.

G4. Prepare first version adoption plan

G4.1. Workshop leading practice adoption guide - mine project team:

 A workshop should be arranged to enable all members of the Mine Adoption

team to have a good and common understanding of both the leading practice

and  the  adoption  process.  The  agenda  for  the  workshop  should  include  the

following:

- Opening by Mine manager to explain the steps already taken

- The case for adopting the leading practice

- Key elements of the MOSH Adoption System

- Potential assistance from the COPA and the MOSH Adoption Team

- Key technical elements of the leading practice

- The concepts of leadership behaviour and behavioural communication

- The leading practice adoption guide

 Much  of  the  material  required  for  the  initial  agenda  points  is  in the  leading

practice  adoption  guide,  but  these  points  should be  discussed  before  going

through  the  guide  to  provide  a  context  that  will  be  helpful  when  working

through the guide.

 The  Mine  Adoption  Team  Manager  should  consider  inviting  the  MOSH

Adoption Team Manager to attend the workshop to assist in presenting some

of the concepts and in answering some of the questions that could arise.

G4.2. Review / refine example adoption plan

 The Mine Adoption Team must properly understand and take ownership of the

adoption  plan  to  be  implemented. The  framework plan provided  in Appendix

A1 must  thus  be  carefully  reviewed  and  adjusted  as  appropriate  to  take

account of mine and  team  specific  requirements. The  adoption guide should

then also be adjusted / annotated / and used accordingly.

 The  team  needs  to  allocate  date  specific  timing  to  each  of  the  various

activities. Particular attention must be given to the time required for arranging

access  to any  intellectual property,  capital  funds or major  equipment, and  to

scheduling early action to minimise the impact of such time requirements.

 The  team  should  ensure  that  any  adjustments  to  the  example  plan  do  not

compromise  proper  customisation  and  implementation  of  the  behavioural

plans. The MOSH Adoption Team Manager should be consulted in the event of

any uncertainty on this point.

G4.3. Identify an appropriate piloting section / area at the mine

 Initiation of  the adoption process at the mine should be piloted in a carefully

selected site. The selected site should be:

- of  sufficient  size  to  meaningfully  implement  all  aspects  of  the  leading

practice  that  will  be  encountered in  extending  its  adoption  across  the

mine, and

- well  managed,  and  not  beset  with  unusual

operational problems.

 Ensuring that these criteria are met will minimise

risks  and  enable  adoption  challenges  to  be

appropriately addressed.

G4.4. Identify/arrange any specialist technical support considered necessary

 During the course of reviewing and updating the framework adoption plan the

team  should  identify  any  areas  where  they  consider  specialist  technical

support to be necessary.

 Training  or  specialist  support  required  for  handling  the  direct  enquiry  and

analysis work involved in customising the behavioural plans is dealt with under

points G8.3 and G8.4. Requirements additional to these should be arranged as

appropriate.

G4.5. Agree critical enabling factors for successful  adoption of the practice

 The Mine Adoption Team and senior management at the mine should be clear

about, and agree upon, the factors which are critical enablers for adoption of

the practice at the mine to be successful.

 These factors should be identified by the Mine Adoption Team for discussion

and agreement with senior and top management.

 Consideration should be given to factors such as:

- Understanding and ownership of the adoption process

- Effective communication with all key stakeholders and operational adopters

- Adequate allocation of time and resources

- Effective customisation of the practice and behavioural plans

- Management  involvement,  interest  and

support

- Union involvement

- Other factors identified by the Mine Adoption

Team.

G4.6. Ensure that sufficient time / resources have been provided:

 At  this  point  the  Mine Adoption Team  Manager should make an  explicit  and

careful  assessment of the time allowed for the project, and of  the  resources

allocated to it.

Points to consider in updating this section

 The  experience  gained  at  the  first  adoption  (or

demonstration) mine should be reviewed and used as

appropriate when updating the guide, to provide more

specific  information  to  assist  in  selecting  the  piloting

section at adoption mines.

Points to consider in updating this section

 Based  on  experience  and  considerations  at  the  first

adoption mine (or demonstration) mine, when updating

the  guide  the MOSH Adoption  Team  may  be  able  to

provide additional guidance on this point.

 The Mine Manager should be advised of the outcome of this review and at that

time any shortcomings that cannot be readily addressed by the team should be

raised with the Mine Manager.

 Both the Mine manager and the Mine Adoption Team Manager have a special

responsibility to ensure that no inappropriate short cuts or omissions occur due

to understaffing or the imposition of deadlines that are too tight.

G5. Initiate baseline monitoring programme

G5.1. Identify key measurements to determine performance of the practice

 Identification and planning of the monitoring process to acquire data to quantify

the  impact  of  the leading practice should start  as soon as possible  after the

decision to adopt.

 The key measurements needed to quantitatively indicate the performance and

impact  of  the  practice  must be  identified  by  the  Mine  Adoption  Team  well

before implementation of the practice begins.

 Consideration should be given to measuring parameters such as:

- Relevant OHS indicators

- Operational problems encountered

- Equipment availability

- Non-compliance incidents

- Relevant production indicators

- Absenteeism

 The identified parameters and the procedure and responsibility for making the

measurements should be written up in a brief document. The document should

also indicate the envisaged analysis and the responsibility for its execution.

 These details must be  regarded as an  important  aspect of  the adoption  plan

and not as a nice to have.

G5.2. Initiate collection of baseline data

 Arrangements to gather the necessary baseline data must be implemented as

soon  as  possible,  otherwise  the  opportunity  to  credibly  quantify  the

performance / impact of the leading practice will be lost.

 The data routinely collected by the mine simply assumed to be adequate. They

are unlikely to be fully sufficient for this purpose and additional measurements

will probably be necessary.

Points to consider in updating this section

 Based  on  experience  and  considerations  at  the  first

adoption  (or  demonstration) mine,  when  updating  the

guide the MOSH Adoption Team may be  in  a  position

to provide more specific and helpful guidance.

G6. Establish effective relationship with the COPA more

G6.1. Meet with COPA coordinator to establish a working relationship:

 The  Mine  Adoption  Team  Manager  should  meet  with  the  MOSH  Adoption

Team Manager to clarify the mine’s membership of the COPA, and the nature

and  extent  of  support  and  assistance  that  might  be  sourced  from  either  the

MOSH Adoption Team, the source mine, or COPA members.

 A number of key people at the mine should already have been contacted by

the MOSH Adoption Team Manager and some may thus already be members

of  the  COPA. The  Mine  Adoption  Team  Manager should  become  the

regular member, with the Behavioural Plans Overseer attending when

necessary.  It  would  be  appropriate  for  someone  from  the  mines  top

management team to also be a member, but not more than this.

 A  modus  operandi  for  active  and  productive membership  of  the  COPA,  including  obtaining assistance  when  needed,  should  be  discussed and  agreed with  MOSH  Adoption  Team Manager.

G6.2. Secure support / input / secondment / training via COPA interaction:

 This must be seen as an on-going activity. Particular needs are likely to arise

as  the  adoption  process  unfolds  and  these  should  be  explored  through  the

COPA  according  to  the modus  operandi  agreed  upon  in point G6.1.  Active

participation in the COPA will help enable this.

 Depending  of  the  skills  of  identified  team  members,  the  need  for  support

through the COPA, in one form or another, could well emerge at an early stage

– see point G4.4. This should be acted on without delay.

G7. Update key stakeholders on progress

G7.1. Provide feedback on implementation challenges / successes to COPA

 Detailed  feedback  should be  provided  to  the COPA on  significant  difficulties

encountered and on key successes achieved.

 Voluntarily  sharing problems encountered and

successes achieved should be regarded as an

important  way  of  learning  and  of  passing  on

hard earned experience.

 The  MOSH  Adoption  Team  Manager  may  wish  to

arrange  for  the  interaction  and  relationship  with  key

persons at adoption mines to be initiated differently. If

so this section should be adjusted accordingly.

 Whatever  the  adjustment,  the  net  effect  must  be  to

secure  an  effective  working  and  liaison  relationship

with  the  key  persons  at  adoption  mines,  particularly

the  first  few  mines  that  decide  to  adopt  the  leading

practice.

Points to consider in updating this section

 Based  on  experience  and  considerations  at  the  first

adoption  (or  demonstration)  mine,  when  updating  the

guide  the  MOSH  Adoption  Team  may  be  able  to

provide more specific guidance on this point.

G7.2. Prepare and issue progress updates to key stakeholders

 The Mine Adoption Team Manager must ensure that key stakeholders are kept

informed of progress.

 Brief progress updates should be prepared and

issued regularly  to  the  Union  leaders,  mine

management,  and  the  MOSH  Adoption  Team

Manager.

 Progress on  the  adoption process  should be reported  to  and discussed  with

the Mine Manager at least once per month.

G8. Plan and conduct direct enquiries

G8.1. Review / update expert causal chain risk summary

 The Mine Adoption Team, with the assistance of relevant experts at the mine,

should critically review the causal chain expert risk model provided in Appendix

A6.

 The  expert  risk  model should  be  updated  to  include  any  important  mine

specific  risks being  addressed  by  the  leading  practice  that  is  not  reflected  in  the

expert model of Appendix A6.

 Discarded or  added  aspects  should  be  identified  and  retained  as  they  may

assist the process of customising the behavioural plans.

 In concluding the review process it  is essential to ensure that all participants

have  the same understanding of  the  risks  situation at the mine that  is  being

addressed  by  the  leading  practice. (It  is  this  expert  understanding  of  the  mine’s  risk

situation that allows the team to identify important knowledge gaps or misperceptions that must be

addressed through the customised behavioural communication plan.)

G8.2. Identify adopters and key stakeholders

 The Mine Adoption Team must identify the adopters and stakeholders that will

be  involved in the process of adopting the leading  practice at  the mine. This

should be done with the guidance provided by:

- the list of anticipated adopters and key stakeholders identified in Appendix

A7 , and

- The  notes  included  on  the  Worksheet  of  Appendix  A8 to  facilitate

identification of the appropriate people at the mine.

G8.3. Identify persons to conduct direct enquiry interviews

 Persons  trained  in  conducting  direct  enquiry  interviews  should  be  used  to

conduct the interviews.

 The mining company’s Group Adoption Coordinator, if appointed, is expected

to  maintain  a  list  of  persons  in  the  Group  who  have  been  trained  in  direct

enquiry interview techniques, and he should be contacted to establish whether

trained persons can be made available to conduct the interviews.

 In  the  event  that  trained  persons  are  not  available  through  with  the  Group

Adoption  Coordinator,  the  Mine  Adoption  Team  Manager together  with  the

Behaviour Plans Overseer should select persons for training in direct enquiry

interview skills.

 The persons selected should not be directly involved in adopting or operating

the leading practice. They should be persons who are most likely to:

- Cause interviewees to feel comfortable within an interview setting, that is, to

feel free to speak openly and candidly about their observations and views,

- Be considered credible by those being interviewed, and

- Diligently complete each scheduled  interview  on  time  and  in  the  required

manner.

Points to consider in updating this section

 Based  on  experience  and  considerations  at  the  first

adoption  (or  demonstration)  mine,  when  updating  the

guide  the  MOSH  Adoption  Team  may  be  able  to

provide more specific guidance on this point.

G8.4. Train and brief the interviewers

 The  Mine  Adoption  Team  Manager  should  liaise  with  the  MOSH  Adoption

Team Manager to arrange any required training.

 The trained interviewers should be provided with the briefing material provided

in Appendix A9.

 They should then be collectively briefed by the Mine Adoption Team maanger about the leading practice, the risks being addressed, the objectives of the interview process, the procedures

and  logistics  of  arranging  the  interviews, the  persons  they  are  scheduled  to

interview,  and  the  time  scale  of  the  process.  They  should  also  be  taken

through the briefing material provided to them.

 The  Behavioural  Overseer  must  ensure  that  all  interviewers  know  that  they

must prepare for their interviews  by:

- Studying  and  discussing  the  updated  summary  risk  story  with  an

appropriate member of the Mine Adoption Team to ensure that they have a

thorough  understanding  of  the  risks  being  addressed  by  the  leading

practice.

- Ensuring  that  they  are  fully  familiar  with  the  interviewer’s  briefing  and

guidance  provided  in  Appendix  A9, on  conducting  a  one-on-one  direct

interview properly.

- Practicing the interview at least once (perhaps with a mine adoption team

member), and finally,

- Reviewing with him their understanding of the interview process and how it

should be conducted and documented.

G8.5. Select persons to be interviewed

 The people selected  should range across the various categories  of adopters

and  stakeholders  in  such  a  way  as  to  ensure  good  representation  of  those

most involved in accomplishing adoption of the practice.

 The number of persons to be interviewed should be between 25 and 30. This

has  been  shown  to  be  an  appropriate  number  to  get  meaningful  interview

results.

 The sample should be drawn from across the entire mine and not just the site

selected to pilot the adoption process.

 Identifiers for the selected interviewees should be entered into the worksheet

of Appendix A8. The names of those to be interviewed should not be entered

as they should be kept confidential to the Mine Adoption Team.

G8.6. Conduct the interviews

 The  direct  enquiry  interview  questions  to  be  used  in  the  direct  enquiry

interviews are provided in Appendix A10. The interview seeks to establish the

following:

- Stakeholders/ Adopters beliefs about the causes and outcomes of the risk

- Stakeholders/ Adopters beliefs about the leading practice and how best to

protect people from the risk, and

- Stakeholders/Adopters beliefs about key leader behaviours and behavioural

communication needs

 Each  interviewer  should  schedule  all  of  their  allotted  interviews  to  be

conducted one-on-one in a place suitably private and free from noise and other

distractions.

 Interviewers should ask all questions fully, prompting for as complete and in-

depth  answers as  possible.  It is  the  prompting aspect  of  the  interviewing

procedure that should be focused upon in the practice sessions

 Interview  responses  should  be  carefully  documented  at  the  time  of  the

interview using the Interview Worksheet of Appendix A10 and the Interviewee’s

own words. It should be typed up to facilitate the analysis process.

 Recorders  may  be  used  to  assist  the  process  of  accurately  capturing  the

interviewees  responses,  but  only  if  the  interviewee  is  explicitly  asked  and

clearly gives approval.

G9. Customise generic behavioural plans

G9.1. Identify persons to analyse the interview results

 Persons capable of reliably summarising the interview results must be chosen

to undertake this work. A number of the members of the Mine Adoption Team

should be well suited for this task.

 Alternatively, the task may be assigned to two or more individuals associated

with the team and adoption effort, but not to only one person.

G9.2. Analyse results of direct enquiry interviews

 Each analyst must ensure that they have a sound understanding and familiarity

with  the  updated  expert  risk  model,  as  well  as  the  generic  mental  models

report provided in Appendix A12.

 Analysts must carefully read each set of interview responses and make notes

against key questions posed in the analysis worksheet of Appendix A11.

 Working alone, each analyst should read and note their observations against

the questions posed in the analysis worksheet.

 Once all interviews have been analysed in this way, the analysts should meet

in  a  group  session  to share  and  compare  the  results  of  their  analyses.  The

analysts should identify where  their individual analyses agree,  and why,  and

where they  disagree and  why.   Unresolved disagreements  between  analysts

should be noted.

 As a group the analysts should address the main questions in the worksheet

for  analysis,  writing  mutually  agreed  detailed  answers  to  the  questions,  and

identifying  the  most  influential  beliefs,  and  their  underlying  rationale  in  the

process of doing so.

 As a final check, the analysts should re-read the interviews to ensure that they

have  adequately  captured  and  described  the  key  beliefs  expressed  in  the

answers to  the questions asked of the stakeholders and adopters.

 Using  their completed  Appendix A11Analysis  Worksheet,  and  with  a  view  to

identifying  any  important  differences,  the  results  of  their  analyses  should  be

compared with the updated expert risk model and the generic mental models

report provided in Appendix A12. It is these differences that need to be taken

into account in customising the behavioural plans.

G9.3. Customise leadership behaviour and behavioural communication plans

 The Mine Adoption Team Manager and the Behavioural Plans Overseer must

ensure that they fully understand the leadership behaviour and the behavioural

communication plans and their derivation, before proceeding with the process

of customising the plan. These plans are provided in Part 3 in sections P3 and

P2 respectively.

 Customisation of the two behavioural plan must be based strictly on answers

to the guiding questions set out in the analysis worksheet of Appendix A11.

 New material to be introduced into either of the plans should be expressed in

the form of behavioural outcomes - actions that can be observed (what should

they  be  seen  to  do?)  or  the  expression  of  an  understanding  or  beliefs  in

particular circumstances (what should they be heard to say?).

 In  customising  the  behavioural  communication  plans  the  contents  of  each

communication  should  be  adjusted  to  take  account  of  the  answers  to  the

questions  in  Appendix  A11,  and  also  the modes of  communication  that  are

available at the mine

 The  material  in  the  generic  plans  should  be  taken  as  guidance  on  the

formulation  of  new  content.  Once  updated  each  of  the  customised  plans

should  be checked  and adjusted  to ensure  that  it  is  both  coherent  and  self-

consistent.

 The  Mine  Adoption  Team  Manager  should  liaise  with  the  MOSH  Adoption

Team  Manager  to  explore  the  possibility  of  having  the  customised  plan

reviewed, by either the MOSH Adoption Team Manager or by an appropriate

Specialist at the MOSH Learning Hub.

G9.4. Ensure that customisation checks have been fully satisfied

 The Behavioural Plans Overseer must ensure that that each of the 8 steps in

the  process  of  customising  the  behavioural  plans  has  been  properly  done

before allowing the team to progress to the next.

 On completion  of  the customisation process, a  final  overall check  should  be

done  jointly  by  the  Mine  Adoption  Team  Manager  and  the  Behaviour  Plans

Overseer

G9.5. Identify any new special communication requirements

 The Mine Adoption Team should critically review

the customised plans in relation to the example

materials provided with this guide to identify any

new  communication  material  considered

necessary,  such  as  signage,  posters,  slides,

video etc.

G9.6. Secure top management approval of customised behavioural plans

 Given the nature of the behavioural communication and leadership behaviour

plans, and their potential impact on the management culture at the mine, the

customised  behavioural  plans  should  be  presented  in  detail  to  top

management to get their buy-in and approval.

 The Mine Manager should be asked to explicitly approve implementation of the

plans

 In  presenting  the  plans,  the  results  of  the  direct  enquiry  process  should  be

highlighted – in particular the generic mental model and the new mine specific

findings  should  be  brought  out and  their  broad  implications  for  the  mine

discussed.

Points to consider in updating this section

 The  experience  gained  at  the  first  adoption  (or

demonstration) mine should be reviewed at the time of

updating  the  guide.  In  particular  the  review  should

focus  on  identifying  more  specific  guidance  about

sourcing  or  producing  some  of  the  key  materials

identified in the generic behaviour communication and

leadership behaviour plans.

G10. Harmonise leading practice with mine standards

G10.1. Review leading practice against current mine operational standards

 The operational details of the leading practice must be reviewed in relation to

mine standards to identify any potential conflicts or operational problems.

 The practicality and acceptability of the operational details in implementing the

leading  practice  should  also  be  tested  and  confirmed  with  the  operational

managers at the mine.

G10.2. Identify non-core adjustments to harmonise practice with mine standards

 Any changes or adjustments to the leading practice that need to be made to

harmonise  the  practice  with  mine  standards must be  carefully  assessed  to

ensure  that  they  do  not  detract  from  the  essence  and  effectiveness  of  the

leading practice.

 In  particular  the  identified  changes  must  not  impact  negatively  on  the  core

aspects of the leading practice.

 In  the  event  that  that  this  assessment  cannot  be  made  with  certainty,  the

MOSH Adoption Team Manager should be consulted.

G10.3. Adjust leading practice to harmonise with mine standards

 The Mine Adoption Team should  work out when and how best to  implement

and test the identified adjustments to harmonise the leading practice with mine

standards.

 If possible, this should be done before initiating the full piloting process.

 Details  of  successfully  implemented  harmonisation  adjustments  should  be

shared with members of the COPA.

G11. Assess risks and develop final adoption plan for approval

G11.1. Plan roll-out of adoption across the mine

 The  Mine  Adoption  Team  needs  to  initiate  planning  of  the  process  for

extending adoption of the leading practice across the mine at an early stage.

Such planning should involve:

- Obtaining input from the relevant operational managers at the mine.

- Scheduling  of  feedback  sessions  to  senior  management  and  operational

managers  on  progress,  problems

encountered and solutions found – see G7.

- Arrangements for operational persons to visit

the piloting site at appropriate times.

- Scheduling  of  the  envisaged  roll-out

activities.

Points to consider in updating this section

 The  experience  gained  at  the  first  adopter  (or

demonstration) mine should  be reviewed and used as

appropriate  when updating the guide, to provide more

specific  guidance  on  the  factors  that  need  to  be

considered  and  on  the  specific  steps  that  should  be

taken

G11.2. Conduct "what if" exercise and adjust plans as necessary

 Most mines routinely conduct a “what if” exercise in planning their project work

and a similar due diligence exercise is envisaged here, to  identify and put in

place any contingency plans considered necessary.

 Each  of  the  implementation  actions  should  be

systematically considered by  the  Mine  Adoption

Team in a session arranged for this purpose.

 The  adoption  implementation  plans  should  be

adjusted as necessary.

G11.3. Conduct risk assessment of planned changes

 In many respects the “what if” exercise should deliver the same outcomes as a

systematic  risk  assessment  of  the  planned

changes.  The  risk  assessment  must  however

involve  a  more  holistic  assessment.  In  practice

the  two  exercises  may  be  combined  and  be

outcomes  from  the  same  session  of  the  Mine

Adoption Team.

G11.4. Update and finalise adoption plan

 Having completed the planning process the adoption plan should be updated

to reflect any changes considered necessary and finalised for presentation to

top management at the mine. The plan should be in a convenient format and

form for on-going review and use.

G11.5. Clarify and agree criteria and time scale for completion of the project:

 The Mine  Adoption Team should critically  review  the  finalised  adoption  plan

and agree the criteria and timescale for completion of the adoption process.

 It is important to specify criteria for completion of the adoption process so that

both  the  Mine  Adoption  Team  and  Mine  Management  have  the  same

understanding of when the adoption process is complete.

 The  criteria  for  completion  should  include

successful  mine-wide  adoption  to  the  point

where the leading practice is operating to the

satisfaction  of  the  responsible  operational

management.

G11.6. Secure top management sign-off of adoption plan:

 In the event that top management has been kept properly informed of progress

and developments, a formal sign-off on the implementation plan may appear to

be  unnecessary  at  this  stage.  The  temptation  to  skip  this  step  should  be

resisted.

Points to consider in updating this section

 Based  on  experience  and  considerations  at  the  first

adoption  (or  demonstration)  mine,  when  updating  the

guide  it  may  be  possible  to  provide  more  definitive

guidance  in  regard  “what  if”  issues  that  should  be

considered.

 Based  on  experience  and  considerations  at  the  first

adoption (or  demonstration)  mine,  when  updating  the

guide the MOSH Adoption Team may elect to combine

points #35 and #36 into a single  point concerned with

risk management

 Based  on  experience  and  considerations  at  the  first

adoption (or demonstration) mine, it may be possible to

provide  more  definitive  guidance  in  regard  to  the

criteria for completion when updating the guide.

 Arrangements should thus be made to present  the finalised adoption plan  to

top management in order to maintain their involvement and support.

G12. Plan / develop training and communication materials

G12.1. Plan training necessary for successful adoption

 The  Mine  Adoption  Team  Manager,  the  Behaviour  Plans  Overseer, the

Training Manager and the Production Manager or his nominee should together

plan the training necessary for successful adoption of the leading practice.

 The starting point of this planning process should be an in-depth consideration

of the following:

- The  customised  leadership  behaviour  and  behavioural  communication

plans, to  identify  key  elements  that  need  to  be  built  into  the  training

materials  for  each  level  of  the  hierarchy  involved  in  adoption  of  the

practice.

- The example training materials included in this guide.

- Any special training requirements identified by equipment or other service

providers associated with supply of the leading practice.

 The mine’s existing training arrangements should then also be considered  in

relation to the findings from the above to clearly identify the scope and content

of the additional training considered necessary for successful adoption.

 A  schedule  of who  is  to  receive  what  training

and  when  should  then  be  developed  and

agreed,  initially  for  those  involved  in  the  pilot

adoption,  but  then  also  for  others involved  in

adoption  of  the  practice  as  it  is rolled-out

across the mine.

G12.2. Prepare training documentation

 The Mine Adoption Team Manager, the Training Manager, and the Behavioural

Plans Overseer should agree the responsibilities and procedures for preparing

the necessary training material and training lesson plans.

 The Training Manager and the Behavioural Plans Overseer should oversee the

process of  developing the necessary  training documents, and  for ensuring a

quality outcome.

G12.3. Develop required behavioural communications material

 The Behavioural  Plans Overseer  and the person at the mine responsible for

developing mine communications material should meet to  review and decide

upon how best to produce all of the behavioural communications materials that

arise  from  the  behavioural  communication  and  leadership  behaviour  plans.

Much of this will be for use in the training programme, but some should also be

for  use  elsewhere,  such  as  in  the  briefing  sessions and  in  various  other

operational situations not covered in the training programme.

 The Behavioural Plans Overseer must ensure that materials produced are of

acceptable  quality,  and  that  they  are  produced in  good  time  for  use  as

planned.

Points to consider in updating this section

 The  training  implemented  at  the  first  adopter  (or

demonstration)  mine  should  be  reviewed  to  identify

any additional guidance that could be added when the

guide is updated and finalised.

 In  particular,  ways  of  avoiding  or  dealing  any

particular  difficulties  that  might  arise  in  this  planning

process should be provided.

G12.4. Prepare documentation / signage to assist in implementing the practice

 The  Mine  Adoption Team Manager and  the  Behaviour  Plans Overseer must

together identify and arrange for production any additional documents, posters,

and signage needed to secure successful adoption of the leading practice.

 Together  they  must  ensure  that  all  of  the  communication  materials  for

successful  implementation  of  the adoption  process  have  been  identified  and

appropriately addressed in one way or another.

G13. Brief and train key mine persons

G13.1. Brief supervisory levels involved in adopting the practice

 The Mine Adoption Team Manager should discuss and agree arrangements for

briefing supervisors and workers involved in adoption the leading practice.

 The  first  of  the  two  briefings  should  be  held  soon  after  identifying  the  key

stakeholders and adopters involved in the adoption process. The primary point

of  the  initial  briefing  should  be  to  explain  the direct  enquiry  process  to  alert

them  to  the  fact  that  certain  people  would  be  selected  to  participate  in

confidential interviews to make input into the adoption process.

 It should also be explained that in due course all people involved in adoption of

the leading practice would receive appropriate training.

 A  brief  description  of  the  practice  should  also  be  given  and  an  opportunity

provided  for  any  uncertainties  to  be  raised  and  addressed  either  then  or  in

follow-up sessions.

 The need for workers to be properly briefed about what lies ahead should also

be appropriately covered.

 The second of the two briefings should be held prior to implementation of the

training  programme.  The  Mine  Adoption  Team

Manager  should  brief  all  supervisors  of  the

training  and  other  arrangements  relevant  to

implementation of the adoption process.

 As  part  of  this  briefing,  and  as  an  aide  memoir,

the  supervisors  should  be  provided  with  a  schedule  setting  out  details  and

timing  of  their  and  their  staff’s  training,  as  well  as  a  brief  document

summarising key operational aspects of the adoption process.

Points to consider in updating this section

 Based  on  the  experience  gained  at  the  first  adoption

(or  demonstration) mine, when updating  the guide  the

MOSH Adoption Team may be in a position to provide

more specific information and guidance of the content

of these briefings

G13.2. Brief the workers involved in adopting the practice

 The  first  of  the two  briefings supervisors  must  be  focused  on  informing  staff

about the direct enquiry process to obtain input into the adoption process, and

in  which  some  staff  from  all  levels  will  be  invited  to  participate,  and  that  all

persons  involved  with the practice  would be  appropriately  trained  prior  to  its

adoption.

 A  brief  description  of  the practice  should  also  be  given  and  an  opportunity

provided  for any  uncertainties  to  be  raised  and  addressed,  either  then or  in

follow-up sessions if necessary.

 In the second of the two briefings, details about the nature and timing of the

impending training should be provided, along with

any other detail considered necessary prior to the

training sessions. The  briefing  may also  include

delivery  of  certain  elements  of  the  behavioural

communications plan.

G13.3. Implement aspects of the two behavioural plans not included in training

 Much of  the  behavioural  communication  and  leadership  behaviour plans  will

have been integrated into the training programme in one way or another (some

for delivery directly by the trainer, and some to be provided to supervisors for

their use in operational communications with those who report to them).

 Those aspects of the two behavioural plans that are not included in the training

programme should  be  identified  by  the  Mine  Adoption  Team,  along  with  the

persons  responsible  for  their  delivery  or  for  ensuring  that  they  are

implemented. This may involve persons at higher levels of management.

 The Mine Adoption Team Manager along with the Behaviour Plans Overseer

should  arrange  to  meet  with  these  people individually  or  collectively as

appropriate to properly brief them on what is required, to clarify any points of

uncertainty, and to provide them with the necessary communication material.

 Follow up sessions with various individuals should be arranged as necessary

to ensure a full understanding of what is required.

G13.4. Train the persons involved in adopting the practice

 Initiate the training process according to the training programme that has been

developed, with the initial focus being on those who require training to enable

successful adoption of the leading practice at the piloting site.

 Follow-on with the training programme according to plan, which should extend

right  through  to completion of  the mine-wide  roll-out  process  for  the  leading

practice.

Points to consider in updating this section

 When  updating  the  guide,  the MOSH Adoption  Team

may  be  in  a  position  to  provide  more  specific

information  and  guidance  of  the  content  of  these

briefings  and  this  section  should  be  expanded  to

accommodate such guidance.

G14. Implement pilot adoption of the practice

G14.1. Arrange access to any required intellectual property

 As indicated in the example adoption plan, access to any required intellectual

property should be one of the first actions taken by the Mine Adoption Team.

This  requirement  should  seldom  arise. However,  when  it  does,  the  need  to

obtain such access and the process for doing so should be highlighted at the

time  of  presenting  the  case  to  top  management  for  adopting  the  leading

practice.

 The  Mine  Adoption  Team  Manager,  in  liaison

with  the  Group  Adoption  Coordinator and  with

the  support  of  legal  counsel  when  necessary,

should  secure  access  to  the  required

intellectual  property  if  the  Group  has  not

already done so previously.

G14.2. Arrange purchase of the required equipment

 As with intellectual property, arrangements for the purchase of the equipment

may need to start at a time similar to that of arranging access to any required

intellectual property, particularly if long delivery times apply, or if the purchase

is subject to a lengthy capital approval process.

 Depending on the time scale on the procurement

process,  scheduling  of  the  various  adoption

activities may need to be substantially  adjusted,

and perhaps to some extent reordered.

G14.3. Set up the required maintenance arrangements

 The Mine Adoption Team Manager must arrange for any required maintenance

arrangements to  be  set  up  as  an  integral  part  of  the  leading  practice,  as

outlined in PART 3 of this guide.

 In  doing  so,  any  aspects  of  the  behavioural

plans  that  are  applicable  to  the  maintenance

arrangements should also be put in place.

G14.4. Conduct preliminary pilot-scale adoption of the practice

 Most of the arrangements for implementing the practice at the pilot site should

already  have  been  taken  through  the  training  or  briefing  activities  outlined

above.

 The Mine Adoption Team Manager should meet

with  the  team  of  supervisors  responsible  for

installing  the  required  equipment  and  or

procedures  to  arrange  implementation the practice, and to deal with any other issues that need attention, including those raised by the operational supervisors.

Points to consider in updating this section

 In the  event that  there is a need to  acquire access to

intellectual property the MOSH Adoption Team should

provide clear detail about this in PART 3 of the guide.

 This section should include reference to that detail, as

well  as  setting  out  more  specific  detail  that  would  be

appropriate to add here

 The experience at the first  adoption (or  demonstration)

mine could point to more specific guidance that should

be included in this section when the guide is updated.

 Based  on  experience  and  considerations  at  the  first

adopter  (or  demonstration)  mine,  the MOSH Adoption

Team may  be  able  to  provide  additional  guidance  on

this point.

 Based  on  experience  and  considerations  at  the  first

adoption  (or  demonstration)  mine,  when  preparing  or

updating the guide the MOSH Adoption Team may be

able to provide more specific guidance on this point.

G15. Monitor, evaluate and report on performance

G15.1. Set up monitoring and data collection arrangements

 The  Mine  Adoption  Team  manager  should

ensure  that  effective  arrangements  are  put  in

place for  making  and  recording  the  necessary

measurements, and for gathering any other data

needed  to assess  the performance and  impact of  the  leading  practice  being

adopted.

G15.2. Implement the monitoring and reporting programme

 The Mine Adoption Team Manager must ensure consistent implementation of

the monitoring and  reporting  arrangements  that have been put in place,  that

that quality gathered data is being gathered, and regularly reported.

G15.3. Store key data in an electronic data base for later analysis

 The Mine Adoption Team Manager should ensure that all data is entered into

an electronic data base for later analysis. This should be seen as an integral

part of activities G15.1 and G15.2

G15.4. Analyse data to establish the performance and impact of the practice

 Once  sufficient  data  has  been  collected,  the  Mine  Adoption  Team  Manager

should arrange for the data to be analysed to establish the performance of the

practice and the impact that it has had at the mine.

 This should be written up in the form of a brief report for presentation to key

stakeholders, starting with top management, who should be given the chance

to comment on the report before it is finalised for wider distribution.

 The  report  should  then  be  distributed  to  all

key  stakeholders,  including  those  directly

involved in the adoption process. Supervisors

should be tasked with sharing outcomes with

their staff at the earliest opportunity.

 At least one follow up report should be prepared within the next 6 to 12 months

to  identify  any  longer-term  impacts,  and  consistency  of  the  performance

achieved.

G15.5. Report on adoption and performance achieved - to COPA

 In  the  example  adoption  plan  provided  in  Appendix  A1,  a  number  of  the

activities are identified as key milestones. The Mine Adoption Team Manager

should  advise  the MOSH Adoption Team  Manager  when  each  of  these  key

milestone activities have been completed. This will assist in keeping the COPA

and  Executive  Management  in  Industry  advised  of  the  extent  to  which  the

leading practice has been adopted at mines.

 On completion of the brief report referred to in point G15.4, the Mine Adoption

Team  Manager  should  arrange  to make  a  presentation  at  a COPA  meeting

about the mine’s experience in adopting the leading practice.

Points to consider in updating this section

 Based  on  experience  and  considerations  at  the  first

adoption  (or  demonstration)  mine,  when  updating  the

guide  the  MOSH  Adoption  Team  may  be  able  to

provide more specific guidance on this point.

 Based  on  experience  and  considerations  at  the  first

adoption  (or  demonstration)  mine,  when  updating  the

guide  the  MOSH  Adoption  Team  may  be  able  to

provide more specific guidance on this point.

G16. Finalise and implement mine-wide roll-out plan

G16.1. Decide/document any refinement to practice prior to roll-out

 The Mine Adoption Team Manager must monitor progress at the piloting site

closely to identify any particular difficulties encountered. Any special measures

taken to address such difficulties should be carefully documented.

 Depending  on  operating  experience  during  of  the  piloting  phase,  at  an

appropriate time the Mine Adoption Team Manager should convene a meeting

to  review  the  adoption  experience  and  consider  and  decide  whether  any

refinements to the practice are necessary.

G16.2. Introduce and confirm effectiveness of identified refinements

 In the event that some form of refinement is considered necessary, the Mine

Adoption  Team  should  arrange  for  any  necessary  refinements  to  be

implemented  and  tested  until  their  effectiveness  has been  satisfactorily

confirmed.

 The details of the refinements introduced should then be documented in detail

to  ensure  consistent  implementation  as  the  practice  is  rolled-out  across  the

mine.  Details  of  the  refinement  should  be  provided  to  the  MOSH  Adoption

Team Manager for presentation at a future COPA meeting.

G16.3. Finalise plans and commence mine-wide roll-out

 As  soon  as  the  leading practice  is  working  satisfactorily  at  the pilot  site,  the

roll-out process should be initiated.

 This should begin with a critical review of the roll-out plans developed earlier,

to  identify  any  adjustments  that  may  need  to  be  made  to  take  account  of

experience to date.

 Once these adjustments have been made an effectively communicated to all

concerned, implementation of the roll-out plan should proceed.