## EE&MS (hidden)
0
MOSH FOG Adoption Programme Monitor for the Adoption of the Leading Practice for Entry Examination and Making Safe May 2013
[9 empty] | Leading Practice Adoption Process Review (Yes = Y, No = N) | [6 empty] | I = In Progress C = Completed S = Signed Off | [12 empty] | I = In Progress C = Completed S = Signed Off
COPA | Commodity | No. | Name of Mine | Company | Name of Manager | Name of Project Leader | E-mail Address of Project Leader | Telephone Number | Do you have a FOG Risk associated with Entry Examination and Making Safe | Do you have FOG Risk Controls in place | Do you have a Procedure on Entry Examination and Making Safe | Is your FOG related LTIFR<0,05 | Have you considered the Adoption of the Leading Practice on Examination and Making Safe | Yes, we want to Adopt the Leading Practice on Examination and Making Safe | No, we do not want to Adopt the Leading Practice on Examination and Making Safe | Leading Practice Adoption Review | Implementation Plan | Procedure Amended | Mental Model Interviews | Leadership Behaviour Plan | Behaviour Communication Plan | Risk Assessment | Training Lesson Plans | Management Review Process | Roll-out plan in place | No. of Crews to Train | No. of Crews Trained | Progress | Signed Off Factor | [9 empty] | Completion Factor | [9 empty] | In Progress Factor | [9 empty] | Progress Table
|  | 1 | Finsch Diamond Mine | Petra Diamonds | Mr. Luctor Roode |  |  |  | Y | Y | Y | Y | Y | Y |  | I | [9 empty] | 17 |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0% | 0%
|  | 2 | Koffiefontein Diamond Mine | Petra Diamonds | Mr. P Coetzee | Mr. S Nxele | siphon@petradiamonds.com | 0734401876 | Y | Y | Y | Y | Y | Y |  | I | I | I | I | I | I |  |  |  |  | 18 |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0% | 0%
|  | 3 | Cullinan Diamond Mine | Petra Diamonds | Mr. Cor Bactus | Ms. H Sealey |  |  | Y | Y | Y | Y | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 15 | 15 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 4 | Venetia Diamond Mine | De Beers Cons. |  |  |  |  | Y | Y | Y | Y | Y | Y |  | I | [9 empty] | 4 |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0% | 0%
|  | 5 | Black Rock Mine | ARM |  |  |  |  | Y | Y | Y | Y | Y | Y |  | I | [9 empty] | 52 |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0% | 0%
|  | 6 | Kimberley Diamond Mines | Petra Diamonds | Mr. S Klopper | Mr. M Spadone | marlons@patradiamonds.com | 0728589041 | Y | Y | Y | Y | Y | Y |  | I | I | I | I | I | I |  |  |  |  | 12 |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0% | 0%
|  | 7 | Ya Rona - Pitseng | Gold Fields KDC West | Mr. M Kriel | Mr. Dennis Mc Dougall | denis.mcdougall@goldfields.co.za | 0187818722/0824511708 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 65 | 65 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 8 | West Section | Gold Fields Beatrix | Mr.B Haumann | Mr. Deon Louw | deon.louw@goldfields.co.za | 057 73 8405 / 082 850 8725 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 74 | 74 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 9 | Unisel Operation | Harmony | Mr. S Green | Mr. Marius Barnard | marius.barnardjn@harmony.co.za | 0724965737 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 29 | 29 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 10 | Union Mine | Anglo Platinum | Mr. M Nzimande | Mr A Mabotja | abramm@angloplat.com | 0834550931 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 488 | 488 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 11 | Impala Platinum Mines | Impala Platinum | ? | Mr. N Fernandes | noel.fernandes@implats.co.za |  | Source Mine | [6 empty] | S | S | S | S | S | S | S | S | S | S | 459 | 459 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 12 | Mponeng | AngloGold Ashanti | Mr. R Rademann | Mr. M Gillespie | mgillespie@anglogoldashanti.com | (018) 700-5455 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 441 | 441 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 13 | Khuseleka | Anglo Platinum | Mr. T van den Berg | Mr. J Boshielo | jboshielo@angloplat.com | 083 461 3822 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 388 | 388 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 14 | Thembalani | Anglo Platinum | Mr. P Tobias | Mr. D Oberholzer | doberholzer@angloplat.com | 834556997 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 264 | 264 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 15 | Rowland | Lonmin | Mr. E Hamman | Mr. J Erasmus | Jacques.Erasmus@lonmin.com | 0828537801 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 191 | 191 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 16 | Marula | Impala Platinum | Mr. J Pretorius | Mr. D Venter | Dawie.venter@implats.co.za | 013 214 6001 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 190 | 190 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 17 | Kloof 4 shaft | Gold Fields KDC East | ? | Mr. Dennis Mc Dougall | denis.mcdougall@goldfields.co.za | 084 597 6625 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 189 | 189 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 18 | Khomanani | Anglo Platinum | Mr. R Rudolph | Mr. C Grobler | carelg@angloplat.com | 0732516183 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 180 | 180 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 19 | Moab Khotsong | AngloGold Ashanti | Mr. J Ferreira | Mr. B Swanepoel | bswanepoel@anglogoldashanti.com | (018) 478-1918 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 170 | 170 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 20 | TauTona | AngloGold Ashanti | Mr. A van Jaarsveld | Mr. D Davies | ddavies@anglogoldashanti.com | (018) 700-8963 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 154 | 154 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 21 | Modikwa | Anglo Platinum | Mr. S O'Connor | Dr. J Lidderd | jlidderd@modikwa.co.za | 013 230 2050 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 150 | 150 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 22 | Bambisanani/Khomanane | Gold Fields KDC West | Mr. Z Moni | Mr. Dennis Mc Dougall | denis.mcdougall@goldfields.co.za | 0187818722/0824511708 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 150 | 150 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 23 | Great Noligwa | AngloGold Ashanti | Mr. E Mohlabi | Mr. GE White | gewhite@anglogoldashanti.com | (018) 478-8057 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 145 | 145 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 24 | Hlanganani | Gold Fields KDC West | Mr. F Smith | Mr. Dennis Mc Dougall | denis.mcdougall@goldfields.co.za | 0187818722/0824511708 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 141 | 141 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 25 | Evander | Harmony | Mr. M da Silva | Mr. Marius Pelser | marius.pelser@harmony.co.za | O824411266 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 138 | 138 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 26 | Dishaba | Anglo Platinum | Mr. JJ Joubert | Mr. K Letebele | kletebele@angloplat.com | 0835793846 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 129 | 129 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 27 | Kopanang | AngloGold Ashanti | Mr. F Naude | Mr. J Booysen | jbooysen@anglogoldashanti.com | (018) 478-9989 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 117 | 117 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 28 | Tumela | Anglo Platinum | Mr. P van Dorssen | Mr. L Kadi | lkadi@angloplat.com | 014 784 1278 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 116 | 116 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 29 | North Section | Gold Fields Beatrix | Mr.B Haumann | Mr. Deon Louw | deon.louw@goldfields.co.za | 057 73 8405 / 082 850 8725 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 116 | 116 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 30 | Masakhane | Gold Fields KDC West | Mr. T Uys | Mr. Dennis Mc Dougall | denis.mcdougall@goldfields.co.za | 0187818722/0824511708 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 110 | 110 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 31 | Blyvooruitzicht | DRD | Mr. P Watters | Mr. W Nelson | Willie.nelson@za.drdgold.com |  | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 90 | 90 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 32 | Siphumelele | Anglo Platinum | Mr. I Mannini | Mr. W Reader | reader@angloplat.com | 083 455 8177 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 85 | 85 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 33 | West Section | Gold Fields Beatrix | Mr.B Haumann | Mr. Deon Louw | deon.louw@goldfields.co.za | 057 73 8405 / 082 850 8725 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 74 | 74 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 34 | Bathopele | Anglo Platinum | Mr. L Labuchagne | Mr. A Diedericks | braam.diedericks@angloplat.com | 083 455 2273 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 70 | 70 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 35 | Ya Rona - Pitseng | Gold Fields KDC West | Mr. M Kriel | Mr. Dennis Mc Dougall | denis.mcdougall@goldfields.co.za | 0187818722/0824511708 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 65 | 65 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 36 | Kroondal Chrome Mine | Xstrata | Mr. R Murley | M Prinsloo & R v Rooyen | mprinsloo@xstrata.co.za | 082 871 3552 or 083 587 1167 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 64 | 64 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 37 | Doornkop | Harmony | Mr. B van Zyl | Mr. Jacques Du Triou | jacques.dutriou@harmony.co.za | O829268898 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 60 | 60 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 38 | Smokey Hills | Platinum Australia SA | Mr. W Smart | Mr. D Comley | dcomley@platinumaus.com | 079 697 1663 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 54 | 54 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 39 | Mototolo | Xstrata - Eastern Platinum | Mr J van Tonder | Mr P Garner | pgarner@xstrata.co.za | 082 921 9441 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 48 | 48 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 40 | Dilokong Chrome Mine | ASA Metals | Mr. J. J van Rensburg | Mr L Kruger | lkruger@asametals.co.za | 0826062656/0132307855 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 47 | 47 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 41 | Bambanani | Harmony | Mr. Z Ndese | Mr. Maurice Mkhwanazi | maurice.mkwanazi@harmony.co.za | O832870330 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 45 | 45 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 42 | Waterval Chrome Mine | Xstrata | Mr. V Makuni | M Prinsloo & R v Rooyen | mprinsloo@xstrata.co.za | 082 871 3552 or 083 587 1167 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 45 | 45 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 43 | South section | Gold Fields Beatrix | Mr.B Haumann | Mr. Deon Louw | deon.louw@goldfields.co.za | 057 73 8405 / 082 850 8725 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 43 | 43 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 44 | Dwarsrivier | ASSMANG | Mr. F Uys | Mr. K Kasselmann | kassiek@dwarsrivier.co.za | 082 305 0868 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 36 | 36 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 45 | Horizon Chrome Mine | Xstrata | Mr. D Ngubane | M Prinsloo & R v Rooyen | mprinsloo@xstrata.co.za | 082 871 3552 or 083 587 1167 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 34 | 34 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 46 | Joel | Harmony | Mr. K Moagi | Mr. Warren Freeman | warren.freeman@harmony.co.za | O847016876 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 33 | 33 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 47 | Unisel Operation | Harmony | Mr. S Green | Mr. Marius Barnard | marius.barnardjn@harmony.co.za | 0724965737 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 29 | 29 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 48 | Arnot Colliery | Exxaro Coal | Mr. C van Deventer | Mr. George Cronje | George.cronje@exxaro.com | 072 330 6063 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 28 | 28 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 49 | Twickenham | Anglo Platinum | Mr. M Mutangwa | Mr T Erasmus | terasmus@angloplat.com | 0824586587 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 24 | 24 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 50 | Thorncliffe | Xstrata - Eastern Chrome | Mr L Murenzvi | Mr P Garner | pgarner@xstrata.co.za | 082 921 9441 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 24 | 24 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 51 | Two Rivers | ARM | Mr. A de Beer | Mr A Esterhuizen | andre.esterhuizen@trp.co.za | 0722146942 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 15 | 15 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 52 | Helena | Xstrata - Eastern Chrome | Mr. D Sammons | Mr P Garner | pgarner@xstrata.co.za | 082 921 9441 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 15 | 15 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 53 | Nkomati | ARM | Mr. L Motshwaiwa | Mr. L Motshwaiwa | lazarus.motshwaiwa@nkomati.co.za | 082 783 4182 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 14 | 14 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 54 | Thembalani 2 | Anglo Platinum | Mr. J B Robinson | Mr. Petrus Molise | pmolise@angloplat.com | 0727185254 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 7 | 7 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 55 | Magareng | Xstrata | Mr. D Sammons | Mr P Garner | pgarner@xstrata.co.za | 082 921 9441 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 2 | 2 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 56 | Kusasalethu | Harmony | Mr. T Keyter | Mr. Francois Cronje | francois.cronje@harmony.co.za | O833789413 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 132 | 132 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 57 | Tshepong | Harmony | Mr. F Janse van Rensburg | Mr. Willem Gouws | willem.gouws@harmony.co.za | O836070850 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 132 | 132 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 58 | Phakisa / Nyala | Harmony | Mr. B Nel | Mr. Marcus Maree | marcus.maree@harmony.co.za | O579167293 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 76 | 76 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 59 | Bokoni Mine | Anooraq | Mr. B Wessels | Mr. P Labuschagne | pierrelabuschagne@atlatsa.com | 082 788 6675 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 93 | 93 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 60 | Masimong 4,5 | Harmony | Mr. H Bornman | Mr. Geoffrey Acheampong | geoffrey.acheampong@harmony.co.za | O579105967 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 84 | 84 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 61 | Target | Harmony | Mr. A Sobreira | Mr. Danie Botha | danie.botha1@harmony.co.za | 0832569140 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 40 | 40 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 62 | Kloof 1 Shaft | Gold Fields KDC East |  | Mr. Dennis Mc Dougall | denis.mcdougall@goldfields.co.za | 0824429878 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 143 | 143 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 63 | Kloof 3 Shaft | Gold Fields KDC East |  | Mr. Dennis Mc Dougall | denis.mcdougall@goldfields.co.za | 0824429879 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 120 | 120 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 64 | Kloof 8 Shaft | Gold Fields KDC East |  | Mr. Dennis Mc Dougall | denis.mcdougall@goldfields.co.za | 0824429880 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 102 | 102 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 65 | Kloof 7 Shaft | Gold Fields KDC East |  | Mr. Dennis Mc Dougall | denis.mcdougall@goldfields.co.za | 0824429881 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 89 | 89 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 66 | Black Rock Mining Operations | ASSMANG | Mr C Melamu | Mr C Melamu | cmelamu@brmo.co.za | 072 369 4602 | Y | Y | Y | N | Y | Y |  | S | S | S | S | I | I |  |  |  |  | 24 |  | 40% | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | [5 empty] | 0 | 40% | 0%
|  | 67 | Tau Lekoa | Village Main |  | Ms. Maria Mogaledi | MariaMog@buf-simmers.co.za | (018) 478-5436 | Y | Y | Y | N | Y | Y |  | S | S | I | I | [6 empty] | 88 |  | 20% | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | [7 empty] | 0 | 20% | 0%
|  | 68 | Newman | Lonmin | Mr. Molefi Mohau | Mr. I Goolam | imraan.goolam@lonmin.co.za | 828021074 | Y | Y | Y | N | Y | Y |  | S | S | I | [7 empty] | 19 |  | 20% | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | [7 empty] | 0 | 20% | 0%
|  | 69 | Elands Platinum | Xstrata | Mr R O'Reilly | Mr. B Isitt | bissit@xstrata.co.za | 0744965150 | Y | Y | Y | N | Y | Y |  | S | S | I | C | [6 empty] | 15 |  | 20% | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | [7 empty] | 0 | 20% | 0%
|  | 70 | Twin Shaft | Gold Fields South Deep | Mr. D Geyser | Dr. Bryan Watson | bryan.watson@goldfields.co.za | 0724753154 / 0114111314 | Y | Y | Y | N | Y |  | Y | S |  | Leading Practice not Applicable | [7 empty] | 1 | 1 | 20% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | 1 | 10% | 10%
|  | 71 | South Shaft | Gold Fields South Deep | Mr. D Geyser | Dr. Bryan Watson | bryan.watson@goldfields.co.za | 0724753154 / 0114111314 | Y | Y | Y | N | Y |  | Y | S |  | Leading Practice not Applicable | [7 empty] | 1 | 1 | 20% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | 1 | 10% | 10%
|  | 72 | Eastern Chrome Mines | SAMANCOR |  | Mr. Frank Cottonn | Frank.Cotton@SamancorCr.com | 0828083301 | Y | Y | Y | N | Y | Y |  | S | I | [8 empty] | 22 |  | 10% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | 0 | 10% | 0%
|  | 73 | Sasol Coal (Middelbult) | Sasol | Mr P Jordaan | Mr Lood Boshoff | Lood.boshoff@sasol.com | 082 571 5571 | Y | Y | Y | N | Y | Y |  | S | I | I | [7 empty] | 38 |  | 10% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | 0 | 10% | 0%
|  | 74 | Cooke Section | Gold One | Mr. N James | Mr. JC Smith | jc.smith@randuranium.co.za | 0823369215 | Y | Y | Y | N | Y | Y |  | I | [9 empty] | 12 |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0% | 0%
|  | 75 | Royal Bafokeng Rasimone Platinum Mine | Royal Bafokeng RasimoneMr. M Harris |  | Mr. P Coetzer | phillipc@bafokengplatinum.co.za | 08334552221 | Y | Y | Y | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 68 | 56 | 98.24% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.82353 | 90% | 8.235%
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
|  | Number of Units Signed Off | [13 empty] | 69 | 65 | 62 | 62 | 61 | 61 | 61 | 61 | 61 | 61 | 7062 | 6729 |  | 69 | 65 | 62 | 62 | 61 | 61 | 61 | 61 | 61 | 61 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 69 | 65 | 62 | 62 | 61 | 61 | 61 | 61 | 61 | #DIV/0! |  | 9.528%
|  | Percentage of Units with Documents Signed Off | [13 empty] | 92% | 86.67% | 82.67% | 82.67% | 81.33% | 81.33% | 81.33% | 81.33% | 81.33% | 81.33% | 95.28% |  |  | 92% | 86.67% | 82.67% | 82.67% | 81.33% | 81.33% | 81.33% | 81.33% | 81.33% | 81.33% | 0% | 0% | 0% | 1.333% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 5.333% | 8% | 4% | 4% | 4% | 0% | 0% | 0% | 0% | 92% | 86.67% | 82.67% | 82.67% | 81.33% | 81.33% | 81.33% | 81.33% | 81.33% | #DIV/0!
|  | Percentage of Units Completed not Signed Off | [13 empty] | 0% | 0% | 0% | 1.333% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Percentage of Units with Work In Progress | [13 empty] | 8% | 5.333% | 8% | 4% | 4% | 4% | 0% | 0% | 0% | 0%
|  | Percentage of Units No Action | [13 empty] | 0% | 8% | 9.333% | 12% | 14.67% | 14.67% | 18.67% | 18.67% | 18.67% | 18.67%

## Nets with Bolts (hidden)
MOSH FOG Adoption Programme Monitor for the Adoption of the Leading Practice for Applying Nets with Bolts in Narrow Reef Hard Rock Workings May 2013
Number | Name of Mine | Company | Name of Manager | Name of Project Leader | E-mail Address of Project Leader | Telephone Number | Do you have a FOG Risk associated with nets with bolts? | Do you have FOG Risk Controls in place | Do you have a Procedure on the applicationof Bolts with Nets | Is your FOG related LTIFR<0,05 | Have you considered the Adoption of the Leading Practice on Nets with Bolts | Yes, we want to Adopt the Leading Practice on Nets with Bolts | No, we do not want to Adopt the Leading Practice on Nets with Bolts | Leading Practice Adoption Review | Implementation Plan | Procedure Amended | Mental Model Interviews | Leadership Behaviour Plan | Behaviour Communication Plan | Risk Assessment | Training Lesson Plans | Management Review Process | Roll-out plan in place | No. of Crews to Train | No. of Crews Trained | Total Number of employees | Progress
1 | Masimong 5 | Harmony |  | Rusiano Tsoka | rusiano.tsoka@harmony.co.za | 829271018 | y | Y | Y | Y | Y |  |  | S | S | S | [7 empty] | 58 | 0 |  | 0%
2 | Savuka | Anglo Gold Ashanti |  | Thembinkosi Madondo | mmadondo@anglogoldashanti.com | 187006279 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | I | 12 | 3 |  | 2.273%
3 | Kopanang | Anglo Gold Ashanti | Francois Naude |  | fnaude@anglogoldashanti.com | 713635097 | y | y | y | y | y |  |  | S | S | S | I | I | I | I | I | I | I | 63 | 0 |  | 0%
4 | Target 1 | Harmony |  | Marius Van der Merwe | marius.vandermerwe@harmony.co.za | 0723684289/0574524445 | y | y | y | y | y |  |  | S | S | S | S | S | I |  |  |  |  | 8 | 3 |  | 3.409%
5 | Phakisa | Harmony | Rudi Phillis | Tienie Landman | Tienie.Landman@Harmony.co.za | 579167111 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 51 | 39 |  | 6.952%
6 | Eastern Mines | Xstrata Alloys |  | Phil Garner | pgarner@xstrata.co.za | 829219441 | y | y | y | y | y |  |  | I | [9 empty] | 45 |  |  | 0%
7 | Mponeng | Anglo Gold Ashanti | Randel Rademan |  | crrademann@anglogoldashanti.com | 187005450 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | I | I | S | 69 | 14 |  | 1.845%
8 | Target 3 | Harmony |  | Velaphi Waganda | velaphi.waganda@harmony.co.za | 579074114 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 21 | 21 |  | 9.091%
9 | Joel | Harmony |  | Warren Freeman | Warren.Freeman@harmony.co.za | 847016876 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 33 | 33 |  | 9.091%
10 | TauTona | Anglo Gold Ashanti | Andre van Jaarsveld | Danny Davis | ddavies@anglogoldashanti.com | 187008963 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | I | 53 | 4 |  | 0.6861%
11 | Impala (UG2) | Impala | Mathias Sithole |  | Mathias.sithole@implats.co.za | 829431572 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 313 | 22 |  | 0.639%
12 | Impala (Merensky) | Impala | Nelson Ndlala |  | nelson.ndlala@implats.co.za | 829410912 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 300 | 240 |  | 7.273%
13 | Kusasalethu | Harmony | Theo Keyter |  | Theo.Keyter@harmony.co.za | 187829152 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 72 | 72 |  | 9.091%
14 | Bambanani Mine | Harmony | Pieter Fourie | Pieter Fourie | Pieter.Fourie@harmony.co.za | 829403283 | y | y | y | y | y |  |  | C | C | C | C | C | C | C | C | C | C | 55 | 50 |  | 8.264%
15 | Doornkop Mine | Harmony | Jaques Du Triou | Bennie Nelson | Jacobus.Nelson@harmony.co.za | 112786712 | y | y | y | y | y | y |  | S | S | S | S | S | S | S | S | S | S | 49 | 49 | 3734 | 9.091%
16 | Tshepong | Harmony | Adriano Sobreira | Kenny Makgakga | Kenny.makgakga@harmony.co.za | 0579072188/0828801325 | y | y | y | y | y |  |  | S | S | S | I | I | I | I | I | I | I | 88 | 36 | 3000 | 3.719%
17 | Lonmin | Lonmin |  | Eddie Landsberg | Eddie.landsberg@lonmin.com | 836074875 | y | y | y | y | y |  |  | S | S | S | S | I | I | S | S |  |  | 219 | 150 |  | 6.227%
18 | Evander | Harmony | Manny Da Silva | Wynand Van Der Mesch | wynand.van der Mescht@harmony.co.za | 0176201606/0834243001 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | I | I | I | 21 | 0 |  | 0%
19 | Bafokeng Rasimone (M) | Royal Bafokeng Platinum | Glenn Harris | Chisto Haasbroek | christoh@Bafokengplatinum.co.za |  | y | y | y | y | y |  |  | S | S | S | I | I | I | S | S | I | S | 100 | 0 |  | 0%
20 | Rasimone UG2 | [12 empty] | S | S | S | S | S | S | S | S | S | S | 30 | 30 |  | 9.091%
21 | Sibanye Gold(Kloof & Dries) | Gold Fields | Henry Barnard |  | Henry.barnard@goldfields.co.za |  | y | y | y | y | y |  |  | C | C | C | S | C | S | C | C | I | C | 334 | 8 | 6359 | 0.2177%
22 | Kalgold (Not Applicable) | Harmony |  | Motoma Modise | Modise.motoma@harmony.co.za |  | y | y | y | y | y |  |  | S | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
23 | Great Noligwa | Anglo Gold Ashanti | Noah Mabunda | [10 empty] | S | [9 empty] | 37 | 0 |  | 0%
24 | UNISEL (NOT REGISTERED) | [5 empty] | Y | Y | Y | Y | Y | Y |  | S | S | S | S | S | S | S | I |  |  | 27 | 27 |  | 9.091%
25 | Modikwa | AAP Impala | [11 empty] | S | S | I | I | I | I | S | S | S | S | 47 | 47 |  | 9.091%
26 | MOAB KHOTSONG (NOT REGISTERED) |  |  | Johan Oelofse |  |  | Y | Y | Y | Y | Y | Y |  | S | S | S | I | I | I | I | I |  |  | 46 |  |  | 0%
27 | COOKE 4 Ezulwini | [12 empty] | I
NB - All AngloAmerican Platinum Underground Mines adhere to the practice of Nets with Bolts in their Stopes (Source Mines)
NB - KDC Comprises of Kloof Mines and Driefontein Mines of thye Sibanye Group and consist of a number of shafts
Taking the above into account we are currently working with about 42 Shafts (Mines) to adopt the leadingpractice for Nets with Bolts
Many lives have already been saved due the installation of nets (with bolts) in especially the stoping environment and many member mines can attest to this!!

## TARP
0
MOSH FOG Adoption Programme Monitor for the Adoption of the Leading Practice for TARP May 2013
[9 empty] | Leading Practice Adoption Process Review (Yes = Y, No = N) | [6 empty] | I = In Progress C = Completed S = Signed Off | [12 empty] | I = In Progress C = Completed S = Signed Off
COPA | Commodity | No. | Name of Mine | Company | Name of Manager | Name of Project Leader | E-mail Address of Project Leader | Telephone Number | Do you have a FOG Risk associated with Entry Examination and Making Safe | Do you have FOG Risk Controls in place | Do you have a Procedure on Entry Examination and Making Safe | Is your FOG related LTIFR<0,05 | Have you considered the Adoption of the Leading Practice on Examination and Making Safe | Yes, we want to Adopt the Leading Practice on Examination and Making Safe | No, we do not want to Adopt the Leading Practice on Examination and Making Safe | Leading Practice Adoption Review | Implementation Plan | Procedure Amended | Mental Model Interviews | Leadership Behaviour Plan | Behaviour Communication Plan | Risk Assessment | Training Lesson Plans | Management Review Process | Roll-out plan in place | No. of Crews to Train | No. of Crews Trained | Progress | Signed Off Factor | [9 empty] | Completion Factor | [9 empty] | In Progress Factor | [9 empty] | Progress Table
|  | 1 | Finsch Diamond Mine | Petra Diamonds | Mr. Luctor Roode |  |  |  | Y | Y | Y | Y | Y | Y |  | I | [11 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
|  | 2 | Koffiefontein Diamond Mine | Petra Diamonds | Mr. Pieter Coetzee | Mr Siphe Nxele | siphon@petradiamonds.com | 0734401876 | Y | Y | Y | Y | Y | Y |  | I | I | I | I | I | I | [6 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
|  | 3 | Cullinan Diamond Mine | Petra Diamonds | [23 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
|  | 4 | Venetia Diamond Mine | De Beers Cons. |  |  |  |  | Y | Y | Y | Y | Y | Y |  | I | [11 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
|  | 5 | Kimberley Diamond Mine | Petra Diamonds | Mr. Steven Klopper | Mr. Marlon Spadone | marlons@petradiamonds.com | 0728589041 | Y | Y | Y | Y | Y | Y |  | I | I | I | I | I | I | [6 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
|  | 6 | Black Rock Mine | ARM | [23 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
|  | 7 | Tautona Mine | Anglo Gold Ashanti | Andre van Jaarsveld | Danny Davies | ddavies@anglogoldashanti.com | 834696807 | Y | Y | N | N | Y | Y |  | S | [9 empty] | 25 | 0 | 10% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | 0 | 10% | 0%
|  | 8 | Phakisa mine | Harmony Gold | Moses Motlhageng | Moses Motlhageng | moses.motlhangeng@hamorny.co.za | 827889623 | Y | Y | N | N | Y | Y |  | S | [9 empty] | 0 | 0 | #DIV/0! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
|  | 9 | Nkomati Mine | Nkomati | Trevor Visagie | Trevor Visagie | trevor.vasagie@nkomati.co.za | 137128207 | Y | Y | N | N | Y | Y |  | S | [9 empty] | 0 | 0 | #DIV/0! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
|  | 10 | Doornkop | Harmony Gold | Jacques Du Triou | Jacques Du triou | jacques,dutriou@harmony.co.za | 829268898 | Y | Y | N | N | Y | Y |  | S | [9 empty] | 0 | 0 | #DIV/0! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
|  | 11 | Kusasalethu | Harmony Gold | Francois Naude | Francois Naude | francois.naude@harmony.co.za | 018 782 91 52 | Y | Y | N | N | Y | Y |  | S | [9 empty] | 0 | 0 | #DIV/0! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
|  | 12 | Bambanani | Harmony Gold | Steven Green | Pieter Fourie | pieter.fourie@harmony.co.za | 579046118 | Y | Y | N | N | Y | Y |  | S | [9 empty] | 0 | 0 | #DIV/0! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
|  | 13 | Target 3 | Harmony Gold | Seromo Joseph | Seromo Joseph | seromo.mofokeng@harmony.co.za | 828564115 | Y | Y | N | N | Y | Y |  | S | [9 empty] | 0 | 0 | #DIV/0! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
|  | 14 | Target 1 | Harmony Gold | Carel Joubert | Carel Joubert | carel.joubert@harmony.co.za | 827987416 | Y | Y | N | N | Y | Y |  | S | [9 empty] | 0 | 0 | #DIV/0! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
|  | 15 | Masimong | Harmony Gold | Hannes Bornman | Hannes Bornman | hannes.borman@harmony.co.za | 579105703 | Y | Y | N | N | Y | Y |  | S | [9 empty] | 0 | 0 | #DIV/0! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
|  | 16 | Kopanang Mine | Anglo Gold Ashanti | Dawid Swanepoel | Dawid Swanepoel | daswanepoel@anglogoldashanti.com | 828287825 | Y | Y | N | N | Y | Y |  | S | [9 empty] | 0 | 0 | #DIV/0! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
|  | 17 | Unisel | Harmony Gold | Steven Green | Steven Green | Steven .green@harmony.co.za | 833801240 | Y | Y | N | N | Y | Y |  | S | [9 empty] | 0 | 0 | #DIV/0! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
|  | 18 | Tshepong | Harmony Gold | Adriano Sobreira |  | adriano.sobreira@harmony.co.za | 579073112 | Y | Y | N | N | Y | Y |  | S | [9 empty] | 0 | 0 | #DIV/0! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
|  | 19 | Anglo American Platinum | Amplats | Pieter Louw | Riaan Carstens | riaan.carstens@angloplatinum.com | 734666523 | Y | Y | Y | N | Y |  | N | S | S | S |  |  |  | S | S | S | S | 430 | 430 | 70% | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 | 60% | 10%
|  | 20 | Joel Mine | Harmony Gold | Kennedy Moagi | Warren Freeman | warren.freeman@harmony.co.za | 847016876 | Y | Y | N | N | Y | Y |  | S | S | S | S | S | S | S | S | S | S | 20 | 20 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 21 | Royal Bafokeng Rasimone | RBPM | Martin Stander | Christo Haasbroek | christoh@bafokengplatinum.co.za | [8 empty] | S | [9 empty] | 0 | 0 | #DIV/0! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[29 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
|  | Number of Units Signed Off | [13 empty] | 15 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 475 | 450 |  | 15 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | [11 empty] | 9.474%
|  | Percentage of Units with Documents Signed Off | [13 empty] | 71.43% | 9.524% | 9.524% | 4.762% | 4.762% | 4.762% | 9.524% | 9.524% | 9.524% | 9.524% | 94.74% |  |  | 71.43% | 9.524% | 9.524% | 4.762% | 4.762% | 4.762% | 9.524% | 9.524% | 9.524% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 9.524% | 9.524% | 9.524% | 9.524% | 9.524% | 0% | 0% | 0% | 0%
|  | Percentage of Units Completed not Signed Off | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Percentage of Units with Work In Progress | [13 empty] | 19.05% | 9.524% | 9.524% | 9.524% | 9.524% | 9.524% | 0% | 0% | 0% | 0%
|  | Percentage of Units No Action | [13 empty] | 9.524% | 80.95% | 80.95% | 85.71% | 85.71% | 85.71% | 90.48% | 90.48% | 90.48% | 90.48%
[16 empty] | LP Review | Implementation Plan | Procedure Amended | MM Interviews | LB Plan | BC Plan | Risk Assessment | Lesson Plans | Management Reviews | Roll Out Plan