## Slide 1: Noise Adoption Team
20th February 2014

## Slide 2
Contents
Key activities/highlights of the month
Lowlights
Key lessons learnt
Past & Future activities

## Slide 3
Key Team activities for the Month (Jan 2014-Feb 2014)
No | Highlights (Achievements, Industry Interactions)
1. 2. | HPD_TAS Adoption Received COPA nominations for HPD adopters (20) Some nominees are not adopters (5) Created POE for All adopters Company COPA meetings will be used to discuss and introduce POE Company COPA meetings will be precursor for industry COPA meeting - end March Industry Noise Data Base and Industry silencing of equipment data base Circulated request to the Industry Receiving response from Industry Data Base will have a dual function Leading Practice Planning workshop IBMQI

## Slide 4
Key Team activities for the Month (Jan 2014-Feb 2014)
No | Highlights (Achievements, Industry Interactions)
3. 4. | Leading Practice Planning workshop preparation Continued Site visits & Data collection – Harmony, AGA, ARM, Glencore, Exxarro, Sasol, Lonmin, Northam IBMQI Received nominees and awaiting MOSH Task Force approval – 21 Feb 2014

## Slide 5
No | Activities | Lowlights (Issues, Risks, Concerns) | Response - Remedial Action
1. | High Management turn-over (Modikwa, BECSA, Exxarro) | Re-work and sustainability of the HPD_TAS Adoption | Escalate to MOSH task Force, Re-doing the complete process
2. |  |  | 
3. |  |  | 
4. |  |  | 
5. |  |  | 
8. |  |  | 
Low lights – For the Month (Jan 2014 – Feb 2014)

## Slide 6
Noise team M&E Report (Jan 2014 – Feb 2014 )
KPA No | Key Performance Area | KPI No | KPI | Measure 1 (Definition) | Measure 2 (Definition) | Measure 1 | Measure 2 | Originally planned completion
A22 | Leading practice adoption | T95 | Identified potential adoption mines | (101) 102 Mines/Operations | Monthly | 100 % | Feb 2014 | Ongoing
 |  | T97 | Positive decision to adopt | (101) 102 Mines/Operations | Monthly | 100 % | Feb 2014 | Ongoing
 |  | T98 | Mine adoption team appointed | (51) 52 Mines/Operations | Monthly | (51) 52% | Feb 2014 | ?
 |  | T103 | Mental models interviews | (101) 102 Mines/Operations | Monthly | (60%) 62% | Feb 2014 | ?
 |  | T104 | Customised BC plan | (101) 102 Mines/Operations | Monthly | (20%) 62% | Feb 2014 | ?
 |  | T105 | Customised LB plan | (101) 102 Mines/Operations | Monthly | (20%) 62% | Feb 2014 | ?
 |  | T108 | Management sign-off | (101) 102 Mines/Operations | Monthly | 0% | Feb 2014 | ?
 |  | T109 | Leading practice piloted | (101) 102 Mines/Operations | Monthly | 0% | Feb 2014 | ?
 |  | T110 | Roll-out plan implementation | (101) 102 Mines/Operations | Monthly | 0% | Feb 2014 | ?
 |  | T111 | Completed adoptions of leading practice | (79) 101 Mines/Operations | Monthly | 0% | Feb 2014 | ?

## Slide 7
Key lessons learnt (Jan 2014 – Feb 2014)
No | Key Lessons learnt
1. | Biggest challenge is to get buy in from all stakeholders.
2. | 
3. | 
4. | 
5. | 
6. | 
7. | 
8. | 
9. | 

## Slide 8
Key Team activities for the Month (Jan 2014 – Feb 2014)
No | Activities
1. | Past (Jan – Feb) Re Training at Modikwa , Exxarro, Glencore MOSH Noise Team Strategy HPD_TAS Induction at Samrec (New Shaft) Sponsor Meeting Future (Feb - March) Sponsor Meeting HPD TAS Company COPAs - PoE HPD TAS Induction for Black Rock Mine Reports and Analysis of Noise Databases Reports and Analysis of Practices on offer
Important past & future activities