|  | The Learning Hub Draft Reporting Template – LH Strategic Plan for 2014 – 2016 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Visionary Goal 1: Drive Industry Ownership (MOSH is widely accepted as the common change management approach) |  |  |  |  |  |  |
| Strategic objectives: Engage closely with key decision makers at the DMR, organised labour and company level for their buy-in, demonstrated through improved understanding of, and active participation in the Leading Practice Adoption System |  |  |  |  |  |  |
| Key Performance Areas |  | Planned Completion Date | New Completion Date | Person Responsible | Progress to date | Comments / Feedback |
| - Develop and maintain an updated stakeholder map. |  | 21 Nov 2014 |  | SM |  |  |
| - Re-affirm the importance of voluntary eager adoption, behavioural aspects of the MOSH system from the CEO Elimination of Fatalities Team, Gold Producers’ Committee, Collieries Committee and Chamber Council. |  | 21 Nov 2014 |  | SM |  |  |
| - Reconstitute the composition of the MOSH Task Force in consultation with CEOs. |  | 31 Mar 2015 |  | SM |  |  |
| - Evaluate the industry’s change management capability and capacity in relation to MOSH approach. |  | 31 Nov 2014 |  | PAS |  |  |
| - Raise awareness and appreciation of the MOSH (principles) targeting all key stakeholders. |  | 31 Mar 2015 |  | SM |  |  |
| - Lobby Adoption Team Sponsors and MOSH Task Force members individually and collectively for their support on key decisions. |  | 31 Mar 2015 |  | ATM / PAS |  |  |
| - Advocate for the nomination and assignment of a senior operational manager to the role of Mine Adoption Team Manager. |  | Ongoing |  | ATM / PAS |  |  |
| - Develop and facilitate delivery platforms for MOSH competence training.. |  | Ongoing |  | T&M TEAM |  |  |
| - Assist adopting mines to prepare Portfolios of Evidence for improved quality of adoption. |  | Ongoing |  | ATM / PAS |  |  |
| - Monitor progress against company adoption plans and/or leading practice investigation reports as per Mining Charter. |  | Ongoing |  | LM |  | Q1 Progress report prepared and presented at the MOSH Adoption Team meeting of 19 March 2015. |
| Visionary Goal 2: Review the MOSH products and methodologies (Ensure flexibility and acceptance of the MOSH process and methodologies) |  |  |  |  |  |  |
| Strategic objectives: Identify and remove bottlenecks in the MOSH activities, methodologies and processes for improved acceptance, effectiveness and quality outputs / outcomes. |  |  |  |  |  |  |
| Key Performance Areas |  | Planned Completion Date | New Completion Date | Person Responsible | Progress to date | Comments / Feedback |
| - Identify, agree and document the key principles of MOSH. |  | 15 Dec 2014 |  | KB & AvZ | Complete | Final document sent to Head of Learning Hub on 17 March 2015 |
| - Identify, agree and document the critical path and related activities in the MOSH process. |  | 15 Dec 2014 |  | HG & GP |  |  |
| - Identify, agree and document the key outputs, products and outcomes on the critical path |  | 31 Jan 2015 |  | LM & CL |  |  |
| - Identify, agree and document the critical success factors in the MOSH process. |  | 31 Jan 2015 |  | DA &AB |  |  |
| - Identify, agree and document the key MOSH methodologies. |  | 31 Jan 2015 |  | HS, DC & BEH. SPEC |  |  |
| - Develop and agree criteria for identifying successful adopting mines (success stories / case studies) – Best practice adopter mines |  | Ongoing |  | DA, JvR & JDB |  |  |

| Visionary Goal 3: Brand and Market the MOSH Adoption System (Reflect a positive image of the MOSH Adoption system in the eyes of the clients at all times) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Strategic objectives: Improve MOSH visibility at fifteen (15) different operations per month. |  |  |  |  |  |
| Key Performance Areas | Planned Completion Date | New Completion Date | Person Responsible | Progress to date | Comments / Feedback |
| - Lobby and influence individual General Managers / Mine Managers to formally nominate and assign an “on-mine MOSH agent”. | 31 Mar 2015 |  | ALL |  |  |
| - Develop training materials and train the “on-mine MOSH agents”. | Ongoing |  | GP & JvR |  |  |
| - Coordinate the distribution of MOSH promotional and information materials including but not limited to fact sheets and success stories at key industry events – Mine Safe, Coal Safe, etc. | Ongoing |  | CL |  |  |
| - Obtain and analyse stakeholder inputs and feedback on MOSH events, meetings and workshops. | Ongoing – all events |  | LM |  | MOSH Dust Indaba: COPA Meetings evaluation: MOSH LP Demo Workshop on 20 April 2015: |
| - Partner with individual mining houses’ communication departments to run the “MOSH Appreciation Campaign”. | 30 Jun 2015 |  | JvR |  |  |
| - Identify and recognise success stories through the MOSH Behavioural Awards at the annual MOSH Review Workshop and Newsletter. | Ongoing |  | DA, JvR & JDB |  |  |
| - Keep the MOSH website up to date and report on usage. | Ongoing |  | LM & PAS |  | MOSH Website Update: |

| Visionary Goal 4: Turbo-charging the MOSH Learning Hub (To fully staff and skill the Learning Hub for effective facilitation of leading practice adoption) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Strategic objectives: Implement appropriate and cost effective strategies to energise the Learning Hub team to become super-charged. |  |  |  |  |  |
| Key Performance Areas | Planned Completion Date | Revised / New Completion Date | Person Responsible | Progress to date | Comments / Feedback |
| - Attract and appoint people with the requisite skills and demeanour / character to succeed in the Learning Hub. | Ongoing |  | SM |  |  |
| - Develop and implement a strong employee value proposition that fully brings out the many attractive aspects of work within the Learning Hub. - (training and skills development; technical and personal challenges; long –term secondments; retention measures; opportunities for local and international exposure; personal growth and satisfaction; etc) | Ongoing |  | ALL |  |  |
| - Implement strategies that help improve employee relationships. | Ongoing |  | SM |  |  |
| - Implement effective employee support strategies. | Ongoing |  | SM |  |  |

| Completed |  |
| --- | --- |
| In Progress |  |
| Not yet started / No progress |  |