Date: 7 October 2015

MOSH TASK FORCE CIRCULAR NO.  XX /15

(For consideration and noting)

INDUSTRY-WIDE BUY AND MAINTAIN QUIET INITIATIVE PROGRESS REPORT

Synopsis: A progress report on the implementation of the Industry-wide buy and Maintain Quiet Initiative is attached for the consideration of the MOSH Task Force at the meeting scheduled for 16th of October 2015.

Introduction

The Industry-wide Buy and Maintain Quiet Initiative (IBMQI) working group was requested by the MOSH Taskforce to submit a progress report on this initiative. This is not only to provide feedback to MOSH Taskforce members but to also ensure that the priority issues and medium term issues are being tackled and to identify potential constraints and challenges.

Substantive issue.

A total of three sub-working groups have been formed namely, the Measurement Standards Team, Research Consolidation Team and the Procurement Team. Some of the key achievements of the IBMQI to date include, among others:

  - Guidance document on the standardized noise measurement methodology to be used by both suppliers and mining houses;

  - Noise Data collection template;

  - Compiling an industry noise source inventory;

  - Review of past research on Noise;

  - Draft template for screening critical equipment; and

  - Creating a process flow for activities during procurement phase.

Conclusion or recommendation

The main challenge being faced by the IBMQI working group is on the noise data quality and lack of standardized way of reporting. The IBMQI initiative is progressing well and some of the research work identified will not have a significant negative impact on the project timelines. The IBMQI progress report is attached for the consideration of MOSH Task force at the meeting scheduled for the 16th of October 2015.

Name: Sharks Gumede

Tel: e.g.  011 498 7752

Mobile: 073 572 2279

Email: hgumede@chamberofmines.org.za

Web: www.chamberofmines.org.za