| The Learning Hub Balanced Scorecard for 2014 – 2017 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Visionary Goal 1: Drive Industry Ownership (MOSH is widely accepted as the common change management approach) |  |  |  |  |
| Strategic objectives: Engage closely with key decision makers at the DMR, organised labour and company level for their buy-in, demonstrated through improved understanding of, and active participation in the Leading Practice Adoption System |  |  |  |  |
| Key Performance Areas | Planned Completion Date | New Completion Date | Progress to date | Comments / Feedback |
| - Develop and maintain an updated stakeholder map. | 21 Nov 2014 |  |  |  |
| - Reaffirm the importance of voluntary eager adoption, behavioural aspects of the MOSH system from the CEO Elimination of Fatalities Team, Gold Producers’ Committee, Collieries Committee and Chamber Council. | 21 Nov 2014 |  |  |  |
| - Reconstitute the composition of the MOSH Task Force in consultation with CEOs. | 31 Mar 2015 |  |  |  |
| - Evaluate the industry’s change management capability and capacity in relation to MOSH approach. | 31 Nov 2014 |  |  |  |
| - Raise awareness and appreciation of the MOSH (principles) targeting all key stakeholders. | 31 Mar 2015 |  |  |  |
| - Lobby Adoption Team Sponsors and MOSH Task Force members individually and collectively for their support on key decisions. | 31 Mar 2015 |  |  |  |
| - Advocate for the nomination and assignment of a senior operational manager to the role of Mine Adoption Team Manager. | Ongoing |  |  |  |
| - Develop and facilitate delivery platforms for MOSH competence training. | Ongoing |  |  |  |
| - Assist adopting mines to prepare Portfolios of Evidence for improved quality of adoption. | Ongoing |  |  |  |
| - Monitor progress against company adoption plans and/or leading practice investigation reports as per Mining Charter. | Ongoing |  |  |  |
| Visionary Goal 2: Review the MOSH products and methodologies (Ensure flexibility and acceptance of the MOSH process and methodologies) |  |  |  |  |
| Strategic objectives: Identify and remove bottlenecks in the MOSH activities, methodologies and processes for improved acceptance, effectiveness and quality outputs / outcomes. |  |  |  |  |
| Key Performance Areas | Planned Completion Date | New Completion Date | Progress to date | Comments / Feedback |
| - Identify, agree and document the key principles of MOSH. | 15 Dec 2014 |  |  |  |
| - Identify, agree and document the critical path and related activities in the MOSH process. | 15 Dec 2014 |  |  |  |
| - Identify, agree and document the key outputs, products and outcomes on the critical path | 31 Jan 2015 |  |  |  |
| - Identify, agree and document the critical success factors in the MOSH process. | 31 Jan 2015 |  |  |  |
| - Identify, agree and document the key MOSH methodologies. | 31 Jan 2015 |  |  |  |
| - Develop and agree criteria for identifying successful adopting mines (success stories / case studies) – Best practice adopter mines | Ongoing |  |  |  |

| Visionary Goal 3: Brand and Market the MOSH Adoption System (Reflect a positive image of the MOSH Adoption system in the eyes of the clients at all times) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Strategic objectives: Improve MOSH visibility at fifteen (15) different operations per month. |  |  |  |  |
| Key Performance Areas | Planned Completion Date | New Completion Date | Progress to date | Comments / Feedback |
| - Lobby and influence individual General Managers / Mine Managers to formally nominate and assign an “on-mine MOSH agent”. | 31 Mar 2015 |  |  |  |
| - Develop training materials and train the “on-mine MOSH agents”. | Ongoing |  |  |  |
| - Coordinate the distribution of MOSH promotional and information materials including but not limited to fact sheets and success stories at key industry events – MineSafe, CoalSafe, etc. | Ongoing |  |  |  |
| - Obtain and analyse stakeholder inputs and feedback on MOSH events, meetings and workshops. | Ongoing – all events |  |  |  |
| - Partner with individual mining houses’ communication departments to run the “MOSH Appreciation Campaign”. | 30 Jun 2015 |  |  |  |
| - Identify and recognise success stories through the MOSH Behavioural Awards at the annual MOSH Review Workshop and Newsletter. | Ongoing |  |  |  |
| - Keep the MOSH website up to date and report on usage. | Ongoing |  |  |  |

| Visionary Goal 4: Turbo-charging the MOSH Learning Hub (To fully staff and skill the Learning Hub for effective facilitation of leading practice adoption) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Strategic objectives: Implement appropriate and cost effective strategies to energise the Learning Hub team to become super-charged. |  |  |  |  |
| Key Performance Areas | Planned Completion Date | New Completion Date | Progress to date | Comments / Feedback |
| - Attract and appoint people with the requisite skills and demeanour / character to succeed in the Learning Hub. | Ongoing |  |  |  |
| - Develop and implement a strong employee value proposition that fully brings out the many attractive aspects of work within the Learning Hub. - (training and skills development; technical and personal challenges; long –term secondments; retention measures; opportunities for local and international exposure; personal growth and satisfaction; etc) | Ongoing |  |  |  |
| - Implement strategies that help improve employee relationships. | Ongoing |  |  |  |
| - Implement effective employee support strategies. | Ongoing |  |  |  |

| Completed |  |
| --- | --- |
| In Progress |  |
| Not yet started / No progress |  |