## Outline
Learning Hub Monitoring and Evaluation (M&E) Framework
This document presents the Monitoring and Evaluation Framework that has been developed for use by the Learning Hub, both internally and in its interaction with key stakeholders. It takes account of input received through an extensive consultation process involving the Adoption Teams, the Learning Hub Secretariat, the Health and Safety and Sustainable Development Advisory Functions, the MOSH Task Force and the Learning Hub Advisory Committee.
Purpose
In general, the purpose of any monitoring and evaluation framework is to track progress and to facilitate appropriate decision making. In relation to the Learning Hub, it follows that its Monitoring and Evaluation Framework must be aligned with the Hub's purpose and operational needs, but also with the needs of its key stakeholders. In this context the following points are relevant:
Primary purpose of the Learning Hub: The agreed mission of the MOSH Learning Hub is to facilitate the adoption of leading practices through a people oriented process to significantly improve occupational health and safety in the mining industry. In this way the learning Hub seeks to lead the change to zero harm. It is very important to recognise that this mission clearly identifies facilitation as the key direct responsibility of the Learning Hub.
Facilitation: A facilitator cannot be held directly responsible for achievement of desired outcomes where the responsibility and the means for achieving the outcomes lies with others. This is an important point of principle. The outcomes achieved can however be used as an indicator, but not a direct measure, of the extent to which the facilitation process has been successfu, since the outcome might have been possible, and indeed achieved, without any facilitation effect at all.
Facilitator responsibility: Importantly a facilitator can and should be held responsible for selecting and applying appropriately effective facilitation techniques designed to prompt others to take the steps necessary to achieve the desired outcome. In the development of the adoption system a number of such techniques were selected and integrated to become the key elements of the MOSH adoption system, and these are presented in the Handbook. In principle, and in practice, Learning Hub staff are thus responsible for ensuring that, unless other better techniques are agreed upon, at least these techniques are properly used with a view to facilitating the desired outcomes.
Other issues of strategic importance to the Learning Hub: In addition to its primary purpose, there are other issues of strategic importance that the Learning Hub needs to address from time to time, such as those identified at a Learning Hub strategic planning workshop. Learning Hub staff are clearly also responsible for ensuring that these issues are effectively addressed.
Purpose of Learning Hub M&E Framework: Following on from the above the purpose of the Hub's M&E Framework is thus to provide a means for ensuring that identified key facilitation elements are effectively executed, that they are having their intended effect, and that other issues of strategic importance to the Hub are also being effectively addressed. More specifically, the purpose of the Learning Hub M&E Framework is to define a set of measurements for assessing progress and deciding action (focus / priorities / quality / content / remedial action / etc) in respect of:
  Key elements of the process for facilitating the selection and widespread adoption of leading practice
  Achievement of people oriented adoption of leading practice
  Improvements in occupational health and safety at adopting mines and for the mining industry
  Achievement of other key Learning Hub objectives.
Key Considerations
In regard to the M&E Framework, the following points are relevant:
Effectiveness and simplicity: A fundamental ideal of any M&E Framework is that it should be both effective and simple. However, in striving for simplicity a framework must not be simplified to the point where it is no longer effective in terms of its intended purpose. In this context it must be recognised that, operationally, there are different users and uses of the monitored data, each with their own purpose and data requirements, and that this must be taken into account in framework.
Different users and needs: The following users and uses (who, what, why, how) were identified in developing the Learning Hub M&E Framework:
  Adoption Team Leadership: From time to time each adoption team needs to plan and schedule the key tasks involved in identifying, selecting, investigating, documenting and facilitating the widespread adoption of the leading practice considered to have the greatest potential to improve health and safety in their area of concern. This plan needs to be shared and agreed with the Head of the Learning Hub. The team then needs to report and evaluate performance in relation to this agreed plan, and take any necessary corrective or other appropriate action. It also needs to monitor, assess and report the impact of its work on the risk area in question.
  Learning Hub Secretariat: From time to time the Learning Hub Secretariat needs to plan and schedule the actions considered necessary to address key issues that arise out of strategic planning sessions, or which are otherwise agreed for inclusion in the Learning Hub’s M&E Framework. Once planned and agreed to, the secretariat needs to report and evaluate performance in relation to this agreed plan, and take any necessary or appropriate action. Importantly, the secretariat also needs to consolidate the performance and impact data of the individual adoption teams to clearly bring out the overall performance of the Learning Hub, and the impact of its activities.
  Learning Hub Leadership and staff: Execution of the adoption team plans and on action to address agreed issues of importance to the Learning Hub need to be reported upon and evaluated at regular meeting of the Learning Hub Staff. At such meetings the Learning Hub Leadership, and in particular the Head of Hub, may identify any further action needed to address issues that emerge through the evaluation process. The Learning Hub Leadership and staff also need to monitor and evaluate the impact of the Hub's work on industry occupational health and safety progress towards agreed milestones and goals.
  COPA and Adoption Team members: Following establishment of the COPA to facilitate widespread adoption of the leading practice, progress on adoption of the leading practice at individual mines and mining groups needs to be monitored and reported for evaluation and responsive action by both COPA members and industry members of the adoption team.
  Executive level stakeholders: Persons at an executive level who have oversight responsibility for the funding and performance of the Learning Hub have an important monitoring and evaluation role to play, but at an appropriately high level. In particular, the data they consider needs to relate to action and decision making pertinent at their level, including the desired outcomes and impacts that led to establishment of the Learning Hub. This includes the MOSH Task Force, MOSH Advisory Committee, MOSH Sponsors, GPC, CC, "Other sectors" Committee, COM Executive Council, and on an adhoc basis, various other Chamber Committees. Such information will also be useful in interactions with other stakeholders such as SACM, AMSA, SACEA, AMRE, Unions and various tri-partitie structures, such as the MHSC.
Levels of monitoring and evaluation: A further point that has been taken into account in developing the M&E Framework is that monitoring and evaluation can, and indeed should take place at different levels. These levels are as follows:
Inputs……….The financial, human and material resources required for the planned intervention
Activities…… Actions taken or work performed to achieve a desired output or outcome
Outputs……..The direct products, services or physical deliverables that result from action taken
Outcomes…. The effect of activities or delivered outputs
Impacts ….... Changes in the broader socio-economic environment .
The provision of pertinent indicators at these different levels has thus been considered in developing the Framework. Importantly, as with most project monitoring arrangements, not all indicators will be active and relevant on every reporting occasion.
Key performance areas: The key performance areas used in the Framework identify the areas that need to be monitored and evaluated with a view to deciding future action. In line with earlier arguments, the key performance areas include all of the key elements of the MOSH facilitation process, as well as the key tasks agreed to in the learning Hub's strategic planning process. Areas of key intended outcomes are also included, to provide an indirect indication of not only the effectiveness of the MOSH facilitation process, but also the effectiveness of the leading practices that have been adopted.
Key performance indicators: The key performance indicators of the Framework define the measurements that need to be made to indicate progress or particular aspects of performance within each key performance area. The indicators used are uniquely identified by the numbering system. They may be quantitative or qualitative, but the measurements must be made consistently in accordance with the definition provided. Although all of the required measurements are defined, in some cases the required measuring tool may require development, and in some cases the data may not be readily available. Such issues will need to be resolved on a case by case basis.
The Learning Hub M&E Framework
Based on various users, needs and other considerations presented above, a Learning Hub M&E Framework comprising of two planning datasheets and seven scorecards has been developed:
Adoption Teams Datasheet: The datasheet provides a detailed checklist for guidance and use by the adoption teams in planning their work. It is also designed for internal use by adoption teams as they see fit. The example planning schedules provided in the Handbook are also included in framework to assist with this planning process. The Team's Adoption Specialist should take responsibility for preparing and updating the datasheet to the extent decided upon by the adoption team.
LP Process Scorecard : The scorecard includes the indicators most important for reporting progress on identifying, selecting, investigating and documenting a leading practice. It deals with the adoption process right up to the point of initiating the process of facilitating widespread adoption of the leading practice. It therefore covers that part of the adoption process that is largely under the team's control. It is designed for use by the adoption team in monitoring and evaluating progress in relation to their agreed plan, and for regularly reporting progress at Learning Hub meetings.The team's Adoption Specialist should take responsibility for preparing and regularly updating the scorecard .
SLP Process Scorecard : As for the LP Process Scorecard.
LP Adoption Scorecard: The scorecard includes indicators that track the progress made by each of the identified potential adoption mines in assessing and then adopting the leading practice at their mine. It is for use by the adoption team at COPA, Adoption Team and Learning Hub meetings in reporting and evaluating progress on facilitating widespread adoption of the leading practice. The team's Adoption Specialist should take responsibility for preparing and regularly updating the scorecard.
SLP Adoption Scorecard: As for the LP Adoption Scorecard.
Team Impact Scorecard: The scorecard keeps track of the extent that the various leading practices have been adopted across industry, as well as movement in the parameters expected to best indicate the occupational health and safety benefits derived from adopting the practices in question.The scorecard is designed for use by the adoption teams in quarterly reporting on the outcomes and impacts of the team's work. The team's Adoption Specialist should take responsibility for preparing and regularly updating the scorecard. The Monitoring Specialist should establish and maintain a data base of relevant industry data needed by the adoption specialists for updating the scorecard.
Learning Hub Datasheet: The datasheet is intended for use by the secretariat in the detailed planning of activities in addition to or in support of activites undertaken by the various adoption teams. It is intended for internal use by the Learning Hub Secretariat. It should be prepared and updated to the extent necessary by the Monitoring Specialist.
Learning Hub Scorecard: The scorecard provides a basis for monitoring and evaluating progress on the key activities that are in addition to the usual activities of the adoption teams. It also consolidates data presented by the various adoption teams to present an overall picture of progress being made by the Learning Hub. It is for use at Learning Hub meetings to monitor and evaluate progress on key Learning Hub activities in relation to agreed plans. The Monitoring Specialist should take responsibility for preparing and updating the scorecard for consideration at Learning Hub meetings.
High-level Scorecard: This scorecard contains a selection of indicators of relevance to high-level stakeholders in monitoring and assessing the output of the Learning Hub and its impact on health and safety performance across industry. It also contains indicators that track industry participation in and support of the adoption process and its structures. The scorecard is designed to enable monitoring and evaluation of parameters crucial to the success of the adoption system and progress towards the ultimate industry goal of zero harm. It is for for consideration at Task Force meetings and other relevant high-level meetings. The MOnitoring Specialist should take responsibility for preparing and updating the scorecard for presentation at these meetings.
The nine reporting templates that comprise the Learning Hub M&E Framework are attached. They include brief guidance notes to assist in their use.
Concluding comment
It is important to recognise that the Learning Hub M&E Framework must be capable of addressing all of the identified monitoring and evaluation needs. Although the outcome indicators will inevitably be of greatest interest, the greatest value is likely to be derived from the lower-level indicators, which are concerned with inputs, activities and outcomes; it is ensuring effective execution at this level that will lead to achievement of the desired outcomes and impacts. It is the responsibility of Adoption Team Managers and Learning Hub Specialists to use the various elements of the Leaning Hub M&E Framework to ensure effective execution of actions at this level, as it is these actions that they can control, and for which they are responsible.

## Definitions
Definitions
Given below is an explanation of various terms used in the monitoring and evaluatuion framework
KPA - Key Performance Area | This is an area of activity considered to be of particular importance to the realisation of the major objectives of either a MOSH Adoption Team or of the Learning Hub
KPI - Key Performance Indicator | Something within a key performance area that can be assessed / measured in quantitative or qualitative terms to indicate performance or progress within the key performance area.
Input | Resources, in one form or another (staff, skills, information, etc.) required or used in a programme of work to deliver a defined output.
Activity | Action that needs to be taken to within a programme of work to deliver a defined output
Output | The product, service or result that is delivered by the programme of work (project) designed and undertaken expressly for this purpose.
Outcomes | The change, benefit, learning or other effect derived from an output that has been delivered
Definition of Measurement | A statement that defines / explains how the particular measure / assessment is to be made and in what form it needs to be expressed, in order to ensure consistent reporting and understanding.
Data Source | Provides an indication of where the data needed to derive the measure is expected to be, and ought to be available.
Timing for Assessment | Indicates the timing / frequency of reporting on the indicator in question
Target | Indicates the desired level of performance in respect of the indicator in question.
Measure | The reported value for the indicator at the time of assessment, measured in accordance with the definition provided
Date completed | The actual date of completion of work associated with the indicator in question
Planned Completion | The originally planned date of completion of work associated with the indictor in question.

## LP Process Scorecard
[12 empty] | -6017 | [26 empty] | -47484
Leading Practice Process Scorecard - Monthly print-out table (See procedure text box below) - Rev 0: For (Leading Practice Name) |  |  |  |  | 31 Aug | Report for the month of: |  |  |  | Aug |  | List of KPIs for planning purposes - see more detail in columns to the left | Adoption Team Scorecard -12-Month data entry table for 20xx (See procedure text box below): For (Name of Leading Practice) | [25 empty] | List of KPIs for planning purposes - see more detail in columns to the left | Planning of KPI activity start and completion dates, for: (Name of Leading Practice ) Insert calendar date to indicate the end of week 1 - the other dates will be adjusted automatically | [71 empty] | Currently agreed completion date | Originally planned completion date | Record of actual completion dates
 | time axis 2013-01-20 to 2014-06-01
KPA No | KPA | KPI No. | KPI | Definition of measurement (See Team datasheet for fuller descriptions) Measure 1 ¦ Measure 2 | Timing for report | Target | Data for past and present month |  |  |  | Originally planned completion | [28 empty] | 2013-01-20: 4-week periods and weeks
[7 empty] | Measure 1 |  | Measure 2 | Curr planned completion |  | KPI | Dec |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  | KPI | 2013-01-20: 1; 2013-02-17: 2; 2013-03-17: 3; 2013-04-14: 4; 2013-05-12: 5; 2013-06-09: 6; 2013-07-07: 7; 2013-08-04: 8; 2013-09-01: 9; 2013-09-29: 10; 2013-10-27: 11; 2013-11-24: 12; 2013-12-22: 13; 2014-01-19: 14; 2014-02-16: 15; 2014-03-16: 16; 2014-04-13: 17; 2014-05-11: 18
[7 empty] | Prev Curr |  | Prev Curr |  |  |  | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 |  |  | Meas 1 | Meas 2
| Leading Practice Adoption Process | [10 empty] | Leading Practice Adoption Process | [26 empty] | Leading Practice Adoption Process
| Identification of Leading Practice | [10 empty] | Identification of Leading Practice | [26 empty] | Identification of Leading Practice
A1 | Appropriate persons to select leading practice | T4 | Approved participants list | Head of Hub approved list of workshop participants Yes or No ¦ Date approved | Monthly | Yes | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Approved participants list | [26 empty] | Approved participants list | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A2 | Appropriate plans for planning workshop | T8 | HOH review and approval | Review and approval against checklist at least two weeks before workshop Yes or No ¦ Date of approval | Monthly | Yes | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | HOH review and approval Plans for workshop | [26 empty] | HOH review and approval Plans for workshop | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A3 | Detailed expert model of risk story | T12 | Detailed expert models | Detailed drafts of the two expert models ready for workshop Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Detailed expert models | [26 empty] | Detailed expert models | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T14 | Hub Peer Group assessment | Peer group review of expert model quality Assessment score % ¦ Date completed | Monthly | >90% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Peer Group assessment | [26 empty] | Peer Group assessment | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A4 | Leading practice with greatest OHS impact | T19 | Credibility of selected Leading Practice | Workshop participants assessment of practice against key criteria (at workshop) Assessment score in % ¦ Date assessed | Monthly | >90% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Credibility of selected LP | [26 empty] | Credibility of selected LP | [72 empty] | 2030-01-01 | 2030-01-01 | 0
| Documention of Leading Practice | [10 empty] | Documention of Leading Practice | [26 empty] | Documention of Leading Practice
A5 | Adoption mines and key people | T22 | Prioritised list of mines and key people | Consolidated prioritised list of adopter mines and key persons at mines, with contact details Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 100 | 2012-05-15 | 2030-01-01 | 2030-01-01 | List of mines / key people Prioritised potential adopters | [8 empty] | 90 |  | 100 | 2012-05-15 | [14 empty] | List of mines / key people Prioritised potential adopters | [72 empty] | 2030-01-01 | 2030-01-01 | 100 | 2012-05-15
A6 | Direct enquiry protocol | T27 | Direct enquiry protocol | Custom designed enquiry protocol signed off by Behaviour Specialist for the leadng practce Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Direct enquiry protocol | [26 empty] | Direct enquiry protocol | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A7 | Effective direct enquiry process | T30 | Interview process | All planned interviews conducted by trained interviewers Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Interview process Effective direct enquiry process | [26 empty] | Interview process Effective direct enquiry process | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A8 | Detailed mental models report | T33 | Mental models report | Detailed mental models report signed off by Behaviour Specialist Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Mental models report | [26 empty] | Mental models report | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T34 | Identification of implications | Documented implications of the identified mental models as input for BC and LB plans Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 2013-07-12 | 2030-01-01 | 2030-01-01 | Identify implications of mental model findings | [15 empty] | 2013-07-12 | [10 empty] | Identify implications of mental model findings | [72 empty] | 2030-01-01 | 2030-01-01 | 0 | 2013-07-12
A9 | BC Plan for deciders | T35 | BC plan for deciders (at mines) | Detailed BC plan for deciders signed off by Behaviour Specialist (see T50) Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | BC plan for deciders | [26 empty] | BC plan for deciders | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A10 | Generic BC plan for adoption mines | T38 | BC plan for adoption mines | Detailed BC plan for use at adoption mines signed off by Behaviour Specialist Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 2013-06-12 | 2030-01-01 | 2030-01-01 | BC plan for adoption mines | [13 empty] | 2013-06-12 |  |  |  |  | 80 |  | 80 | [5 empty] | BC plan for adoption mines | [72 empty] | 2030-01-01 | 2030-01-01 | 0 | 2013-06-12
A11 | Generic LB plan for adoption mines | T41 | LB plan for adoption mines | Detailed LB plan for use at adoption mines signed off by Behaviour Specailist Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | LB plan for adoption mines | [8 empty] | 20 |  | 30 | [15 empty] | LB plan for adoption mines | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A12 | Peer reviewed value case report | T47 | Final externally peer reviewed report | Final updated version of peer reviewed value case report Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Final peer reviewed report Of the value case | [26 empty] | Final peer reviewed report Of the value case | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A13 | Implemented BC plan for deciders | T50 | Implementation of Decider BC plan | Implementation of BC plan for deciders prior to Leading Practice Adoption Workshop Estimate % complete ¦ Date completed | Monthly | 100% | 100 | 100 | 2012-07-10 | 2030-01-01 | 2030-01-01 | Implement Decider BC plan | [8 empty] | 20 |  | 20 |  |  |  | 100 | 2012-07-10 | [10 empty] | Implement Decider BC plan | [72 empty] | 2030-01-01 | 2030-01-01 | 100 | 2012-07-10
A14 | Source mine report | T55 | Final source mine report | Updated draft of report based on input from consultations at mine and with adoption team Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Final source mine report | [26 empty] | Final source mine report | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T56 | Hub peer group assessment | Hub Peer Group assesment using an agreed score card for assessing source mine reports Assessment score % ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Peer Group assessment of source mine report | [8 empty] | 20 |  | 22 | [15 empty] | Peer Group assessment of source mine report | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A15 | Source investigations summary report | T57 | Summary of behavioural work | A summary report of the work undertaken in developing the generic BC and LB plans Estimate % complete ¦ date completed | Monthly | 100% | 0 | 0 | 2012-03-14 | 2030-01-01 | 2030-01-01 | Summary of beh. work |  |  |  |  | 80 |  |  | 2012-03-14 | [18 empty] | Summary of beh. work | [72 empty] | 2030-01-01 | 2030-01-01 | 0 | 2012-03-14
|  | T58 | Source investigations summary report | A report that pulls together the separate investigation reports which are appended Estimate % complete ¦ date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Source investigation report Covering all investigations of the LP | [26 empty] | Source investigation report Covering all investigations of the LP | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T59 | Hub peer group assessment | Hub Peer Group assesment using score card for source investigations summary reports Assessment score % ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Peer Group assessment of source investigations report | [26 empty] | Peer Group assessment of source investigations report | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A16 | Draft leading practice adoption guide | T61 | Draft LPAG for use at mines | Draft guide for use at adoption mines based on input from source mine and team Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 95 | 2012-06-10 | 2030-01-01 | 2030-01-01 | Draft LPAG for use at mines | [8 empty] | 95 | 2012-06-10 | [16 empty] | Draft LPAG for use at mines | [72 empty] | 2030-01-01 | 2030-01-01 | 95 | 2012-06-10
|  | T62 | Hub peer group assessment | Hub Peer Group assesment of LPAG using agreed score card Assessment score % ¦ Date completed | Monthly | 100% | 0 | 0 | 2013-07-30 | 2030-01-01 | 2030-01-01 | Peer assessment of draft LPAG | [15 empty] | 2013-07-30 | [10 empty] | Peer assessment of draft LPAG | [72 empty] | 2030-01-01 | 2030-01-01 | 0 | 2013-07-30
| Facilitation of widespread adoption | [10 empty] | Facilitation of widespread adoption | [26 empty] | Facilitation of widespread adoption
A17 | Leading practice industry workshop | T65 | Workshop programme | Programme for workshop signed off by HoH at least two weeks before workshop Yes or No ¦ Date completed | Monthly | Yes | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Workshop programme | [26 empty] | Workshop programme | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T66 | Effective key presentations | A special workshop assessment form completed at workshop by all participants Assessment score % ¦ Date completed | Monthly | >80% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Effective key presentations | [26 empty] | Effective key presentations | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A18 | Establishment of effective COPA | T69 | COPA modus operandi | Modus operandi agreed with COPA members within 4 weeks of establishing the COPA Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | COPA modus operandi | [26 empty] | COPA modus operandi | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T72 | COPA membership | To include one originally identified key persons at adoptn mine and / or Adoptn Team Managr % of mines with required membership ¦ No.of mines | Monthly | > 80% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | COPA membership | [26 empty] | COPA membership | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T73 | COPA attendance | COPA attendance by identified key (required) members % attendance by key members ¦ Date of last meeting | Monthly | > 60% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | COPA attendance | [26 empty] | COPA attendance | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T75 | COPA effectiveness - self assessment | A COPA effectiveness assessment form completed six-monthly by COPA participants Assessment score in % ¦ Date completed | Monthly | > 80% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | COPA effectiveness | [26 empty] | COPA effectiveness | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A19 | Working relationship with Lead Adoption Mine | T78 | Agreement with Mine Manager | Working relationship agreed with Mine Manager Estimate % complete ¦ Date completed | Monthly | 100% by adoption workshop | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Agreemnt with Mine Managr | [26 empty] | Agreemnt with Mine Managr | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A20 | Report on adoption at Lead Adoption Mine | T79 | Agreed adoption plan | Copy of agreed adoption plan for lead adopter mine with comments for use in updating LPAG Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Agreed adoption plan | [26 empty] | Agreed adoption plan | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T81 | Direct enquiry process | Direct enquiry process using selected interviewees and trained interviewers Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Direct enquiry process | [26 empty] | Direct enquiry process | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T82 | Customised BC & LB plans | Customised BC and LB plans involving proper application of customisation process Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Customised BC & LB plans | [26 empty] | Customised BC & LB plans | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T84 | Monitoring and evaluation plan | Impact and performance monitoring and evaluation plan agreed with the mine Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Monitorng and evaltn plan | [26 empty] | Monitorng and evaltn plan | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T85 | Effectiveness of BC & LB plans | Assessment of effectiveness using standard behaviour modification survey tool Assessment score in % ¦Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Effectvness of BC+LB plans | [26 empty] | Effectvness of BC+LB plans | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T88 | Documented findings | All findings (lessons learnt) at first adoption mine documented and on file Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Documented findings | [26 empty] | Documented findings | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T90 | Signed off report on first adoption | Updated report based on input from consultations at mine and with adoption team Estimate % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Signed off report on first adoption | [26 empty] | Signed off report on first adoption | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T91 | Hub peer group assessment | Hub Peer Group assesment of adoption report using an agreed score card Assessment score % ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Peer Group assessment | [26 empty] | Peer Group assessment | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A21 | Final leading practice adoption guide | T93 | Final Leading Practice Adoption Guide | Updated final draft of the LPAG based on input from first adoption mine and adoption team Assessment score % ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Final LPAG | [26 empty] | Final LPAG | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T94 | Hub peer group assessment | Hub Peer Group assesment of LPAG using an agreed score card Assessment score % ¦ Date completed | Monthly | 100% | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Peer assessment of LPAG | [26 empty] | Peer assessment of LPAG | [72 empty] | 2030-01-01 | 2030-01-01 | 0
A21a | Adequacy of adoption process | T94a | Average of peer group assessments | Average value of peer group assessments conducted to date (T14, 15, 56, 59, 62, 75(av), 91, 94) Average assessment score ¦ Date all assessments completed | Monthly | >90% | 0 | 0 | 0 | 2030-01-01 |  | Average of peer group assessments | [26 empty] | Average of peer group assessments | [72 empty] | 2030-01-01 | 2030-01-01 | 0
|  |  | This date is entered in yellow font in place of the planned completion dates, which should be entered for each indicator once the relevant completion date has been established | [6 empty] | 2030-01-01
Each adoption team should enter the planned completion dates for each of the activities / indicators in the two columns to the far right (columns "DN" and "DP") - see more detail in the notes below the tables
Broad guide for estimation of % complete
In general it would be appropriate for the the estimates of %-age completion to be based on an estimate of time spent to date as a % of the total time required for the work in question, with both time periods being estimates in person days, as opposed to calendar days.
For indicators involving data gathering and report / document preparation, the following scale is likely to roughly approximate estimates based on work time. It is provided for guidance and to help ensure that the time required for report writing and finalisation of the document are not grossly underestimated.
0 % No work yet
10 % Required work planned and initiated
20 % Early stages of data gathering
30% Late stages of data gathering
40 % Required data gathered - write-up started
50 % Analysis in progress
60 % Data analysed
70 % First draft of document complete
80% Review and comment process in progress
90 % Document updated and edited
100 % Document finalised and posted, all work complete
Conditional formatting on monthly scorecard printout
The cells in this print out have been conditionally formatted as follows:
White for cells where no applicable data data has yet been entered into the data entry sheetl
Amber for cells where there has been no progress since the last report, or where the entered completion date is later than the scheduled completion date
Green for cells where progress has been made or where the entered completion date is before the scheduled completion date
Dark pink for cells where the activity is still in progress after the scheduled completion date has passed
Conditional formatting on 12-month data entry sheet
The cells in the 12-month data entry sheet have been conditionally formatted to grey out the remaining cells in a row once the completion date has been entered.
The data entry table otherwise contains no formulas so values may be entered , deleted and changed in the sheet without affecting the conditional formatting .
The corrected values in the data entry sheet will be pulled through into the monthly scorecard printout.
The month of the scorecard report must be entered in this cell in the example three letter month format, to enable the correct data to be pulled through from the 12-month data entry table
Procedure for using the above M&E Framework tables
Step 1: Plan work on the leading practice using the planning chart and entering the planned completion date for each indicator in the original completion date entry column to the right of the planning chart. When necessary, revised completion dates should be entered into the current completion date column, leaving the original completion date unchanged. The data will automatically appear in the relevant columns of the Scorecard print-out table.
Step 2: Where applicable, enter data for December of the previous year in the 12 month data entry table.
Step 3: At the end of each month enter into the 12 month data entry table the relevant data for the two measures for each of the indicators for the leading practice in question
Step 4: Enter the three character month indicator in the top right hand cell of the monthly print out table. The Scorecard print-out table will then be automatically updated for printing / filing for the month in question.
Note: Most of the cells of the monthly scorecard print-out table have been protected to prevent inadvertent changes to the coding contained in the various cells . The cells requiring input such as the month of the print out, the name of the leading practice and the definition of the measures and time periods in the impact section of the table have been left unprotected so that the teams can enter the relevant data. (Lettie, I have not yet done the necessary protections)
Yellow for cells where planned completion date has not yet been entered.
Note 1: Planning of an adoption teams work for a leading practice should be completed with the assistance of the planning charts provided in sections 3.1 and 4.10 of the Handbook. Consideration of those charts provides indicative completion dates marked by the dot at the end of the activity bars shown in this chart. The rest of each activity bar refelects associated prior activity
Note: This indicator tentatively provides an integrated measure of the the adequacy with which the fundamentals of the leading practice adoption process have been undertakenadoption
Note 2: Should the adoption team wish to include the planning of other important activities into this planning chart, this may be done by introducing additional spreadsheet rows , which can then be appropriately named and used accordingly. The additional rows should then simply be "hidden" when presenting / printing the scorecard for assessment.
Note 4: Necessary revised planning bars could be indicated by simply copying the original planning bar, changing its coulour and then repositioning and resizing it, as shown by the red example. It also clearly shows the need to reschedule / replan the following activity
Note 3: In order to show clearly the present date in relation to the planned duration and completion of the various activities , the black dotted vertical line should simply be moved to the appropriate position on the planning chart.

## SLP Process Scorecard
SLP Process Scorecard - Monthly print-out table (See procedure text box below) - Rev 0: For (SLP Name) |  |  |  |  | 31 May | Report for the month of: |  |  |  |  | May |  |  | Adoption Team Scorecard -12-Month data entry table for 20xx (See procedure text box below): (Name of Leading Practice) | [25 empty] | List of KPIs for planning purposes - see more detail in columns to the left |  | Planning of KPI activity start and completion dates For: (Name of SLP ) Insert calendar date to indicate the end of week 1 - the other dates will be adjusted automatically | [35 empty] | Currently agreed completion dates | Originally agreed completion dates | Final completion dates
KPA No | KPA | KPI No. | KPI | Definition of measurement (See Team datasheet for fuller descriptions) Measure 1 ¦ Measure 2 | Timing for report | Target | Data for past and current month |  |  |  |  | Originally planned completion date | KPI | Dec |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | 2013-01-20 | 2013-01-27 | 2013-02-03 | 2013-02-10 | 2013-02-17 | 2013-02-24 | 2013-03-03 | 2013-03-10 | 2013-03-17 | 2013-03-24 | 2013-03-31 | 2013-04-07 | 2013-04-14 | 2013-04-21 | 2013-04-28 | 2013-05-05 | 2013-05-12 | 2013-05-19 | 2013-05-26 | 2013-06-02 | 2013-06-09 | 2013-06-16 | 2013-06-23 | 2013-06-30 | 2013-07-07 | 2013-07-14 | 2013-07-21 | 2013-07-28 | 2013-08-04 | 2013-08-11 | 2013-08-18 | 2013-08-25 | 2013-09-01 | 2013-09-08 | 2013-09-15 | 2013-09-22
[11 empty] | Currently planned completion date | [30 empty] | 2013-01-20: 4-week periods and weeks |  |  | Meas 1 | Meas 2
[7 empty] | Measure 1 Prev Curr |  | Measure 2 Prev Curr |  |  |  |  | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | Meas 1 | Meas 2 | KPI |  | 2013-01-20: 1; 2013-02-17: 2; 2013-03-17: 3; 2013-04-14: 4; 2013-05-12: 5; 2013-06-09: 6; 2013-07-07: 7; 2013-08-04: 8; 2013-09-01: 9
[7 empty] | Prev Curr |  | Prev Curr | [32 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
2013-01-07
| SLP Adoption Process | [11 empty] | SLP Adoption Process | [26 empty] | SLP Adoption Process
| Identification of SLP | [11 empty] | Identification of SLP | [26 empty] | Identification of SLP
A23 | SLP Adoption | T112 | Identified potential SLP adoption mines | List of identified potential SLP adoption mines No. of mines ¦ Date completed | Monthly | All | 0 | 0 | 0 |  | 2030-01-01 | 2030-01-01 | Identified potential SLP adoption mines | [26 empty] | T112 | Identified potential SLP adoption mines | [36 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T113 | Full Adoption Team assessment of SLP | SLP assessment form discussed and confirmed at meeting of full industry adoption team Yes or No ¦ Date confirmed | Monthly | Yes | 0 | 0 | 0 |  | 2030-01-01 | 2030-01-01 | Full Adoption Team assessment of SLP | [26 empty] | T113 | Full Adoption Team assessment of SLP | [36 empty] | 2030-01-01 | 2030-01-01 | 0
| Documention of SLP | [11 empty] | Documention of SLP | [26 empty] | Documantation of SLP
|  | T114 | Arrangements with source mine | Arrangements for investigation set up and ageeed in writing with mine manager Yes or no ¦ Date agreed | Monthly | Yes | 90 | 100 | 2013-05-15 |  | 2013-05-30 | 2030-01-01 | Arrangements with source mine | [8 empty] | 90 |  | 100 | 2013-05-15 | [14 empty] | T114 | Arrangements with source mine | [36 empty] | 2013-05-30 | 2030-01-01 | 100 | 2013-05-15
|  | T115 | Investigations at source mine | Investigations at source mine conducted in accordance with handbook Estimate of % complete ¦ Date completed | Monthly | 100% | 0 | 0 | 0 |  | 2030-01-01 | 2030-01-01 | Investigations at source mine | [26 empty] | T115 | Investigations at source mine | [36 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T116 | Documentation of SLP | Findings from source mine documented and on file in website database Estimate of % complete¦ Date completed | Monthly | 100% | 0 | 0 | 0 |  | 2030-01-01 | 2030-01-01 | Documentation of SLP | [26 empty] | T116 | Documentation of SLP | [36 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T117 | Formal review by Review Panel | Formal review by duly convened indepenndent review panel Yes or no ¦ Date completed | Monthly | Yes | 0 | 0 | 0 |  | 2030-01-01 | 2030-01-01 | Formal review by Review Panel | [26 empty] | T117 | Formal review by Review Panel | [36 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T118 | Customisation of SLP behavioural plans | Standard SLP behavioural plans updated to take account of SLP specifics Estimate of % completed ¦ Date completed | Monthly | 100% | 0 | 0 | 2013-07-20 |  | 2013-07-14 | 2030-01-01 | Customisation of SLP behavioural plans | [15 empty] | 2013-07-20 | [10 empty] | T118 | Customisation of standard SLP behavioural plans | [36 empty] | 2013-07-14 | 2030-01-01 | 0 | 2013-07-20
|  | T119 | Preparation / external review of SLP adoption brief | SLP Adoption Brief finalised following external review and on file in website database Estimate of % complete¦ Date completed | Monthly | 100% | 0 | 0 | 0 |  | 2030-01-01 | 2030-01-01 | Preparation of SLP adoption brief | [26 empty] | T119 | Preparation / external review of SLP adoption brief | [36 empty] | 2030-01-01 | 2030-01-01 | 0
| Facilitation of widespread adoption | [11 empty] | Facilitation of widespread adoption | [26 empty] | Facilitation of widespread adoption
|  | T120 | Potential adoption mines & key contacts | Prioritised list of potential adoption mines with contact details of key persons Estimate of % completed ¦ Date completed | Monthly | 100% | 0 | 0 | 2013-08-30 |  | 2013-09-15 | 2030-01-01 | Potential adoption mines & key contacts | [17 empty] | 2013-08-30 | [8 empty] | T120 | Identified key contacts at potential adoption mines | [36 empty] | 2013-09-15 | 2030-01-01 | 0 | 2013-08-30
|  | T121 | Invitation to briefing workshop | SLP Adoption Brief and briefing workshop invitation sent to key persons at all potential adoption mines Estimate of % complete ¦ date completed | Monthly | 100% | 0 | 0 | 0 |  | 2030-01-01 | 2030-01-01 | Invitation to briefing workshop | [26 empty] | T121 | Circulation of SLP Adoption Brief | [36 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T122 | Effectiveness of SLP Briefing Workshop | Standard SLP Briefing Workshop assessment form completed by all attendees to assess effectiveness of workshop Assessment score in % ¦ Date completed | Monthly | >80% | 0 | 0 | 0 |  | 2030-01-01 | 2030-01-01 | Effectiveness of SLP Briefing Workshop | [26 empty] | T122 | SLP Briefing Workshop | [36 empty] | 2030-01-01 | 2030-01-01 | 0
|  | T123 | Adoption reporting arrangements | Email to key person at all potential adoption mines requesting participation in monthly tracking of SLP adoption Number of mines invited ¦ % participating | Monthly | 100% participatn | 0 | 0 | 0 | 0 | 2030-01-01 | 2030-01-01 | Adoption reporting arrangements |  |  |  |  | 100 | 24 | 100 | 24 | [18 empty] | T123 | Adoption reporting arrangements | [36 empty] | 2030-01-01 | 2030-01-01
|  |  | This date is entered in yellow font in place of the planned completion dates, which should be entered for each indicator once the relevant completion date has been planned | [7 empty] | 2030-01-01
Formulas:
Measure 2 Prev Curr = IF([Meas 2]>0,[Meas 2],IF([Meas 2]>0,[Meas 2],IF([Meas 2]>0,[Meas 2],IF([Meas 2]>0,[Meas 2],IF([Meas 2]>0,[Meas 2],IF([Meas 2]>0,[Meas 2],IF([Meas 2]>0,[Meas 2],IF([Meas 2]>0,[Meas 2],IF([Meas 2]>0,[Meas 2],IF([Meas 2]>0,[Meas 2],IF([Meas 2]>0,[Meas 2],IF([Meas 2]>0,[Meas 2],IF([Meas 2]>0,[Meas 2],0)))))))))))))
Meas 2 = IF([Measure 2 Prev Curr]>0,[Measure 2 Prev Curr],"")
Each adoption team should enter into thiis column the planned completion dates for each of the activities / indicators
Broad guide for estimation of % complete
In general it would be appropriate for the the estimates of %-age completion to be based on an estimate of time spent to date as a % of the total time required for the work in question, with both time periods being estimates in person days, as opposed to calendar days.
For indicators involving data gathering and report / document preparation, the following scale is likely to roughly approximate estimates based on work time. It is provided for guidance and to help ensure that the time required for report writing and finalisation of the document are not grossly underestimated.
0 % No work yet
10 % Required work planned and initiated
20 % Early stages of data gathering
30% Late stages of data gathering
40 % Required data gathered - write-up started
50 % Analysis in progress
60 % Data analysed
70 % First draft of document complete
80% Review and comment process in progress
90 % Document updated and edited
100 % Document finalised and posted, all work complete
Conditional formatting on monthly scorecard printout
The cells in this print out have been conditionally formatted as follows:
White for cells where no data has yet been entered into the data entry sheet
Amber for cells where there has been no progress since the last report, or where the entered completion date is later than the scheduled completion date
Green for cells where progress has been made or where the entered completion date is before the scheduled completion date
Dark pink for cells where the activity is still in progress after the scheduled completion date has passed
Conditional formatting on 12-month data entry sheet
The cells in the 12-month data entry sheet have been conditionally formatted to grey out the remaining cells in a row once the completion date has been entered.
The data entry table otherwise contains no formulas so values may be entered , deleted and changed in the sheet without affecting the conditional formatting .
The corrected values in the data entry sheet will be pulled through into the monthly scorecard printout.
The month of the scorecard report must be entered in this cell in the example three letter month format, to enable the correct data to be pulled through from the 12-month data entry table
Procedure for using the above M&E Framework tables
Step 1: Plan work on the leading practice for the year in question entering the planned completion date for each indicator in the monthly print out table
Step 2: Enter the relevant data for December of the previous year in the 12 month data entry table.
Step 3: At the end of each month enter tinto the 12 month data entry table the relevant data for the two measures for each of the indicators for the leading practice in question
Step 4: Enter the three digit month indicator in the top right hand cell of the monthly print out table . The table will then be automatically updated and may then be printed. for the month in question.
Note: Apart form the planned completion date on the pmonthly rint out table, all data entries / corrections should be made on the 12 month data entry table
Yellow for cells where the planned completion date has not yet been entered
Note: Initially, the originally planned completion dates should be entered into both of the above two columns. The currently agreed column would then be updated when a new completion date is necessary and has been agreed upon. Both columns currently contain default completion dates set at 1 Jan 2030 - when planned dates are entered they will be displayed in clear cells using black font.
Note: These two columns will be hidden as they are purely used to preserve the completion dates for printing in the scorecard when it is printed for later months.
Note: Regarding the use of this chart for planning and updating purposes, please see notes 1 to 4 on the planning chart of the team leading practice scorecard.

## LP Adoption Scorecard
Leading Practice Adoption Scorecard - Rev 0 Date of report: Monitoring of Widespread Eager Adoption of Leading Practice Name of Leading Practice:
Identified potential adoption mines | [9 empty] | Total no. of employees at mine | Estimated no. of personel at mine to benefit from LP | Date adoption initiated (including not to LPAG) | Date adoption completed (Including not to LPAG) | Investment in adoption (Rand value of time and purchases) | Learning accommodated (Specific provision - Y/N) | I = In Progress C = Completed S = Signed Off N = Decided no | [9 empty] | No. of People to Train | No. of People Trained | Overall progress (Not only training) | I = In Progress C = Completed S = Signed Off
No. | Name of Mine | Company | Name of Manager | Commodity | Region/ Province | Chamber Member (Yes / No) | Name of Project Leader | E-mail Address of Project Leader | Telephone Number | [6 empty] | Leading Practice investigated for adoption | Adoption Plan (including M&E) | Leading Practice Procedures Customised | Mental Model Interviews | Customised Leadership Behaviour Plan | Customised Behaviour Communication Plan | Risk Assessment | Training Lesson Plans | Management Sign-off (Review Process) | Roll-out plan in place |  |  |  | Signed Off Factor | [9 empty] | Completion Factor | [9 empty] | In Progress Factor | [9 empty] | Decided No | Progress Table
1 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
2 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
3 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
4 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
5 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
6 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
7 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
8 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
9 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
10 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
11 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
12 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
13 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
14 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
15 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
16 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
17 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
18 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
19 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
20 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
21 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
22 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
23 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
24 | [27 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[28 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
[29 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 0% | #DIV/0!
Number Signed Off | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | #DIV/0!
Percentage with process documents Signed Off | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Percentage Completed but not Signed Off | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Percentage with Work In Progress | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Percent decided No | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Percentage of mines No Action | [15 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Key quarter-end data (reposition / insert month headings as necessary) | [8 empty] | Current Value | 2013-03-01 | 2013-06-01 | 2013-09-01 | 2013-12-01 | 2014-03-01 | 2014-06-01 | 2014-09-01 | 2014-12-01 | 2015-03-01 | 2015-06-01 | 2015-09-01 | 2015-12-01 | 2016-03-01 | 2016-06-01 | 2016-09-01 | 2016-12-01
Number of potential adoption mines | [8 empty] | 24 | [53 empty] | #DIV/0!
Number of signed off adoption roll out plans (according to LPAG) | [8 empty] | 0
Number of reported other adoptions (not according to LPAG) | [8 empty] | 0
Cells within this area of the Scorecard have been conditionally formatted and are thus automatically colour coded depending on the letter entered, according to the legend provided above.
Cells to the far right and below this area contain code to calculate the cell contents, depending on the letters entered into the cells in this region
Presentation of this scorecard can be simplified by hiding all or some of the columns covered by this text box, and then printing the scorecard in portrait orientation using the option to fit all columns on one page.
Note: Only enter numbers in rows that contain the names of identified potential adoption mines
Note: The current values are updated every time the table is updated - At the end of each quarter the table should be updated and the current value simply entered into the cell for the appropriate quarter

## SLP Adoption Scorecard
SLP Adoption Scorecard - Rev 0 Date of report: Monitoring of Widespread Eager Adoption of SLP Name of SLP: | [15 empty] | Calculator Matrix Not included in print area Columns may be hidden if preferred
Identified potential adoption mines | [9 empty] | Total no. of employees at mine | Total no. of production personnel at mine | Date of Email request to participate adoption tracking | Date of first monthly feedback report from mine | Date reported SLP adoption | Date of confirmed adoption according to adoption brief
No. | Name of Mine | Company | Name of Manager | Commodity | Region/ Province | Chamber Member (Yes / No) | Name of Project Leader (Key contact) | E-mail Address of Project Leader (Key contact) | Telephone Number | [6 empty] | Mine name | Key Contact | Date of Email request | Date of first report from mine | Date SLP adopted | Date confirmed according to brief
1 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
2 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
3 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
4 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
5 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
6 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
7 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
8 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
9 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
10 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
11 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
12 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
13 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
14 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
15 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
16 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
17 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
18 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
19 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
20 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
21 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
22 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
23 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
24 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
25 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
26 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
27 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
28 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
29 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
30 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
31 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
32 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
33 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
34 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
35 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
36 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
37 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
38 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
39 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
40 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
41 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
42 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
43 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
44 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
45 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
46 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
47 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
48 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
49 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
50 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
51 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
52 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
53 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
54 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
55 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
56 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
57 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
58 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
59 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
60 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
61 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
62 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
63 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
64 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
65 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0
Number of potential adoption mines | [13 empty] | 0
Number of potential adoption mines with identified key contact persons ¦ % of potential adoption mines | [10 empty] | 0 | 0 | 0 | 0 | 0%
Number of mines invited to participate in adoption feedback ¦ % of potential adoption mines | [13 empty] | 0 | 0%
Number of mines that have reported adoption data ¦ % of mines actually invited | [13 empty] | 0 | 0%
Number of reported adoptions of SLP ¦ % of participtng adoptn mines | [10 empty] | 0 | 0 | 0 | 0 | 0%
Number of reported adoptions (confirmed according to adoption brief) ¦ % of participtng adoptn mines | [10 empty] | 0 | 0 | 0 | 0 | 0%
Number of other reported adoptions ¦ % of participtng adoptn mines | [10 empty] | 0 | 0 | 0 | 0 | 0%
Key quarter-end data (reposition / insert month headings as necessary) | [8 empty] | Current Value | 2013-06-01 | 2013-09-01 | 2013-12-01 | 2014-03-01 | 2014-06-01 | 2014-09-01
Number of potential adoption mines | [8 empty] | 0
Number of reported adoptions confirmed according to adoption brief | [8 empty] | 0
Number of other reported adoptions | [8 empty] | 0
Note: The current values are updated every time the table is updated - At the end of each quarter the table should be updated and the current value simply entered into the cell for the appropriate quarter