## Old Sheet (hidden)
0
MOSH FOG Adoption Programme Monitor for the Adoption of the Leading Practice of Netting with Bolting 04 May 2012
[8 empty] | Leading Practice Adoption Process Review (Yes = Y, No = N) | [6 empty] | I = In Progress C = Completed S = Signed Off | [12 empty] | I = In Progress C = Completed S = Signed Off
| No. | Name of Mine | Company | Name of Manager | Name of Project Leader | E-mail Address of Project Leader | Telephone Number | Do you have a FOG Risk associated with Entry Examination and Making Safe | Do you have FOG Risk Controls in place | Do you have a Procedure on Entry Examination and Making Safe | Is your FOG related LTIFR<0,05 | Have you considered the Adoption of the Leading Practice on Examination and Making Safe | Yes, we want to Adopt the Leading Practice on Examination and Making Safe | No, we do not want to Adopt the Leading Practice on Examination and Making Safe | Leading Practice Adoption Review | Implementation Plan | Procedure Amended | Mental Model Interviews | Leadership Behaviour Plan | Behaviour Communication Plan | Risk Assessment | Training Lesson Plans | Management Review Process | Roll-out plan in place | No. of Crews to Train | No. of Crews Trained | Progress | Signed Off Factor | [9 empty] | Completion Factor | [9 empty] | In Progress Factor | [9 empty] | Progress Table
g | 1 | Masimong 5 | Harmony |  | Rusiano Tsoka | rusiano.tsoka@harmony.co.za | 829271018 | [7 empty] | S | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
b | 2 | Savuka | Anglo Gold Ashanti |  | Thembinkosi Madondo | mmadondo@anglogoldashanti.com | 187006279 | [7 empty] | S | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
b | 3 | Kopanang | Anglo Gold Ashanti | Francois Naude |  | fnaude@anglogoldashanti.com | 713635097 | [7 empty] | S | N | N | [10 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
b | 4 | Target 1 | Harmony |  | Marius Van der Merwe | marius.vandermerwe@harmony.co.za | 0723684289/0574524445 | [7 empty] | S | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
g | 5 | Phakisa | Harmony | Rudi Phillis | Tienie Landman | Tienie.Landman@Harmony.co.za | 579167111 | [7 empty] | S | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
e | 6 | Eastern Mines | Xstrata Alloys |  | Phil Garner | pgarner@xstrata.co.za | 829219441 | [7 empty] | N | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | 7 | Mponeng | Anglo Gold Ashanti | Randel Rademan |  | crrademann@anglogoldashanti.com | 187005450 | [7 empty] | S | S | I | S | I | I | [5 empty] | S |  | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 |  | 1 | [5 empty] | #VALUE! | 30% | #VALUE!
g | 8 | Target 3 | Harmony |  | Velaphi Waganda | velaphi.waganda@harmony.co.za | 579074114 | [7 empty] | S | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [8 empty] | #DIV/0! | 10% | #DIV/0!
g | 9 | Joel | Harmony |  | Warren Freeman | Warren.Freeman@harmony.co.za | 847016876 | [7 empty] | N |  |  |  |  | S | S | S | S | S |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1 | 1 | 1 | 1 | #DIV/0! | 40% | #DIV/0!
g | 10 | TauTona | Anglo Gold Ashanti | Andre van Jaarsveld | Danny Davis | ddavies@anglogoldashanti.com | 187008963 | [7 empty] | S | S | S | S | I | I | S | S |  | I | 53 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 |  | 0 | 60% | 0%
b | 11 | Impala (1) | Impala | Mathias Sithole |  | Mathias.sithole@implats.co.za | 829431572 | [7 empty] | S | I | I | S | S | S | S | S | S | S |  |  | 61300% | 50 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | #DIV/0! | 70% | #DIV/0!
g | 12 | Impala (2) | Impala | Nelson Ndlala |  | nelson.ndlala@implats.co.za | 829410912 | [7 empty] | S | I | I | S | S | S | S | S | S | S |  |  |  | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | #DIV/0! | 70% | #DIV/0!
e | 13 | Kusasalethu | Harmony | Theo Keyter |  | Theo.Keyter@harmony.co.za | 187829152 | [7 empty] | S |  |  | S | S | S | S | S | S | S |  |  |  | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | #DIV/0! | 70% | #DIV/0!
e | 14 | Bambanani Mine | Harmony | Pieter Fourie | Pieter Fourie | Pieter.Fourie@harmony.co.za | 829403283 | [7 empty] | S | S | S |  |  |  | I | I | [5 empty] | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | [6 empty] | #DIV/0! | 30% | #DIV/0!
e | 15 | Doornkop Mine | Harmony |  | Sisanda Nompumza | SisandaNompumza@harmony.co.za | 732569101 | [7 empty] | S | S | S |  |  |  | I | I | I | I |  |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | #DIV/0! | 30% | #DIV/0!
b | 16 | Tshepong | Harmony | Adriano Sobreira | Kenny Makgakga | Kenny.makgakga@harmony.co.za | 0579072188/0828801325 | [7 empty] | S | S | S |  |  | S | I | I | I | I |  |  |  | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 |  |  |  | #DIV/0! | 40% | #DIV/0!
e | 17 | Karee Mine | Lonmin |  | Eddie Landsberg | Eddie.landsberg@lonmin.com | 836074875 | [7 empty] | S | S | S | I | I | S | S | S |  |  | 219 | 150 |  | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 |  |  | 1 | 1 | 1 |  | 0.68493 | 60% | 6.849%
b | 18 | Evander | Harmony | Manny Da Silva | Wynand Van Der Mesch | wynand.van der Mescht@harmony.co.za | 0176201606/0834243001 | wynand.van der Mescht@harmony.co.za | [6 empty] | S | S | S |  |  | S | S | S | I | I |  |  |  | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 |  | #DIV/0! | 60% | #DIV/0!
g | 19 | Bafokeng Rasimone | Royal Bafokeng Platinum | Glenn Harris | Chisto Haasbroek | christoh@Bafokengplatinum.co.za | [8 empty] | S | S | S | I | I | I | S | S | I |  | 130 | S |  | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 |  |  |  | 1 | 1 |  | #VALUE! | 50% | #VALUE!
g | 20 | KDC | Gold Fields | Henry Barnard |  | Henry.barnard@goldfields.co.za | [8 empty] | S | S | S | S | [9 empty] | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | [5 empty] | #DIV/0! | 40% | #DIV/0!
e | 22 | Kalgold | Harmony |  | Motoma Modise | Modise.motoma@harmony.co.za | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
e | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
e |  |  |  | UNISEL (NOT REGISTERED | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
e | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
b | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
b | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
b | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
b | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
b | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
b | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
b | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
e | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0! | #REF! | #VALUE!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
b | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
e | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
e | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
e | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
c | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
e | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
b | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
g | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
|  |  |  | MOAB KHOTSONG (NOT REGISTERED) |  |  | Johan Oelofse | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! | 0% | #DIV/0!
[28 empty] | 67 | 9 | 8 | 6 | 3 | 7 | 8 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 2 | 4 | 3 | 3 | 3 | 4 | 4 | [11 empty] | #DIV/0!
[28 empty] | 319% | 42.86% | 38.1% | 28.57% | 14.29% | 33.33% | 38.1% | 38.1% | 19.05% | 19.05% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 14.29% | 9.524% | 19.05% | 14.29% | 14.29% | 14.29% | 19.05% | 19.05%
[15 empty] | LP Review | Implementation Plan | Procedure Amended | MM Interviews | LB Plan | BC Plan | Risk Assessment | Lesson Plans | Management Reviews | Roll Out Plan
|  | Horizon Chrome Mine | Xstrata | Mr. D Ngubane | M Prinsloo & R v Rooyen | mprinsloo@xstrata.co.za | 082 871 3552 or 083 587 1167 | Y | Y | Y | N | Y | Y |  | S |  | I | C
|  | Kroondal Chrome Mine | Xstrata | Mr. R Murley | M Prinsloo & R v Rooyen | mprinsloo@xstrata.co.za | 082 871 3552 or 083 587 1167 | Y | Y | Y | N | Y | Y |  | S |  | S | S | S | S | S | S | S | S
|  | Waterval Chrome Mine | Xstrata | Mr. V Makuni | M Prinsloo & R v Rooyen | mprinsloo@xstrata.co.za | 082 871 3552 or 083 587 1167 | Y | Y | Y | N | Y | Y |  | S |  | S | S | S | S | S | S | S | S
Assmang:
Dwarsrivier
Responsible manager : Bert Nel 082 701 8007
Project co-ordinator: Kassie Kasselman , ,
18 crews need to be trained.
The process has been completed up to the roll-out plan. Further progress is apparently hampered by production pressure and limited training facilities.
Black Rock Mining Operations.
Officially the process has not started in the NW Cape but in discussions with management it was decide to make a start.
Responsible manager: Cristopher Melamu, 082 643 7475, cristopherm@brmo.co.za
The process has been discussed with Cristopher who is very keen to get involved. I recommended that he contacts Lazarus at Nkomati for guidance since the mining method at Nkomati is identical to that at BRMO and Lazarus has completed the process.
To date Cristopher has not contacted Lazarus.
Progress in the NW Cape is also a function of the official creation of a COPA. It is recommended that this be instituted.
| 40 | Bambanani | Harmony | Mr. Z Ndese | Maurice Mkhwanazi | maurice.mkwanazi@harmony.co.za | O832870330 | S
| 41 | Bush / Viginia | Harmony | Mr. S Green | Marius Barnard | marius.barnardjn@harmony.co.za |  | S | I
| 42 | Doornkop | Harmony | Mr. B van Zyl | Jacques Du Triou | jacques.dutriou@harmony.co.za | O829268898 | S
| 43 | Elandsrand | Harmony | Mr. T Keyter | Sizwe Mthethwa | sizwe.mthethwa@harmony.co.za | O833789413 | S
| 44 | Evander | Harmony | Mr. M da Silva | Marius Pelser | marius.pelser@harmony.co.za | O824411266 | S | S | S | I | I
| 45 | Joel | Harmony | Mr. K Moagi | Warren freeman | warren.freeman@harmony.co.za | O847016876 | S
| 46 | Target | Harmony | Mr. A Sobreira | Kobus Van Tonder | kobus.vantonder@harmony.co.za | O795011566 | S
| 47 | Tshepong | Harmony | Mr. F Janse van Rensburg | Willem Gouws | willem.gouws@harmony.co.za | O836070850 | S | I
| 48 | Phakisa / Nyala | Harmony | Mr. A van Wyk | Marcus Maree | marcus.maree@harmony.co.za | O579167293 | S
| 49 | Masimong 4,5 | Harmony | Mr. H Bornman | None
18
| 42 | Unisel Operation | Harmony | Mr. S Green | Mr. Marius Barnard | marius.barnardjn@harmony.co.za | 724965737 | S | S | S | S | S | S | S | S | 29 | 17 | 96%
|  | 16 | Great Noligwa | AngloGold Ashanti | Mr. J Ferreira | Mr. E Mohlabi | emohlabi@anglogoldashanti.com | (018) 478-8061 | S | S | S | C | C | I |  |  | 82 |  | 40%

## N&B
0
MOSH FOG Adoption Programme Monitor for the Adoption of the Leading Practice for Applying Nets with Bolts in Narrow Reef Hard Rock Workings 27 August 2012
COPA | Commodity | Number | Name of Mine | Company | Name of Manager | Name of Project Leader | E-mail Address of Project Leader | Telephone Number | Do you have a FOG Risk associated with nets with bolts? | Do you have FOG Risk Controls in place | Do you have a Procedure on the applicationof Bolts with Nets | Is your FOG related LTIFR<0,05 | Have you considered the Adoption of the Leading Practice on Nets with Bolts | Yes, we want to Adopt the Leading Practice on Nets with Bolts | No, we do not want to Adopt the Leading Practice on Nets with Bolts | Leading Practice Adoption Review | Implementation Plan | Procedure Amended | Mental Model Interviews | Leadership Behaviour Plan | Behaviour Communication Plan | Risk Assessment | Training Lesson Plans | Management Review Process | Roll-out plan in place | No. of Crews to Train | No. of Crews Trained | Total Number of employees | Progress | Signed Off Factor | [9 empty] | Completion Factor | [9 empty] | In Progress Factor | [9 empty] | Progress Table
|  | 1 | Masimong 5 | Harmony | Rudi Phillis | Pieter Ferreira | rusiano.tsoka@harmony.co.za | 829271018 | y | Y | Y | Y | Y |  |  | S | S | S | S | S | S | S | S | S | S | 58 | 58 |  | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 2 | Savuka | Anglo Gold Ashanti | Andre van Jaarsveld | Cassie Combrink | mmadondo@anglogoldashanti.com | 187006279 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | I | 12 | 3 |  | 84.09% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.25 | 90% | 2.5%
|  | 3 | Kopanang | Anglo Gold Ashanti | Francois Naude |  | fnaude@anglogoldashanti.com | 713635097 | y | y | y | y | y |  |  | S | S | S | I | I | I | I | I | I | I | 63 | 0 |  | 27.27% | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 0 | 30% | 0%
|  | 4 | Target 1 | Harmony |  | Marius Van der Merwe | marius.vandermerwe@harmony.co.za | 0723684289/0574524445 | y | y | y | y | y |  |  | S | S | S | S | S | s | s | s | s | s | 8 | 3 |  | 94.32% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.375 | 90% | 3.75%
|  | 5 | Phakisa | Harmony |  | Tienie Landman | Tienie.Landman@Harmony.co.za | 579167111 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 51 | 51 | 1166 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 6 | Mponeng | Anglo Gold Ashanti | Clive vd Westhuizen | Floyd Masemula |  | 187005450 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | I | I | S | 67 | 14 |  | 74.63% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 0.20896 | 70% | 2.09%
|  | 7 | Target 3 | Harmony |  | Velaphi Waganda | velaphi.waganda@harmony.co.za | 579074114 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 21 | 21 |  | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 8 | Joel | Harmony |  | Warren Freeman | Warren.Freeman@harmony.co.za | 847016876 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 33 | 33 |  | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 9 | TauTona | Anglo Gold Ashanti | Andre van Jaarsveld | Mervin Gillepsie | ddavies@anglogoldashanti.com | 187008963 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 48 | 12 | 3200 | 93.18% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.25 | 90% | 2.5%
|  | 10 | Impala (UG2) | Impala | Mathias Sithole |  | Mathias.sithole@implats.co.za | 829431572 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 313 | 200 |  | 96.72% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.63898 | 90% | 6.39%
|  | 11 | Impala (Merensky) | Impala | Nelson Ndlala |  | nelson.ndlala@implats.co.za | 829410912 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 280 | 271 | 10500 | 99.71% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.96786 | 90% | 9.679%
|  | 12 | Kusasalethu | Harmony |  | Larry Briggs |  | 187829152 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 72 | 72 |  | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 13 | Bambanani Mine | Harmony | Pieter Fourie | Pieter Fourie | Pieter.Fourie@harmony.co.za | 829403283 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 55 | 55 |  | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 14 | Doornkop Mine | Harmony | Jaques Du Triou | Bennie Nelson | Jacobus.Nelson@harmony.co.za | 112786712 | y | y | y | y | y | y |  | S | S | S | S | S | S | S | S | S | S | 49 | 49 | 3734 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 15 | Tshepong | Harmony | Adriano Sobreira | Kenny Makgakga | Kenny.makgakga@harmony.co.za | 0579072188/0828801325 | y | y | y | y | y |  |  | S | S | S | s | S | S | S | S | S | S | 87 | 87 | 3000 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 16 | Lonmin | Lonmin |  | Eddie Landsberg | Eddie.landsberg@lonmin.com | 836074875 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | S | 496 | 264 | 8400 | 95.75% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.53226 | 90% | 5.323%
|  | 17 | Evander | Pan African | Manny Da Silva | Wynand Van Der Mesch | wynand.van der Mescht@harmony.co.za | 0176201606/0834243001 | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | S | I | 21 | 0 |  | 81.82% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 90% | 0%
|  | 18 | Bafokeng Rasimone (M) | Royal Bafokeng Platinum | Glenn Harris | Chisto Haasbroek | christoh@Bafokengplatinum.co.za |  | y | y | y | y | y |  |  | S | S | S | I | I | I | S | S | I | S | 100 | 0 |  | 54.55% | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 |  |  |  | 1 | 1 |  | 0 | 50% | 0%
|  | 19 | Rasimone UG2 | [12 empty] | S | S | S | S | S | S | S | S | S | S | 30 | 30 |  | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 20 | Sibanye Gold(Kloof & Dries) | Gold Fields | Henry Barnard |  | Henry.barnard@goldfields.co.za |  | y | y | y | y | y |  |  | S | S | S | S | S | S | S | S | I | I | 334 | 8 | 6359 | 72.95% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0.023952 | 80% | 0.2395%
|  | 21 | Great Noligwa | Anglo Gold Ashanti |  | Noah Mabunda | [9 empty] | S | S | s | s | I | I | s | s | I | s | 29 | 0 | 1827 | 63.64% | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 |  |  | 1 | 1 |  | 0 | 60% | 0%
|  | 22 | UNISEL |  |  | T Benzien |  |  | Y | Y | Y | Y | Y | Y |  | S | S | S | S | S | S | S | s | s | s | 52 | 52 |  | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 90% | 10%
|  | 23 | MOAB KHOTSONG (NOT REGISTERED) | Anglo Gold Ashanti | Moses Madondo | Dannie Davies |  |  | Y | Y | Y | Y | Y | Y |  | S | S | S | s | I | I | I | S | I | I | 44 | 20 |  | 49.59% | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 0.45455 | 50% | 4.545%
|  | 24 | COOKE 4 Ezulwini |  |  | Tony Ward | [9 empty] | s | S | S | I | I | I | I | I | I | I |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1
|  | 25 | Hernic Ferrochrome | [12 empty] | i | [9 empty] | 20 | 20 | 23320 | 9.091%
|  | Number of Units Signed Off | [13 empty] | 24 | 23 | 23 | 21 | 19 | 19 | 21 | 21 | 17 | 18 | 2323 | 1323 |  |  | 23 | 23 | 23 | 21 | 19 | 19 | 21 | 21 | 17 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 5 | 3 | 2 | 6 | 5 | [11 empty] | 5.695%
|  | Percentage of Units with Documents Signed Off | [13 empty] | 95.83% | 95.83% | 95.83% | 87.5% | 79.17% | 79.17% | 87.5% | 87.5% | 70.83% | 75% | 82.83% |  |  | 82.83% | 95.83% | 95.83% | 95.83% | 87.5% | 79.17% | 79.17% | 87.5% | 87.5% | 70.83% | 75% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.5% | 20.83% | 20.83% | 12.5% | 8.333% | 25% | 20.83%
|  | Percentage of Units Completed not Signed Off | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Percentage of Units with Work In Progress | [13 empty] | 0% | 0% | 0% | 12.5% | 20.83% | 20.83% | 12.5% | 8.333% | 25% | 20.83%
|  | Percentage of Units No Action | [13 empty] | 4.167% | 4.167% | 4.167% | 0% | 0% | 0% | 0% | 4.167% | 4.167% | 4.167%
[16 empty] | LP Review | Implementation Plan | Procedure Amended | MM Interviews | LB Plan | BC Plan | Risk Assessment | Lesson Plans | Management Reviews | Roll Out Plan