## Slide 1: DUST TEAM u p - d a t e November 2014 to date
by
Gerrie Pienaar, Johan van Rensburg and Dr Audrey Banyini
22 January 2015
CHAMBER OF MINES OF SOUTH AFRICA
Putting South Africa First

## Slide 2
Contents
Mission and values reminder
Progress update – key indicators
Highlights
Lowlights
Key lessons learnt
SLP progress
Year Planner - 2015
Leading the change to zero harm

## Slide 3
Mission and Values – MOSH
To facilitate the adoption of leading practice through a people oriented process to significantly improve occupational health and safety in the minerals industry
Our ultimate goal is the provision of working conditions that are free from harmful effects
Values
Leading the change to zero harm

## Slide 4
Mission and Values – MOSH Dust
To facilitate the adoption of leading and/or simple leading practices through a people oriented process to significantly improve occupational health in the minerals industry with specific focus on THE ELIMINATION OF SILICOSIS AND DUST RELATED DISEASES
Values
Leading the change to zero harm

## Slide 5
Leading Practice - key indicators
Leading the change to zero harm
KPA No | Key Performance Area | KPI No | KPI | Continuous real-time monitoring of engineering dust controls
A1 | Appropriate persons to select leading practice | T4 | Approved participants list | 100% (100%)
A2 | Appropriate plans for planning workshop | T8 | HOH review and approval | 100% (100%)
A3 | Detailed expert model of risk story | T12 | Detailed expert models | 100% (100%)
 |  | T14 | Peer Group assessment | 0% (0%)
A4 | Leading practice with greatest OHS impact | T19 | Credibility of selected Leading Practice | 100% (100%)
A5 | Adoption mines and key people | T22 | Prioritised list of mines and key people | 100% (100%)
A6 | Direct enquiry protocol | T27 | Direct enquiry protocol | 100% (0%)
A7 | Effective direct enquiry process | T30 | Interview process | Moab Khutsong: Completed Beatrix: Completed Phakisa: Completed Anglo Platinum: t.b.a. Finch: t.b.a.
A8 | Detailed mental models report | T33 | Mental models report | -
 |  | T34 | Identification of implications | -

## Slide 6
SLP - Key Indicators
KPA No | KPA | KPI No | KPI | Multi-stage Filtration Systems | Winch Covers | Water Blast | Telescopic Spray | Stop-and-fix: managing worker dust exposure with real-time monitoring at a Primary Tip - Collieries
IDENTIFY |  |  |  |  |  |  |  | 
A 23 | SLP adoption | T112 | Identified potential SLP adoption mines | Yes | Yes | Yes | Yes | Yes
 |  | T113 | Full Adoption Team assessment of SLP | Yes | Yes | Yes | Yes | Yes
 |  | T114 | Contact manager of source mine to arrange access | Yes | Yes | Yes | Yes | Yes
 |  | T115 | Identify key contact person at source mine | Yes | Yes | Yes | Yes | Yes
DOCUMENT |  |  |  |  |  |  |  | 
 |  | T116 | Conduct investigations at source mine | 100% (100%) | 100% (100%) | 100% (100%) | 100% (100%) | 100% (100%)
 |  | T117 | Prepare documents for formal SLP assessment | 100% (100%) | 100% (100%) | 100% (100%) | 100% (100%) | 100% (100%)
 |  | T118 | Confirm accuracy of prepared documents with source mine | 100% (100%) | 100% (100%) | 100% (100%) | 100% (100%) | 100% (100%)
 |  | T119 | Final review of documents against SLP criteria by adoption team | 100% (100%) | 100% (100%) | 100% (100%) | 100% (100%) | 100% (100%)
 |  | T120 | Submit motivation of SLP to Head of Hub | 100% (100%) | 100% (100%) | 100% (100%) | 100% (100%) | 100% (100%)
Name change pending

## Slide 7
SLP - Key Indicators
KPA No | KPA | KPI No | KPI | Multi-stage Filtration Systems | Winch Covers | Water Blast | Telescopic Spray | Stop-and-fix: managing worker dust exposure with real-time monitoring at a Primary Tip - Collieries
DOCUMENT (cont.) |  |  |  |  |  |  |  | 
 |  | T121 | Convene SLP review panel | 100% (100%) | 100% (100%) | HoLH to advice | HoLH to advice | HoLH to advice
 |  | T122 | Formal review of SLP by review panel | 100% (100%) | 100% (100%) | - | - | HoLH to advice
 |  | T123 | Conduct any necessary follow-up investigations | Not required | 100% (100%) | - | - | -
 |  | T124 | Prepare customised SLP behaviour plans | 100% (100%) | 100% (100%) | - | - | -
 |  | T125 | Develop guidance notes for SLP adoption | 100% (100%) | 100% (100%) | - | - | -
 |  | T126 | Prepare SLP Adoption Brief | 100% (100%) | 100% (100%) | - | - | -
 |  | T127 | Critical review of SLP Adoption Brief | 100% (100%) | 100% (100%) | - | - | -
Planned for 1st QTR 2015??
Leading the change to zero harm

## Slide 8
SLP - Key Indicators
KPA No | KPA | KPI No | KPI | Multi-stage Filtration Systems | Winch Covers | Water Blast | Telescopic Spray | Stop-and-fix: managing worker dust exposure with real-time monitoring at a Primary Tip - Collieries
FACILITATE |  |  |  |  |  |  |  | 
 |  | T128 | Update list of potential adoption mines | 100% (100%) | 100% (100%) | - | - | -
 |  | T129 | Identify key contact persons at potential adoption mines | 100% (100%) | 100% (100%) | - | - | -
 |  | T130 | Arrange SLP Briefing Workshop | 100% (100%) | 100% (100%) | - | - | -
 |  | T131 | Circulate SLP Adoption Brief to potential adoption mines | 100% (100%) | 100% (100%) | - | - | -
 |  | T132 | Conduct SLP Briefing Workshop | 100% (100%) | 100% (100%) | - | - | -
 |  | T133 | Establish SLP interest group if required | 100% (100%) | 100% (100%) | - | - | -
 |  | T134 | Initiate process of mines reporting on adoption | 100% (100%) | 100% (100%) | - | - | -
 |  | T135 | Provide SLP adoption brief for use at other meetings | 100% (100%) | 100% (100%) | - | - | -
 |  | T136 | Monthly follow-up communication with potential adoption mines | Scheduled meetings finalised |  | - | - | -
 |  | T137 | Arrange meetings / terminate SLP Interest Group as necessary | Scheduled meetings finalised |  | - | - | -
Next scheduled meeting: Feb’15

## Slide 9
Progress for the Month
No | Highlights (Achievements, Industry Interactions)
1 | None to report on
Leading the change to zero harm
Dust Indaba: 06-11-14
Monthly MOSH meeting: 20-11-14.
MOSHIAT-D Coal: 28-11-14
Direct inquiry Mohab/Khutsong: 05-12-14 &
09-12-14
Peer review panel visit to Kopanang: 10-12-14

## Slide 10
Progress for the Month
No | Lowlights (Issues, Risks, Concerns) | Response - Remedial Action | Due Date | Resp. Person
1 | Peer review process at Kopanang could not be concluded | Re-schedule underground component of visit | 28-01-14 | HoLH and team
Leading the change to zero harm
This is a must have – the next available date will only be in April (we will fail industry in terms of the planned roll-out of this practice if we cannot make it on 28-01-14).

## Slide 11
Key lessons learnt
Leading the change to zero harm
No | Key lessons learnt
1 | None to report on

## Slide 12
Leading the change to zero harm
SLP Progress Report
Winch Covers
56.7
Previous month

## Slide 13
Leading the change to zero harm
SLP Adoption Tracker
Winch Covers

## Slide 14
Leading the change to zero harm
SLP Progress Report
Multi-stage Filtration System
86.6
Previous month

## Slide 15
Leading the change to zero harm
SLP Adoption Tracker
Multi-stage Filtration
System

## Slide 16
Leading the change to zero harm

## Slide 17
L E A R N I N G H U B
L E A R N I N G H U B
DUST TEAM
011 498 7100
Dr Audrey Banyini
ABanyini@chamberofmines.org.za
Gerrie Pienaar
gerriepienaar69@gmail.com
Johan van Rensburg
johan.c.vanrensburg@angloamerican.com
Or visit our website: www.mosh.co.za