## Slide 1: MOSH Falls of Ground Team Leading Practice Adoption Team Activity Report
19 March 2015

## Slide 2
Contents
Mission and Values reminder
Progress January February 2015
Leading Practice Adoption
Activities
Challenges
Positives

## Slide 3
Leading the change to zero harm
Mission and Values - MOSH
To facilitate the adoption of leading practice through a people oriented process to significantly improve occupational health and safety in the minerals industry
Our ultimate goal is the provision of working conditions that are free from harmful effects
Values

## Slide 4: Leading Practice Adoption
Leading the change to zero harm
Leading Practice | Mines | % Adoption | No of Crews Trained | No of Persons Influenced
Entry Examination and Making Safe | Central 74 E/Limb 16 N/Cape 6 | 98% 95% 72% | 6990 694 160 | 71000 13880 3200
Bolts with Nets | Central 49 | 97% | 2531 | 30000
TARP (FoG) | Central 41 E/Limb 16 N/Cape 6 | 71% 66% 72% | 1444 395 280 | 27000 7900 560
Value Added Drilling and Blasting (Investigation Phase) | Position Paper drawn up and send to industry members for further inputs |  |  | 
“Ledging” (Investigation Phase) | Sub- committee meeting on the 15 Aprill 2015 at Libanon Business park |  |  | 

## Slide 5
No` | Activities
1 | Tripartite forums visited and positively participated . ( North West, Rustenburg, and Merafong). Andre participated Limpopo OH&H Working Group.
2 | MOSH FOG Industry Adoption Team was held on the 26 February 2015– good participation but worrying attendance. Next meeting 26 March Working on Expert Model and Influence Diagramme for FoG
3 | Special assistance to Harmony Mines (Coordinating TARP Adoption), Unisel, Kopanang(SPECIAL ATTENTION BY DUNCAN), IFM, Smokey Hills, Barberton Mine etc..
4 | Three COPA Meetings held during this time, Central COPA, Eastern Limb COPA and Northern Cape COPA
5 | Paper on Value Added Drilling and Blasting processes is being circulated to industry members for final comments
6 | Conducted interviews on “Ledging” Sibanye Gold – Prof. Malan and Duncan Scott Harmony Gold – Beyers Nel and James Mufara and other senior Managers Anglo-American Platinum – Piet Becker and Dishaba Mine Management Team
Progress for the Month of February / March 2015
Leading the change to zero harm

## Slide 6
No` | Activities
1 | 25March- Eastern Limb Copa, Modikwa mine 26 March- Industry team meeting. Venetia mine, help with EEMS and TARP
2 | 02 APRIL-Free State Tripartite 09 APRIL – Critical Control Workshop 14 April- RETC Meeting
3 | 15 April- Ledging sub committee meeting 16 April- Visit to International Ferro Metal, Lesedi Mine to assist with all 3 LPs
4 | 21 April- Sponsor meeting 24 April- Central COPA
Plan for the Month of March / April 2015
Leading the change to zero harm