## Slide 1
CHAMBER OF MINES OF SOUTH AFRICA
Putting South Africa First
MOSH Noise Adoption Team
21st May 2015

## Slide 2
Contents
Leading the change to zero harm
Key activities/highlights of the month
Past & Future activities
Lowlights
Key learnings
Questions

## Slide 3
1. Key Team activities for the Months (16 Apr’ 15 – 21 May’ 15)
Leading the change to zero harm
 | Highlights (Achievements, Industry Interactions)
1. | HPD_TAS Adoption Impala Platinum Marula Platinum – PoE assessment facilitated Impala PoE verification done. Corrections to be made (June 2015) PPC Mooiplaas (Late comer) Busy capturing completed (29) HPD_TAS Interview analysis. BHP Becsa Middelburg Colliery (Late comer) Placed on hold - Restructuring Exxaro Interviews completed and captured (71) – Matla 1, 2, 3, Plant, Central and mixed areas

## Slide 4
Leading the change to zero harm
 | Highlights (Achievements, Industry Interactions)
 | HPD_TAS Adoption- continued Glencore Coal (Late comer) Impunzi Mine - HPD_TAS induction done. Enablers would rather implement. GAP analysis to follow. Sasol Initial Intervention meetings held . Last meeting (18 June 2015). Aquarius Platinum (Late comer). Introduction completed. Adoption looks promising.
1. Key Team activities for the Months (16 Apr’ 15 – 21 May’ 15)

## Slide 5
Leading the change to zero harm
 | Highlights (Achievements, Industry Interactions)
 | HPD_TAS Adoption- continued ARM TRP Brochure and comic booklet prepared for MVS conference and Mines Safe 2015 Modikwa – HPD TAS Case study – Not confirmed by custodian PoE verification to be done - Not confirmed by custodian Black Rock Operations Introductory meeting date set for 28 May.
1. Key Team activities for the Months (16 Apr’ 15 – 21 May’ 15)

## Slide 6
Leading the change to zero harm
 | Highlights (Achievements, Industry Interactions)
2. | IBMQI - presented at: CM&EE Council CEO Elimination of Fatalities Team MVS Workshop
1. Key Team activities for the Months (16 Apr’ 15 – 21 May’ 15)

## Slide 7
Leading the change to zero harm
 | Activities
3. | Meetings & interactions 17 April 2015 - Task Force meeting & 17 April 2015 - GEE meeting 20 April 2015 - Sasol PoE meeting 20 April 2015 - Dust Leading Practice Launch 22 April 2015 - Lonmin GEE – NRR Calculations and Derating Methodology 24 April 2015 - PPC Interview interaction/meeting 29 April 2015 - Marula Platinum PoE intervention/verification 29 April 2015 - LH Safety Department meeting (Silo’s) 05 May 2015 - Aquarius Introductory meeting 06 May 2015 - Limpopo Hygiene and Task Group meeting 07 May 2015 - Free State Tri-partite meeting 07 May 2015 - Rustenburg Tri-partite 07 May 2015 – Glencore Impunzi Coal HPD_TAS Induction Meeting 13 May 2015 - Noise Team meeting 15 May 2015 - GEE meeting 15 May 2015 - CEO Elimination of Fatalities Team 15 May 2015 - Limpopo Hygiene and Task Group meeting 20 -22 May 2015 - MVS 21 May 2015 - Mosh meeting
Past and future activities

## Slide 8
Leading the change to zero harm
No | Activities | Lowlights (Issues, Risks, Concerns) | Response - Remedial Action
1. | Travelling | Rioting taking place towards Limpopo | Be prepared
2. |  |  | 
3. |  |  | 
4. |  |  | 
5. |  |  | 
6. |  |  | 
7. |  |  | 
8. |  |  | 
3. Low lights for the Months (16 Apr’ 15 – 21 May’ 15)

## Slide 9
4. Key Learnings - (16 Apr’ 15 – 21 May’ 15)
Leading the change to zero harm
No | Activities | Lowlights (Issues, Risks, Concerns) | Response - Remedial Action
1. |  |  | 
2. |  |  | 
3. |  |  | 
4. |  |  | 
5. |  |  | 
6. |  |  | 
7. |  |  | 
8. |  |  | 

## Slide 10
Leading the change to zero harm
Thank you
&
Questions
5. Questions