## Slide 1
CHAMBER OF MINES OF SOUTH AFRICA
Putting South Africa First
MOSH Noise Adoption Team
13th August 2015

## Slide 2
Contents
Leading the change to zero harm
Key activities/highlights of the month
Past & Future activities
Lowlights
Key learnings
Questions

## Slide 3
1. Key Team activities for the period (17 Jul – 13 August)
Leading the change to zero harm
 | Highlights (Achievements, Industry Interactions)
1. | HPD_TAS Adoption Impala Platinum POE verification conducted – 85% - final confirmation awaited on internal sign off PPC (Opencast/Aggregates) Mooiplaas Customizing LB and BC Plans Sasol Adoption process escalated to Unit Managers by Sponsor Exxaro Matla 1 Customization LB and BC plans Continue assisting Late Comers COPA meeting called for end September Special focus on “problem operations” not being able to show progress.

## Slide 4
1. Key Team activities - continued
Leading the change to zero harm
 | Highlights (Achievements, Industry Interactions)
2. | IBMQI Noise Inventory For Equipment And Processes Request 12 Mining Houses(Operations) have responded: Anglo Americam (Coal) Anglo American (Platinum) AnglogoldAshanti ARM Constantia Genet Mining Glencore Impala Koornfontein Lonmin Shanduka South 32 106 Operations 1213 Entries GEE discussion tomorrow

## Slide 5
Leading the change to zero harm
 | Activities
3. | Meetings & interactions Impala POE verification Bokoni Platinum Limpopo Noise Sub-Task Group Hygiene Task Group Fatigue Meeting Petra Diamonds Northam Noise Team Handover with J de Beer FSS Tripartite AGA – POE verification & MOSH Indaba Noise Team meeting – Prep work on IBMQI for GEEs FSS Occ Hygiene Sub-Committee Learning Hub meeting GEE Meeting COPA meeting
2. Past and Future Activities

## Slide 6
Leading the change to zero harm
No | Activities | Lowlights (Issues, Risks, Concerns) | Response - Remedial Action
1. | Noise Team Adoption Manager – J de Beer | Secondment period expired end July | Sourcing replacement
2. |  |  | 
3. |  |  | 
4. |  |  | 
5. |  |  | 
6. |  |  | 
7. |  |  | 
3. Low lights for the Period

## Slide 7
4. Key Learnings for Period.
Leading the change to zero harm
No | Activities | Lowlights (Issues, Risks, Concerns) | Response - Remedial Action
1. |  |  | 
2. |  |  | 
3. |  |  | 
4. |  |  | 
5. |  |  | 
6. |  |  | 
7. |  |  | 
8. |  |  | 

## Slide 8
Leading the change to zero harm
Thank you
&
Questions
5. Questions