## Slide 1: DUST TEAM u p - d a t e 21 August 2015
by
Gerrie Pienaar, Johan van Rensburg and Dr Audrey Banyini
CHAMBER OF MINES OF SOUTH AFRICA
Putting South Africa First

## Slide 2
Contents
Mission and values reminder
Progress update – key indicators
Highlights
Lowlights
Key lessons learnt
Progress up-date
Leading the change to zero harm

## Slide 3
Mission and Values – MOSH
To facilitate the adoption of leading practice through a people oriented process to significantly improve occupational health and safety in the minerals industry
Our ultimate goal is the provision of working conditions that are free from harmful effects
Values
Leading the change to zero harm

## Slide 4
Mission and Values – MOSH Dust
To facilitate the adoption of leading and/or simple leading practices through a people oriented process to significantly improve occupational health in the minerals industry with specific focus on THE ELIMINATION OF SILICOSIS AND DUST RELATED DISEASES
Values
Leading the change to zero harm

## Slide 5
Leading Practice - key indicators
Leading the change to zero harm
KPA No | Key Performance Area | KPI No | KPI | Continuous real-time monitoring of airborne pollutant engineering controls
A1 | Appropriate persons to select leading practice | T4 | Approved participants list | 100% (100%)
A2 | Appropriate plans for planning workshop | T8 | HOH review and approval | 100% (100%)
A3 | Detailed expert model of risk story | T12 | Detailed expert models | 100% (100%)
 |  | T14 | Peer Group assessment | 0% (0%)
A4 | Leading practice with greatest OHS impact | T19 | Credibility of selected Leading Practice | 100% (100%)
A5 | Adoption mines and key people | T22 | Prioritised list of mines and key people | 100% (100%)
A6 | Direct enquiry protocol | T27 | Direct enquiry protocol | 100% (100%)
A7 | Effective direct enquiry process | T30 | Interview process | Moab Khutsong: Completed Beatrix: Completed Phakisa: Completed Mamatwan: Completed Impala Platinum: Completed
A8 | Detailed mental models report | T33 | Mental models report | 100% (100%)
 |  | T34 | Identification of implications | 100% (100%)

## Slide 6
Leading Practice - key indicators
Leading the change to zero harm
KPA No | Key Performance Area | KPI No | KPI | Continuous real-time monitoring of airborne pollutant engineering controls
A9 | BC Plan for deciders | T35 | BC plan for deciders | 100% (100%)
A10 | Generic BC plan for adoption mines | T38 | BC plan for adoption mines | 100% (100%)
A11 | Generic LB plan for adoption mines | T41 | LB plan for adoption mines | 100% (100%)
A12 | Peer reviewed value case report | T47 | Final peer reviewed report | 100% (100%)
A13 | Implemented BC plan for deciders | T50 | Implementation of Decider BC plan | 100% (100%)
A14 | Source mine report | T55 | Final source mine report | 100% (100%)
A15 | Source investigations summary report | T57 | Summary of behavioural work | 100% (100%)
 |  | T58 | Source investigations summary report | 100% (100%)
 |  | T59 | Peer Group assessment | 100% (100%)
A16 | Draft leading practice adoption guide | T61 | Draft LPAG for use at mines | 100% (100%)
 |  | T62 | Peer Group assessment | Awaiting comments

## Slide 7
Leading Practice - key indicators
Leading the change to zero harm
KPA No | Key Performance Area | KPI No | KPI | Continuous real-time monitoring of airborne pollutant engineering controls
A17 | Leading practice industry workshop | T65 | Workshop programme | Completed and distributed
 |  | T66 | Effective key presentations | 28-04-2015
A18 | Establishment of effective COPA | T68 | Updated LPAG | Work in progress – planned for end of August 2015
 |  | T72 | COPA membership | Inappropriate membership – circular submitted to GEE for discussion on 14-08-15
 |  | T73 | COPA attendance | Documented: 30-07-15
 |  | T75 | COPA effectiveness | L Masilo to present
A19 | Working relationship with first adoption mine | T78 | Agreement with Mine Manager | Completed on 30-07-15
A20 | Report on adoption at first adoption mine | T79 | Agreed adoption plan | Scheduled for 15-09-15
 |  | T81 | Direct enquiry process | -
 |  | T82 | Customised BC & LB plans | -
 |  | T84 | Monitoring and evaluation plan | -

## Slide 8
Leading Practice - key indicators
Leading the change to zero harm
KPA No | Key Performance Area | KPI No | KPI | Continuous real-time monitoring of airborne pollutant engineering controls
 |  | T85 | Effectiveness of BC & LB plans | -
 |  | T88 | Documented findings | -
 |  | T90 | Signed off report on first adoption | -
 |  | T91 | Peer Group assessment | -
A21 | Final leading practice adoption guide | T93 | Final Leading Practice Adoption Guide | -
 |  | T94 | Peer Group assessment | -

## Slide 9
SLP - Key Indicators
KPA No | KPA | KPI No | KPI | Multi-stage Filtration Systems | Winch Covers
IDENTIFY |  |  |  |  | 
A 23 | SLP adoption | T112 | Identified potential SLP adoption mines | Yes | Yes
 |  | T113 | Full Adoption Team assessment of SLP | Yes | Yes
 |  | T114 | Contact manager of source mine to arrange access | Yes | Yes
 |  | T115 | Identify key contact person at source mine | Yes | Yes
DOCUMENT |  |  |  |  | 
 |  | T116 | Conduct investigations at source mine | 100% (100%) | 100% (100%)
 |  | T117 | Prepare documents for formal SLP assessment | 100% (100%) | 100% (100%)
 |  | T118 | Confirm accuracy of prepared documents with source mine | 100% (100%) | 100% (100%)
 |  | T119 | Final review of documents against SLP criteria by adoption team | 100% (100%) | 100% (100%)
 |  | T120 | Submit motivation of SLP to Head of Hub | 100% (100%) | 100% (100%)
This will no longer be reported on as the Interest Group will be terminated.

## Slide 10
SLP - Key Indicators
KPA No | KPA | KPI No | KPI | Multi-stage Filtration Systems | Winch Covers
DOCUMENT (cont.) |  |  |  |  | 
 |  | T121 | Convene SLP review panel | 100% (100%) | 100% (100%)
 |  | T122 | Formal review of SLP by review panel | 100% (100%) | 100% (100%)
 |  | T123 | Conduct any necessary follow-up investigations | Not required | 100% (100%)
 |  | T124 | Prepare customised SLP behaviour plans | 100% (100%) | 100% (100%)
 |  | T125 | Develop guidance notes for SLP adoption | 100% (100%) | 100% (100%)
 |  | T126 | Prepare SLP Adoption Brief | 100% (100%) | 100% (100%)
 |  | T127 | Critical review of SLP Adoption Brief | 100% (100%) | 100% (100%)
Leading the change to zero harm

## Slide 11
SLP - Key Indicators
KPA No | KPA | KPI No | KPI | Multi-stage Filtration Systems | Winch Covers
FACILITATE |  |  |  |  | 
 |  | T128 | Update list of potential adoption mines | 100% (100%) | 100% (100%)
 |  | T129 | Identify key contact persons at potential adoption mines | 100% (100%) | 100% (100%)
 |  | T130 | Arrange SLP Briefing Workshop | 100% (100%) | 100% (100%)
 |  | T131 | Circulate SLP Adoption Brief to potential adoption mines | 100% (100%) | 100% (100%)
 |  | T132 | Conduct SLP Briefing Workshop | 100% (100%) | 100% (100%)
 |  | T133 | Establish SLP interest group if required | 100% (100%) | 100% (100%)
 |  | T134 | Initiate process of mines reporting on adoption | 100% (100%) | 100% (100%)
 |  | T135 | Provide SLP adoption brief for use at other meetings | 100% (100%) | 100% (100%)
 |  | T136 | Monthly follow-up communication with potential adoption mines | Scheduled meetings finalised | 
 |  | T137 | Arrange meetings / terminate SLP Interest Group as necessary | Scheduled meetings finalised | 
Leading the change to zero harm
The Interest Group will be terminated as 100% compliance on the adoption process for SLP’s have been reached.

## Slide 12
Progress for the Month
No | Highlights (Achievements, Industry Interactions)
1 | LPAG work in progress – version 1 meeting: 07-07-15
2 | GEE meeting: 10-07-15
3 | Lead adoption mine meeting : 13/20-07-15 and 11-08-15 (Agreement by GM on collaborative arrangements (official letter by HoLH submitted and returned with GM approval)
4 | Monthly MOSH meeting: 16-07-15
5 | Sponsor meeting: 23-07-14
6 | Health and GEE meeting: 24-07-15
7 | Limpopo Occ. Health Forum: 28-07-15
8 | COPA: 30-07-15 (Lead Adoption Mine progress on adoption process)
9 | South KZN RTF “Real-time Monitoring System Presentation”: 13-08-15
Leading the change to zero harm

## Slide 13
Progress for the Month
No | Lowlights (Issues, Risks, Concerns) | Response - Remedial Action | Due Date | Resp. Person
1 | Membership at COPA | Submit circular to GEE’s requesting to nominate appropriate members and alternates | 14-08-15 | GP GEE’s
Leading the change to zero harm

## Slide 14
Continuous Real Time
Leading the change to zero harm
3 Gold Mine Support with mine updates
2. N Cape
3. Coal

## Slide 15
Scheduled for
15-09-15
Leading the change to zero harm
Lead Adoption Mine Progress Report
Continuous real-time monitoring of airborne pollutant engineering controls
Step1
Step2
Step3
Step4
Step5
Facilitate the adoption decision
Secure support for adoption
Establish an effective mine adoption team
Prepare initial plan for adoption
Initiate baseline monitoring programme
Step8
Step7
Step6
Plan and conduct direct enquiries
Update key stakeholders on progress
Establish effective relationship with the COPA

## Slide 16
Leading the change to zero harm
SLP Progress Report
Winch Covers
Previous 71.1

## Slide 17
Leading the change to zero harm
SLP Adoption Tracker
Winch Covers

## Slide 18
Leading the change to zero harm
SLP Progress Report
Multi-stage Filtration System
Previous 88.4

## Slide 19
Leading the change to zero harm
SLP Adoption Tracker
Multi-stage Filtration System

## Slide 20
Important MOSH Dust Date
Leading the change to zero harm
Biannual MOSH Dust Indaba 24 Nov 2015

## Slide 21
For more information
contact the Chamber of Mines
LEARNING HUB
Dust Team
at
011 498 7100
Johan van Rensburg
johan.c.vanrensburg@angloamerican.com
Gerrie Pienaar
gerriepienaar69@gmail.com
Dr Audrey Banyini
ABanyini@chamberofmines.org.za
Principal
Specialist
ATM
ATM
Or visit our website:
www.mosh.co.za
L E A R N I N G H U B
DUST TEAM