## Slide 1: DUST TEAM u p - d a t e March 2013 to date
CHAMBER OF MINES OF SOUTH AFRICA
Putting South Africa First
by
Gerrie Pienaar and Dr Audrey Banyini
16 April 2013

## Slide 2
Contents
Mission and values reminder
Progress update – key indicators
Highlights
Lowlights
Key lessons learnt
Annual plan - 2013
Leading the change to zero harm

## Slide 3
Mission and Values – MOSH
To facilitate the adoption of leading practice through a people oriented process to significantly improve occupational health and safety in the minerals industry
Our ultimate goal is the provision of working conditions that are free from harmful effects
Values
Leading the change to zero harm

## Slide 4
Mission and Values – MOSH Dust
To facilitate the adoption of leading practices through a people oriented process to significantly improve occupational health and safety in the minerals industry with specific focus on THE ELIMINATION OF SILICOSIS AND DUST RELATED DISEASES
Values
Leading the change to zero harm

## Slide 5
Progress update - key indicators from Team Scorecard
Covering identification, documenting, facilitating and impacts for the practices in question
KPA No | Key Performance Area | KPI No | KPI | Measure 1 (Definition) | Measure 2 (Definition) | Measure 1 | Measure 2 | Originally planned completion
A1 | Appropriate participants in selection of leading practice | T1 | Credible team membership | Yes | 18-07-12 | 100 | Ongoing on quarterly basis | 18-07-12 17-10-12 17-01-13 14-02-13
 |  | T2 | Ensure discipline input | Yes | 18-07-12 | 100 | 18-07-12 | 18-07-12
 |  | T3 | Ensure group input | Yes | 18-07-12 | 100 | 17-10-12 | 17-10-12
 |  | T4 | Approved participants list | Yes | Jul 2012 | 100 | Jul 2012 | Jul 2012
 |  | T5 | Peer Group assessment | Yes | May 2012 | 100 | May 2012 | May 2012
A2 | Appropriate plans for planning workshop | T6 | Competent Facilitator | Yes | 13-09-12 | 100 | 25-09-12 | 25-09-12
 |  | T7 | Planning agenda | Yes | 13-09-12 | 100 | 25-09-12 | 25-09-12
A3 | Detailed expert model of risk story | T9 | Stakeholder consultation | Yes | July 2012 and October 2012 | 100 | July 2012 and October 2012 | 17-10-12
 |  | T10 | Prepared questions for input | Yes | July 2012 and October 2012 | 100 | July 2012 and October 2012 | 17-10-12
Leading the change to zero harm

## Slide 6
Progress update - key indicators cont.
KPA No | Key Performance Area | KPI No | KPI | Measure 1 (Definition) | Measure 2 (Definition) | Measure 1 | Measure 2 | Originally planned completion
 |  | T11 | Consultation draft expert model | Yes | July 2012 | 100 | July 2012 | 17-10-12
 |  | T12 | Detailed expert models | Yes | August 2012 | 100 | 17-10-12 | 17-10-12
 |  | T13 | Major risks and improvement possibilities | Yes | August 2012 | 100 | July 2012 | Aug 2012
 |  | T14 | Peer Group assessment | No | Oct 2012 | 100 | 17-10-12 | 17-10-12
Leading the change to zero harm

## Slide 7
Progress update - key indicators cont.
KPA No | Key Performance Area | KPI No | KPI | Measure 1 (Definition) | Measure 2 (Definition) | Measure 1 | Measure 2 | Originally planned completion
A4 | Leading practice with greatest potential OHS impact | T15 | Review of R&D outcomes | Yes | 2008 | 100 | Ongoing on quarterly basis | 2008
 |  | T16 | Industry identified practices | Yes | Feb’12 (5) 2008 | 100 | Ongoing on quarterly basis | Feb’12
 |  | T17 | Exploratory visits to mines | Yes | May’12 | 100 | Ongoing on quarterly basis | May’12
 |  | T18 | Detailed Leading Practice List | Yes (T16 vs T18)? | 2008 and 2012 | 100 | Ongoing on quarterly basis | Up-dated quarterly
 |  | T19 | Credibility of selected Leading Practice | Yes | Jun’12 | 100 | ? | ?
 |  | T20 | Workshop quality | Cannot assess the quality |  |  |  | 
Leading the change to zero harm

## Slide 8
SLP - Key Indicators
KPA No | Key Performance Area | KPI No | KPI | QAFS | Multi-stage Filtration Systems | Winch Covers | Develop. Water Blast | Future SLP’s
IDENTIFY |  |  |  |  |  |  |  | 
A23 | SLP adoption | T112 | Identified potential SLP adoption mines | Yes | Yes | Yes | Yes | -
 |  | T113 | Full Adoption Team assessment of SLP | Yes | Yes | Yes | Yes | -
 |  | T114 | Contact manager of source mine to arrange access | Yes | Yes | Yes | Yes | -
 |  | T115 | Identify key contact person at source mine | Yes | Yes | Yes | Yes | -
DOCUMENT |  |  |  |  |  |  |  | 
 |  | T116 | Conduct investigations at source mine | 100% (100%) | 100% (100%) | 100% (100%) | 20% (20%) | -
 |  | T117 | Prepare documents for formal SLP assessment | 100% (100%) | 100% (100%) | 100% (60%) | 0% (0%) | -
 |  | T118 | Confirm accuracy of prepared documents with source mine | 50% (50%) | 100% (100%) | 100% (60%) | 0% (0%) | -
 |  | T119 | Final review of documents against SLP criteria by adoption team | 30% (30%) | 100% (100%) | 100% (60%) | 0% (0%) | -
 |  | T120 | Submit motivation of SLP to Head of Hub | 0% (0%) | 100% (100%) | 100% (60%) | 0% (0%) | -
Leading the change to zero harm

## Slide 9
SLP - Key Indicators
Leading the change to zero harm
KPA No | Key Performance Area | KPI No | KPI | QAFS | Multi-stage Filtration Systems | Winch Covers | Develop. Water Blast | Future SLP’s
DOCUMENT (cont.) |  |  |  |  |  |  |  | 
 |  | T121 | Convene SLP review panel | - | 25-04-13 | 25-04-13 | - | -
 |  | T122 | Formal review of SLP by review panel | - | 25-04-13 | 25-04-13 | - | -
 |  | T123 | Conduct any necessary follow-up investigations | - | - | - | - | -
 |  | T124 | Prepare customised SLP behaviour plans | - | - | - | - | -
 |  | T125 | Develop guidance notes for SLP adoption | - | - | - | - | -
 |  | T126 | Prepare SLP Adoption Brief | - | - | - | - | -
 |  | T127 | Critical review of SLP Adoption Brief | - | - | - | - | -

## Slide 10
SLP - Key Indicators
Leading the change to zero harm
KPA No | Key Performance Area | KPI No | KPI | QAFS | Multi-stage Filtration Systems | Winch Covers | Develop. Water Blast | Future SLP’s
FACILITATE |  |  |  |  |  |  |  | 
 |  | T128 | Update list of potential adoption mines | - | - | - | - | -
 |  | T129 | Identify key contact persons at potential adoption mines | - | - | - | - | -
 |  | T130 | Arrange SLP Briefing Workshop | - | - | - | - | -
 |  | T131 | Circulate SLP Adoption Brief to potential adoption mines | - | - | - | - | -
 |  | T132 | Conduct SLP Briefing Workshop | - | - | - | - | -
 |  | T133 | Establish SLP interest group if required | - | - | - | - | -
 |  | T134 | Initiate process of mines reporting on adoption | - | - | - | - | -
 |  | T135 | Provide SLP adoption brief for use at other meetings | - | - | - | - | -
 |  | T136 | Monthly follow-up communication with potential adoption mines | - | - | - | - | -
 |  | T137 | Arrange meetings / terminate SLP Interest Group as necessary | - | - | - | - | -

## Slide 11
Progress for the Month
No | Highlights (Achievements, Industry Interactions)
1 | During MOSHIAT-D on 16-01-13 more potential practices were tabled for investigation – review of first one scheduled for 17-04-13. Champions have been identified for the remainder.
2 | Submission of candidate SLP’s on Multi-stage Filtration Systems and Winch Covers to Head of Hub for panel review
3 | Establishment of MOSHIAT-D Collieries: 8 Potential practices tabled during workshop of which 4 have been identified with highest potential – the first one to be reviewed on 19-04-13
4 | Training on direct enquiry process for Harmony Free State region
Leading the change to zero harm

## Slide 12
Verbal feedback for March’13 to date
Leading the change to zero harm
Report on two candidate SLP’s
  Multi-Stage Filtration Systems – tech underground review concluded
  Winch Covers – tech underground review scheduled for 23 April’13
  Both will be formally reviewed on 25 April’13 by the peer review committee
QAFS – underground visit today to review progress – development waterblast will also be discussed
MOSHIAT-D tomorrow – first of “8 identified new practices” to be reviewed nl. Dust Mask Testing
MOSHIAT-D Collieries on Friday – first practice review - Transfer Points Spray Configuration (UG/SUR) at SASOL
Direct enquiry training for Harmony Free State Region completed – similar session is scheduled for Harmony Western Region and a follow-up on Free State Region – awaiting dates from Harmony

## Slide 13
Progress for the Month
No | Lowlights (Issues, Risks, Concerns) | Response - Remedial Action | Due Date | Resp. Person
There were no lowlights to be reported on for the reporting period |  |  |  | 
Leading the change to zero harm

## Slide 14
Key lessons learnt
No | Key lessons learnt
1 | Implementation v/s adoption
2 | How to get practices already implemented MOSH compliant – DC’s 12 point plan
Leading the change to zero harm