## Slide 1: MOSH Falls of Ground Leading Practice Adoption Team Activity Report
JANUARY 2013

## Slide 2
Contents
Mission and Values reminder
Progress update – key indicators
Highlights
Challenges
Key lessons learnt

## Slide 3
Leading the change to zero harm
Mission and Values - MOSH
To facilitate the adoption of leading practice through a people oriented process to significantly improve occupational health and safety in the minerals industry
Our ultimate goal is the provision of working conditions that are free from harmful effects
Values

## Slide 4
FOG Adoption Team Planner
Jan-12 | Feb-12 | Mar-12 | Apr-12 | May-12 | Jun-12 | Jul-12 | Aug-12 | Sep-12 | Oct-12 | Nov-12 | Dec-12 | Jan-13 | Feb-13 | Mar-13 | Apr-13 | May-13 | Jun-13
N&B DEMO
N&B COPA
EE&MS
TARP DEMO
TARP COPA
NLP Plan
Revisiting adoption at mines and tightening the loose ends
8th COPA Meeting was held on the
24 Jan 2013 at Randfontein Golf Club.
24 Mines are participating. 64 % Complete.
20 mines registered.
Gold and Platinum COPA on the
22 March. 2013
Eastern Districts COPA on
27 February 2013
Pre-identification Planning Meeting – held at Glenburn Lodge 30 August 2012.
No new LP this year,2013 is the year of Consolidation
Planning workshop to be held August 2013
Prevention of All Uncontrolled Falls of Ground

## Slide 5
Progress for the Month of January 2013
No` | Highlights (Achievements, Industry Interactions)
1 | Team had a strategic meeting on the 4th of January and the following was agreed on: Team members agreed on the need to have individual KPAs COPAs to be decentralized Tripartite meetings to be used as one of the reporting structures
2 | 24 January we had a Nets with Bolts COPA. Well attended(70 people)
3 | 31 January we had our first Industry member Adoption Team meeting for the year. (Bi-monthly for 2013 forward)
4 | Attended TPF Meetings for Northern Cape, Free Stated, and Northwest
5 | Ad Hoc meetings held with TauTona GM, Impala Executive Management and Directors , Rasimone GM, Head of ARM Platinum
6 | Launched inaugural meeting with new FOG Team Sponsor – Mr Peter Turner (Sibanye Gold)
Leading the change to zero harm

## Slide 6
Progress for the Month of January 2013
No | Lowlights (Issues, Risks, Concerns) | Response - Remedial Action | Due Date | Resp. Person
1 | 18 Jan the team visited BRPM mine to help bring them on board, meeting not successful. Poor or no representation form either Line Management or Unions | A van Zyl and D Cronje met with General Manager to get process back on line | 15/2 | A VZ
2 | Inappropriate attendance of Industry team members at meetings | Lobby MOSH Task Force and Senior Management of Mining Companies for appropriate representation | Feb 13 Mar 13 | AvZ DA
3 | MOSH FOG Sponsor Meeting for 5 February 2013 cancelled | A van Zyl to renegotiate date for next meeting | Mar 13 | AvZ
Leading the change to zero harm

## Slide 7
MOSH TASK FORCE
Know your representatives on various MOSH Forums
Progress update – key indicators
Setting up COAL based FOG Industry Adoption Team

## Slide 8
MOSH FOG Adoption Team Meetings

## Slide 9
KPA No | KPA | KPI No. | KPI | Definition of measurement (See Team datasheet for fuller descriptions) Measure 1 ¦ Measure 2 | Timing for report | Target | LP 1: Nets with Bolts |  |  | 
 |  |  |  |  |  |  | Measure 1 Prev Curr |  | Measure 2 Prev Curr | Planned completion
 | Leading Practice Adoption Process |  |  |  |  |  |  |  |  | 
 | Identification of Leading Practice |  |  |  |  |  |  |  |  | 
A1 | Appropriate persons to select leading practice | T4 | Approved participants list | Head of Hub approved list of workshop participants Yes or No ¦ Date approved | Monthly | Yes | 0 | 0 | 0-Jan | N/A
A2 | Appropriate plans for planning workshop | T8 | HOH review and approval | Review and approval against checklist at least two weeks before workshop Yes or No ¦ Date of approval | Monthly | Yes | 1 | 1 | 1-Nov | June 2010
A3 | Detailed expert model of risk story | T12 | Detailed expert models | Detailed drafts of the two expert models ready for workshop Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jul | July 2012
 |  | T14 | Peer Group assessment | Peer group review of expert model quality Assessment score % ¦ Date completed | Monthly | >90% | 1 | 1 | 1-Feb | July 2012
A4 | Leading practice with greatest OHS impact | T19 | Credibility of selected Leading Practice | Peer group review of practice against key criteria Assessment score in % ¦ Date assessed | Monthly | >90% | 1 | 1 | 1-Jul | July 2012

## Slide 10
Documenting the Leading Practice |  |  |  |  |  |  |  |  | 
Adoption mines and key people | T22 | Prioritised list of mines and key people | Consolidated prioritised list of adopter mines and key persons at mines, with contact details Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | Oct 2013
Direct enquiry protocol | T27 | Direct enquiry protocol | Custom designed enquiry protocol signed off by Behaviour Specialist for the leading practice Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012
Effective direct enquiry process | T30 | Interview process | All planned interviews conducted by trained interviewers Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012
Detailed mental models report | T33 | Mental models report | Detailed mental models report signed off by Behaviour Specialist Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012
 | T34 | Identification of implications | Documented implications of the identified mental models as input for BC and LB plans Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012
BC Plan for deciders | T35 | BC plan for deciders | Detailed BC plan for deciders signed off by Behaviour Specialist Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012
Generic BC plan for adoption mines | T38 | BC plan for adoption mines | Detailed BC plan for use at adoption mines signed off by Behaviour Specialist Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012
Generic LB plan for adoption mines | T41 | LB plan for adoption mines | Detailed LB plan for use at adoption mines signed off by Behaviour Specialist Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012

## Slide 11
T47 | Final peer reviewed report | Final updated version of peer reviewed value case report Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012
T50 | Implementation of Decider BC plan | Implementation of BC plan for deciders prior to Leading Practice Adoption Workshop Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012
T55 | Final source mine report | Updated draft of report based on input from consultations at mine and with adoption team Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012
T56 | Peer Group assessment | Hub Peer Group assessment using an agreed score card for assessing source mine reports Assessment score % ¦ Date completed | Monthly | 100% | N/A | N/A | 1-Jan | 
T57 | Summary of behavioural work | A summary report of the work undertaken in developing the generic BC and LB plans Estimate % complete ¦ date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012
T58 | Source investigations summary report | A report that pulls together the separate investigation reports which are appended Estimate % complete ¦ date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012
T59 | Peer Group assessment | Hub Peer Group assessment using score card for source investigations summary reports Assessment score % ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012
T61 | Draft LPAG for use at mines | Updated draft guide for use at adoption mines based on input from source mine and team Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012
T62 | Peer Group assessment | Hub Peer Group assessment of LPAG using agreed score card Assessment score % ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | Nov 2012

## Slide 12
T65 | Workshop programme | Programme for workshop signed off by HoH at least two weeks before workshop Yes or No ¦ Date completed | Monthly | Yes | 0 | 0 | 0-Jan | 
T66 | Effective key presentations | A special workshop assessment form completed by all workshop participants Assessment score % ¦ Date completed | Monthly | >80% | 1 | 1 | 1-Jul | 
T68 | Updated LPAG | Updated version of LPAG, based on experience gained at first adoption (demo) mine Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jul | Sept 2012
T72 | COPA membership | Must include one of originally identified key persons at adoption mines & Adoption Team Manager % of mines with required membership ¦ No. of mines | Monthly | > 80% | 0.8 | 0 | 0-Jan | Oct 2013
T73 | COPA attendance | COPA attendance by identified key (required) members % attendance by key members ¦ Date of last meeting | Monthly | > 60% | 0.8 | 0 | 0-Jan | Oct 2013
T75 | COPA effectiveness | A COPA effectiveness assessment form completed quarterly by workshop participants Assessment score in % ¦ Date completed | Monthly | > 80% | 0.8 | 0 | 0-Jan | Oct 2013
T78 | Agreement with Mine Manager | Working relationship agreed with Mine Manager Estimate % complete ¦ Date completed | Monthly | 100% by adoption workshop | 0.9 | 0.9 | 1-Jan | Oct 2013
T79 | Agreed adoption plan | Copy of agreed adoption plan with comments on key issues and details of lessons learnt Estimate % complete ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan | 
T81 | Direct enquiry process | Direct enquiry process using selected interviewees and trained interviewers Estimate % complete ¦ Date completed | Monthly | 100% | 0.8 | 0.8 | 1-Jan | Oct 2013

## Slide 13
T82 | Customised BC & LB plans | Customised BC and LB plans involving proper application of customisation process Estimate % complete ¦ Date completed | Monthly | 100% | 0.8 | 0.8 | 1-Jan |  | Oct 2013
T84 | Monitoring and evaluation plan | Impact and performance monitoring and evaluation plan agreed with the mine Estimate % complete ¦ Date completed | Monthly | 100% | 0.2 | 0.2 | 1-Jan |  | Oct 2013
T85 | Effectiveness of BC & LB plans | Assessment of effectiveness using standard behaviour modification survey tool Assessment score in % ¦Date completed | Monthly | 100% | 0.6 | 0.6 | 1-Jan |  | Oct 2013
T88 | Documented findings | All findings (lessons learnt) at first adoption mine documented and on file Estimate % complete ¦ Date completed | Monthly | 100% | 100 | 100 | 1-Jan |  | Oct 2013
T90 | Signed off report on first adoption | Updated report based on input from consultations at mine and with adoption team Estimate % complete ¦ Date completed | Monthly | 100% | 0.2 | 0.2 | 1-Jan |  | Oct 2013
T91 | Peer Group assessment | Hub Peer Group assessment of adoption report using an agreed score card Assessment score % ¦ Date completed | Monthly | 100% | 0 | 0 | 0-Jan |  | Oct 2013
T93 | Final Leading Practice Adoption Guide | Updated final draft of the LPAG based on input from first adoption mine and adoption team Assessment score % ¦ Date completed | Monthly | 100% | 1 | 1 | 1-Jan |  | Oct 2013
T94 | Peer Group assessment | Hub Peer Group assessment of LPAG using an agreed score card Assessment score % ¦ Date completed | Monthly | 100% | 0 | 0 | 1-Jan |  | ?
T95 | Identified potential adoption mines | Number of identified potential adoption mines No. of mines ¦ Date last mine identified | Monthly | 40 | 24 | 24 | 1-Jan |  | Oct 2013
T96 | LP investigated for adoption | No of completed adoption investigation forms returned by mines to adoption team manager Number of mines ¦ % of potential adoption mines | Monthly | 100% | 24 | 0 | 0 | 0 | Oct 2013

## Slide 14
T97 | Positive decision to adopt | Number of mines indicating a positive decision to adopt on their completed forms Number of mines ¦ % of potential adoption mines | Monthly | >95% | 24 | 0 | 0 | 0 | Oct 2013
T98 | Mine adoption team appointed | Number of mines that have appointed an adoption team and a manager Number of mines ¦ % of potential adoption mines | Monthly | >95% | 24 | 0 | 0 | 0 | Oct 2013
T99 | Investment in adoption | Total of planned investment (funds & person days) by mines in adopting the leading practice Cost in Rands ¦ Number of person days | Monthly | None | ? | 0 | 0 | 0 | 
T100 | Implementation plan (incl M&E) | Number of mines that have provided copies of acceptable plans to adopt the leading practice Number of mines ¦ % of potential adoption mines | Monthly | >95% | ? | 0 | 0 | 0 | 
T101 | Accommodation of learning | Number of mines with provisions to accommodate learning during adoption (no bonus loss) Number of mines ¦ % of actual adopter mines | Monthly | 100% | ? | 0 | 0 | 0 | 
T102 | Leading practice harmonised | Number of mines that report successful harmonisation of the leading practice Number of mines ¦ % of potential adoption mines | Monthly | >95% | 20 | 0 | 0 | 0 | Oct 2013
T103 | Mental models interviews | Number of mines that have conducted mental model interviews using trained interviewers Number of mines ¦ % of potential adoption mines | Monthly | >95% | 22 | 0 | 0 | 0 | Oct 2013
T104 | Customised BC plan | Number of mines that have customised BC plan according to LPAG Number of mines ¦ % of potential adoption mines | Monthly | >95% | 22 | 0 | 0 | 0 | Oct 2013
T105 | Customised LB plan | Number of mines that have customised LB plan according to LPAG Number of mines ¦ % of potential adoption mines | Monthly | >95% | ? | 0 | 0 | 0 | Oct 2013
T106 | Risk assessment | Number of mines that have undertaken risk assessment according to LPAG Number of mines ¦ % of potential adoption mines | Monthly | >95% | 0.75 | 0 | 0 | 0 | Oct 2013

## Slide 15
T107 | Training lesson plans | Number of mines that report required development of training lesson plans Number of mines ¦ % of potential adoption mines | Monthly | >95% | 5 | 0 | 0 | 0 | Oct 2013
T108 | Management sign-off | Number of mines that report required management sign-off Number of mines ¦ % of potential adoption mines | Monthly | >95% | 0 | 0 | 0 | 0 | 
T109 | Leading practice piloted | Number of mines that report required initial piloting of the leading practice Number of mines ¦ % of potential adoption mines | Monthly | >95% | 0 | 0 | 0 | 0 | Oct 2013
T110 | Roll-out plan in place | Number of mines that have completed the required mine-wide leading practice roll-out plan Number of mines ¦ % of potential adoption mines | Monthly | >95% | 14 | 0 | 0 | 0 | Oct 2013
T111 | Completed adoptions of leading practice | Number of mines that have provided required documentation confirming full adoption Number of mines ¦ % of potential adoption mines | Monthly | >95% | 0 | 0 | 0 | 0 | Oct 2013
T124 | Reported adoptions of SLP | Number of mines reporting successful adoption of the SLP Number of mines ¦ % of potential adoption mines | Monthly | 50% in 6 mths | 0 | 0 | 0 | 0 | 
T125 | Confirmed full process SLP adoptions | Number of mines reporting adoption of the SLP in accordance with the SLP Adoption Brief Number of mines ¦ % of potential adoption mines | Monthly | >90% | 0 | 0 | 0 | 0 |