## HPDTAS
| 2013-10-16 | MOSH HPD TAS Adoption Monitor Programme
| Mining House | Number | Name of Mine/ Shaft | Company | Name of Manager | Name of Project Leader | E-mail Address of Project Leader | Telephone Number | Do you have a FOG Risk associated with nets with bolts? | Do you have FOG Risk Controls in place | Do you have a Procedure on the application of Bolts with Nets | Is your FOG related LTIFR<0,05 | Have you considered the Adoption of the Leading Practice on Nets with Bolts | Yes, we want to Adopt the Leading Practice on Nets with Bolts | No, we do not want to Adopt the Leading Practice on Nets with Bolts | Setting up Multi disciplinary Adoption Teams | Induction of the Adoption Team (s) | Agree on the Implementation Plan | Identify the interviews & Interviews | Train the Interviewers | Mental Model Interviews | Leadership Behaviour Plan | Behaviour Communication Plan | Risk Assessment | Training Lesson Plans | Management Review Process | Roll-out plan in place | Challenges | Highlights | Number of People to cover | Number of People covered | COPA Participation
1 | ARM | 1 | Black Rock
1 |  | 1 | Modikwa | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  |  | 5896
1 |  | 1 | Nkomati | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS |  | Cooperative and high level involvement | 3128
1 |  | 1 | Two Rivers | Harmony |  | Rusiano Tsoka | rusiano.tsoka@harmony.co.za | 829271018 | y | Y | Y | Y | Y |  |  | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS |  | Cooperative and high level involvement | 3486
|  | 4 | [27 empty] | 12510 | 0
| EXXARRO | 1 | Arnot | Anglo Gold Ashanti | Francois Naude |  | fnaude@anglogoldashanti.com | 713635097 | y | y | y | y | y |  |  | IP | [7 empty] | NS | NS | NS | NS | Raise concerns with group HSEC/GEE |  | 1400
|  | 1 | Grootegeluk | Harmony |  | Marius Van der Merwe | marius.vandermerwe@harmony.co.za | 0723684289/0574524445 | y | y | y | y | y |  |  | IP | [7 empty] | NS | NS | NS | NS | Raise concerns with group HSEC/GEE |  | 2000
|  | 1 | Leeuwpan | [12 empty] | IP | [7 empty] | NS | NS | NS | NS | Raise concerns with group HSEC/GEE |  | 500
|  | 1 | Matla 1 | [24 empty] | Raise concerns with group HSEC/GEE
|  | 1 | Matla 2 | [24 empty] | Raise concerns with group HSEC/GEE
|  | 1 | Matla 3 | [12 empty] | Com | Com | Com | Com | Com | [7 empty] | Raise concerns with group HSEC/GEE |  | 2500
|  | 1 | New Clydesdale | [12 empty] | IP | IP | IP | [9 empty] | Raise concerns with group HSEC/GEE |  | 400
|  | 1 | North Block Complex - Glisa and Strathrae coal mines, Eerstelingsfontein and Belfast coal projects | [24 empty] | Raise concerns with group HSEC/GEE |  | 1621
Raise concerns with group HSEC/GEE
Raise concerns with group HSEC/GEE
Raise concerns with group HSEC/GEE
|  | 1 | Tshekodeni | Harmony | Rudi Phillis | Tienie Landman | Tienie.Landman@Harmony.co.za | 579167111 | y | y | y | y | y |  |  | IP | IP | IP | [9 empty] | Raise concerns with group HSEC/GEE |  | 680
|  | 9 | [27 empty] | 9101 | 0
| IMPALA | 1 | General | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 336
|  | 1 | Laboratories | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 48
|  | 1 | Medical Services | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 108
|  | 1 | Minpro | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 1469
|  | 1 | Opencast | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 207
|  | 1 | Processing | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 641
|  | 1 | Services | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 4955
|  | 1 | Shaft 1 | Xstrata Alloys |  | Phil Garner | pgarner@xstrata.co.za | 829219441 | y | y | y | y | y |  |  | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 4565
|  | 1 | Shaft 11C | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 32
|  | 1 | Shaft 14 | Anglo Gold Ashanti | Randel Rademan |  | crrademann@anglogoldashanti.com | 187005450 | y | y | y | y | y |  |  | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 4803
|  | 1 | Shaft 16 | Harmony |  | Velaphi Waganda | velaphi.waganda@harmony.co.za | 579074114 | y | y | y | y | y |  |  | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 1046
|  | 1 | Shaft 17 | Harmony |  | Warren Freeman | Warren.Freeman@harmony.co.za | 847016876 | y | y | y | y | y |  |  | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 427
|  | 1 | Shaft 2 | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 689
|  | 1 | Shaft 20 | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 2677
|  | 1 | Shaft 4 | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 1755
|  | 1 | Shaft 5 | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 480
|  | 1 | Shaft 6 | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 1195
|  | 1 | Shaft 7A | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 1419
|  | 1 | Shaft EF | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 759
|  | 1 | Shaft10 | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 3181
|  | 1 | Shaft11 | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 6966
|  | 1 | Shaft12 | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 3746
|  | 1 | Shaft7A | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 1244
|  | 1 | Shaft8 | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 980
|  | 1 | Shaft9 | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 2126
|  | 1 | SMLT | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 637
|  | 1 | Tailings | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 237
|  | 1 | Toll | Anglo Gold Ashanti | Andre van Jaarsveld | Danny Davis | ddavies@anglogoldashanti.com | 187008963 | y | y | y | y | y |  |  | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 8
|  | 1 | UG2 | [12 empty] | Com | Com | Com | [5 empty] | NS | NS | NS | NS |  |  | 196
|  | 29 | [27 empty] | 46932
| NORTHAM | 1 | Zondereinde Platinum | Impala | Mathias Sithole |  | Mathias.sithole@implats.co.za | 829431572 | y | y | y | y | y |  |  | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS | Active participation from unions | Good cooperation | 9116
|  | 1 | [27 empty] | 9116 | 0
| GLENCORE XSTRATA - ALLOYS - EASTERN CHROME MINES | 1 | Helena | [12 empty] | Com | Com | Com | Com | Com | IP | IP | IP | NS | NS | NS | NS |  |  | 941
|  | 1 | Magareng | [12 empty] | Com | Com | Com | Com | Com | IP | IP | IP | NS | NS | NS | NS |  |  | 910
|  | 1 | Shared Services | [12 empty] | Com | Com | Com | Com | Com | IP | IP | IP | NS | NS | NS | NS |  |  | 340
|  | 1 | Thorncliffe | [12 empty] | Com | Com | Com | Com | Com | IP | IP | IP | NS | NS | NS | NS |  |  | 946
|  | 1 | UG 2 | [12 empty] | Com | Com | Com | Com | Com | IP | IP | IP | NS | NS | NS | NS |  |  | 17
|  | 5 | [27 empty] | 3154 | 0
| GLENCORE XSTRATA - ALLOYS - WESTERN CHROME MINES | 1 | Horizon | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS |  |  | 563
|  | 1 | Kroondal | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS |  |  | 969
|  | 1 | Rietvlei | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS |  |  | 49
|  | 1 | UG 2 | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS |  |  | 334
|  | 1 | Waterval | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS |  |  | 745
|  | 5 | [27 empty] | 2660 | 0
| GLENCORE XSTRATA - PLATINUM - EASTERN MINES | 1 | Mototolo Borwa | [12 empty] | Com | Com | Com | Com | Com |  |  |  | NS | NS | NS | NS |  |  | 842
|  | 1 | Mototolo Lebowa | [12 empty] | Com | Com | Com | Com | Com |  |  |  | NS | NS | NS | NS |  |  | 1321
|  | 2 | [27 empty] | 2163 | 0
| GLENCORE XSTRATA - PLATINUM - WESTERN MINES | 1 | Eland | [20 empty] | NS | NS | NS | NS
|  | 1 | [27 empty] | 0 | 0
| SASOL | 1 | Bosjiespruit | [12 empty] | Com | Com | Com | Com | Com | Com | IP | IP
|  | 1 | Brandvlei | [12 empty] | Com | Com | Com | Com | Com | Com | IP | IP
|  | 1 | Middelbult | [12 empty] | Com | Com | Com | Com | Com | Com | IP | IP
|  | 1 | Secunda | [12 empty] | Com | Com | Com | Com | Com | Com | IP | IP
|  | 1 | Sigma | [12 empty] | Com | Com | Com | Com | Com | Com | IP | IP
|  | 1 | Syferfontein | [12 empty] | Com | Com | Com | Com | Com | Com | IP | IP
|  | 1 | Twistdraai | [12 empty] | Com | Com | Com | Com | Com | Com | IP | IP
|  | 7 | [27 empty] | 0 | 0
| HARMONY | 1 | Bambanani | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Forms part of management KPI's
|  | 1 | Bambanani Steyn 2 | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Forms part of management KPI's
|  | 1 | Doornkop | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Forms part of management KPI's
|  | 1 | Joel | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Forms part of management KPI's
|  | 1 | Kusasalethu | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Forms part of management KPI's
|  | 1 | Masimong | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Forms part of management KPI's
|  | 1 | Phakisa | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Forms part of management KPI's
|  | 1 | Target 1 | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Forms part of management KPI's
|  | 1 | Target 3 | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Forms part of management KPI's
|  | 1 | Tshepong | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Forms part of management KPI's
|  | 1 | Unisel | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Forms part of management KPI's
|  | 11 | [27 empty] | 0 | 0
| Lonmin | 1 | Eastern Operations - E2
|  | 1 | Eastern Operations - E3
|  | 1 | Karee Operations - 1B
|  | 1 | Karee Operations - 4B
|  | 1 | Karee Operations - K3
|  | 1 | Karee Operations - K4
|  | 1 | Middelkraal Operations - Hossy
|  | 1 | Middelkraal Operations - Saffy
|  | 1 | Opencast - Merensky
|  | 1 | Western Operations - Newman
|  | 1 | Western Operations - Rowland
|  | 1 | Western Operations - W1
|  | 12 | [27 empty] | 0
| ANGLO AMERICAN PLATINUM (AMPLATS) | 1 | Amandebult Mines - Dishaba
|  | 1 | Amandebult Mines - Tumela
|  | 1 | Bokoni
|  | 1 | Mogalakwena
|  | 1 | Rustenburg Mines - Bathopele
|  | 1 | Rustenburg Mines - BRPM
|  | 1 | Rustenburg Mines - Khomanani
|  | 1 | Rustenburg Mines - Khuseleka
|  | 1 | Rustenburg Mines - Marikana
|  | 1 | Rustenburg Mines - Siphumelele
|  | 1 | Rustenburg Mines - Thembelani
|  | 1 | Twickenham
12
| Mining Houses | 11 | Total Operations | [12 empty] | 98 | [12 empty] | Total Labour Force | 85636
Challenges
1 | Becsa
2 | BHP Billiton
3 | Northern Cape
4 | Cullinan Diamonds
5 | Aveng
6 | Coal Sector
7 | Colliery
8 | Khumba Iron Ore
9 | Modikwa
10 | Marula
11 | Twickenham
12 | Foskor
13 | AGA
14 | PPC
15 | Afrisam
16 | Khutala
17 | Lonmin
18 | Impala Platinum
19
20
Note on D10: JDeBeer01: First meeting was not with the mine adoption team, but with Occ hygienist
Note on D11: JDeBeer01: First meeting was not with the mine adoption team, but with Occ hygienist
Note on D15: JDeBeer01: First meeting was not with the mine adoption team, but with Occ hygienist
Note on D73: JDeBeer01: Team establishment will take place on 23 April 2013
Note on D74: JDeBeer01: Team establishment will take place on 23 April 2013
Note on D75: JDeBeer01: Team establishment will take place on 23 April 2013
Note on D76: JDeBeer01: Team establishment will take place on 23 April 2013
Note on D77: JDeBeer01: Team establishment will take place on 23 April 2013
Note on D78: JDeBeer01: Team establishment will take place on 23 April 2013
Note on D79: JDeBeer01: Team establishment will take place on 23 April 2013