## Slide 1: T&M Adoption Team Danie van der Merwe Harold Storbeck Kobus Blomerus
September/October 2013

## Slide 2
Contents
Mission and values reminder
T&M Performance Indicator
Progress update – key indicators
Progress this Month
Plan for next Month
Lowlights
Key lessons learnt
Leading the change to zero harm

## Slide 3
Leading the change to zero harm
Mission and Values - MOSH
To facilitate the adoption of leading practice through a people oriented process to significantly improve occupational health and safety in the minerals industry
Our ultimate goal is the provision of working conditions that are free from harmful effects
Values

## Slide 4
Progress update - key indicators for Hard Rock PDS
Covering identification, documenting, facilitating and impacts for the leading practice in question
Leading the change to zero harm
KPA No | Key Performance Area | KPI No | KPI | Measure 1 (Definition) | Measure 2 (Definition) | Measure 1 | Measure 2 | Originally planned completion
A18 | Establishment of effective COPA | T68 | Updated Leading Practice Adoption Guide |  |  |  |  | Sept 2013
 |  | T69 | COPA modus operandi |  |  | 100% | May 2013 | May 2013
 |  | T70 | Website access |  |  | 0% |  | 
 |  | T71 | Updated membership list |  |  | 100% | June 2013 | May 2013
 |  | T72 | COPA membership |  |  | 80% | June 2013 | May 2013
 |  | T73 | COPA attendance |  |  |  |  | 
 |  | T74 | Adoption investigation process |  |  | 60% |  | Sept 2013
 |  | T75 | COPA effectiveness |  |  | 85% | June 2013 | June 2013
A21 | Final leading peactice adoption guide | T92 | Consultation draft of final guide |  |  |  |  | Dec 2013
 |  | T93 | Final Leading Practice Adoption Guide |  |  |  |  | Dec 2013
 |  | T94 | Peer Group assessment |  |  |  |  | Jan 2014

## Slide 5
Progress update - key indicators for Coal PDS
Covering identification, documenting, facilitating and impacts for the leading practice in question
Leading the change to zero harm
KPA No | Key Performance Area | KPI No | KPI | Measure 1 (Definition) | Measure 2 (Definition) | Measure 1 | Measure 2 | Originally planned completion
A18 | Establishment of effective COPA | T68 | Updated Leading Practice Adoption Guide |  |  |  |  | Sept 2013
 |  | T69 | COPA modus operandi |  |  | 100% | May 2013 | May 2013
 |  | T70 | Website access |  |  | 0% |  | 
 |  | T71 | Updated membership list |  |  | 100% | June 2013 | May 2013
 |  | T72 | COPA membership |  |  | 80% | June 2013 | May 2013
 |  | T73 | COPA attendance |  |  |  |  | 
 |  | T74 | Adoption investigation process |  |  | 60% |  | Sept 2013
 |  | T75 | COPA effectiveness |  |  | 85% | June 2013 | June 2013
A21 | Final leading peactice adoption guide | T92 | Consultation draft of final guide |  |  |  |  | Dec 2013
 |  | T93 | Final Leading Practice Adoption Guide |  |  |  |  | Dec 2013
 |  | T94 | Peer Group assessment |  |  |  |  | Jan 2014

## Slide 6
Progress update - key indicators for Hard Rock PDS cont.
Covering identification, documenting, facilitating and impacts for the leading practice in question
Leading the change to zero harm
KPA No | Key Performance Area | KPI No | KPI | Measure 1 (Definition) | Measure 2 (Definition) | Measure 1 | Measure 2 | Originally planned completion
A22 | Leading practice adoption | T95 | Identified potential adoption mines |  |  |  |  | Sept 2013
 |  | T96 | Leading practice investigated for adoption |  |  |  |  | Sept 2013
 |  | T97 | Positive decision to adopt |  |  |  |  | Sept 2013
 |  | T98 | Mine adoption team appointed |  |  |  |  | Sept 2013
 |  | T99 | Investment in adoption |  |  |  |  | Sept 2013
 |  | T100 | Implementation plan (Including M&E) |  |  |  |  | Oct 2013
 |  | T101 | Accomodation of learning |  |  |  |  | 
 |  | T102 | Leading practice harmonised |  |  |  |  | 
 |  | T103 | Mental models interviews |  |  |  |  | 
 |  | T104 | Customised BC plan |  |  |  |  | 
 |  | T105 | Customised LB plan |  |  |  |  | 
 |  | T106 | Risk assessment |  |  |  |  | 
 |  | T107 | Training lesson plans |  |  |  |  | 
 |  | T108 | Management sign-off |  |  |  |  | 
 |  | T109 | Leading practice piloted |  |  |  |  | 
 |  | T110 | Roll-out plan implementation |  |  |  |  | 
 |  | T111 | Completed adoptions of leading practice |  |  |  |  | 

## Slide 7
Progress update - key indicators for Coal PDS cont.
Covering identification, documenting, facilitating and impacts for the leading practice in question
Leading the change to zero harm
KPA No | Key Performance Area | KPI No | KPI | Measure 1 (Definition) | Measure 2 (Definition) | Measure 1 | Measure 2 | Originally planned completion
A22 | Leading practice adoption | T95 | Identified potential adoption mines |  |  |  |  | Sept 2013
 |  | T96 | Leading practice investigated for adoption |  |  |  |  | Sept 2013
 |  | T97 | Positive decision to adopt |  |  |  |  | Sept 2013
 |  | T98 | Mine adoption team appointed |  |  |  |  | Sept 2013
 |  | T99 | Investment in adoption |  |  |  |  | Sept 2013
 |  | T100 | Implementation plan (Including M&E) |  |  |  |  | Oct 2013
 |  | T101 | Accomodation of learning |  |  |  |  | 
 |  | T102 | Leading practice harmonised |  |  |  |  | 
 |  | T103 | Mental models interviews |  |  |  |  | 
 |  | T104 | Customised BC plan |  |  |  |  | 
 |  | T105 | Customised LB plan |  |  |  |  | 
 |  | T106 | Risk assessment |  |  |  |  | 
 |  | T107 | Training lesson plans |  |  |  |  | 
 |  | T108 | Management sign-off |  |  |  |  | 
 |  | T109 | Leading practice piloted |  |  |  |  | 
 |  | T110 | Roll-out plan implementation |  |  |  |  | 
 |  | T111 | Completed adoptions of leading practice |  |  |  |  | 

## Slide 8
Progress update - key indicators for Open Cast Operations
Leading the change to zero harm
KPA No | Key Performance Area | KPI No | KPI | Measure 1 (Definition) | Measure 2 (Definition) | Measure 1 | Measure 2 | Originally planned completion
A1 | Appropriate participants in selection of leading practice | T1 | Credible team membership |  |  | 100% | 30 April 2013 | 30 April 2013
 |  | T2 | Ensure discipline input |  |  | 100% | 15 March 2013 | 15 March 2013
 |  | T3 | Ensure group input |  |  | 100% | 15 March 2013 | 15 March 2013
 |  | T4 | Approved participants list |  |  |  |  | 30 Aug 2013
 |  | T5 | Peer Group assessment |  |  |  |  | 29 Aug 2013
A2 | Appropriate plans for planning workshop | T6 | Competent Facilitator |  |  |  |  | 23 Sept 2013
 |  | T7 | Planning agenda |  |  |  |  | 28 Aug 2013
 |  | T8 | HOH review and approval |  |  |  |  | 23 Sept 2013
A3 | Detailed expert model of risk story | T9 | Stakeholder consultation |  |  |  |  | 
 |  | T10 | Prepared questions for input |  |  |  |  | 
 |  | T11 | Consultation draft expert model |  |  |  |  | 
 |  | T12 | Detailed expert models |  |  |  |  | 
 |  | T13 | Major risks and improvement possibilities |  |  |  |  | 
 |  | T14 | Peer Group assessment |  |  |  |  | 
A4 | Leading practice with greatest potential OHS impact | T15 | Review of R&D outcomes |  |  |  |  | 
 |  | T16 | Industry identified practices |  |  |  |  | 
 |  | T17 | Exploratory vists to mines |  |  |  |  | 
 |  | T18 | Detailed Leading Practice List |  |  |  |  | 
 |  | T19 | Credibility of selected Leading Practice |  |  |  |  | 
 |  | T20 | Workshop quality |  |  |  |  | 

## Slide 9
Progress for the Month
No | (PDS) (Achievements, Industry Interactions)
1 | Hard rock COPA at Sibanya very well supported with quite a few Production representatives
2 | Inter company Industry safety meeting – Safety day of interaction on the1st of November
3 | Coal Sector COPA very well supported- concern about the OEM support that they get – Specifically Strata
4 | Advisory Committee meeting
5 | PDS Tracking matrix provided to the industry for report on PDS Progress
6 | AMMSA District meetings – Northern Cape – Functionality Presentation – NW & Eastern Districts still outstanding
7 | Glencore /Xstrata colliery meeting with Head of Eng.
9 | NC Tripartite meeting
8 | CEO PDS Functionalities presentation - Coal = 43% - 121 Sections - Hard rock Track bound = 29% - 3278 Locos - Hard rock Trackless = 65% - 1806 Machines
Leading the change to zero harm

## Slide 10
Progress for the Month
No | (PDS) (Achievements, Industry Interactions)
9 | AMMSA District meeting presentation at Central & Free State - Eastern & North West Districts are still outstanding
10 | LDC Presentation on PDS Functionalities and the Possible in the different sectors- Draft has been changed
11 | Completed CEO draft report for Sept meeting
12 | Circular to Mine Managers to lobby support - Response very slow, but have received 7 official commitments
13 | CMEE Meeting – Committee members accepted for the OEM engagement on PDS monitoring requirement – Way Forward
14 | COPA Members T&M_COPA_for_Hard_Rock_PDS_02_October_2013.xlsx T&M_Team_attendanceregister_Coal_9_October_2013.xlsx Industry Members MembersT&MOpencast_24_September_2013.xlsx T&M_TEAM_COAL1.xlsx T&M_Team_members_-_Hard_Rock_-_Sept.xlsx
Leading the change to zero harm

## Slide 11
Progress for the Month
No | (General) (Achievements, Industry Interactions)
1 | Pre Planning activities for the 1st Open pit Planning Workshop at Glenburn (Expert Model)
2 | Pre Planning activities for the 2nd Coal Industry Planning Workshop (Expert Model)
3 | Preparations for the 1st Planning workshop underway for Opencast/Pit sector ( Expert Model & Risk Story
4 | Open Cast Industry Meeting
5 | 
6 | 
7 | 
8 | 
Leading the change to zero harm

## Slide 12
Plan for next Month
No | Industry Interactions ( PDS)
1 | AMMSA District Meeting presentation on PDS Functionalities ED
2 | MOSH Task Force meeting
3 | Mine safe conference
Leading the change to zero harm

## Slide 13
Plan for next Month
No | Industry Interactions (General)
1 | Continue with Pre Planning activities for the 2nd Hard rock & Coal Industry Planning Workshop
2 | Preparations for the 1st Planning workshop for Opencast/Pit sector
3 | Open Cast Industry Meeting
4 | CMEE Meeting
5 | Mine Safe Conference
6 | Meeting with Sponsor – Wilco Uys
Leading the change to zero harm

## Slide 14
Lowlights
No | Lowlights (Issues, Risks, Concerns) | Response - Remedial Action | Due Date | Resp. Person
1 | Slow response to PDS Adoption as per the MOSH Process | Continual Communication |  | 
Leading the change to zero harm

## Slide 15
Key lessons learnt
No | Key lessons learnt
1 | Under estimating the amount of work in wide spread Adoption Process
2 | Availability of resources on the mines to support the Adoption process
3 | 
4 | 
Leading the change to zero harm

## Slide 16
T&M Planning for Oct 2012- Dec 2013
Leading the change to zero harm
Description | Start date | Target date | Responsibility | Remarks
Widespread adoption Industry to join PDS COPA to assist them with widespread adoption n of PDS | 7 Aug ’12 | 4th Quarter '13 | T&M Industry Team | 80% of adoption deciders achieves 60%
2nd Leading Practice Workshops to identify Leading Practice (3) | Nov ’12 | 1st Quarter '13 | T&M Industry Team | 
1 Leading Practices to mature to Adoption Workshop Status | April ’13 | 4th Quarter '13 | T&M Industry Team | 
2 Simple Leading Practices | April ’13 | 3th Quarter '13 | T&M Industry Team | Identify SLP during the first Quarter, widespread adoption by end 2013
Improved Industry Coverage with T&M, with the focus on Surface Mobile Equipment | Jan ‘’13 | 4th Quarter '13 | T&M MOSH Learning Hub Team | Focus on surface mobile equipment
Days of Learning facilitated as requested by industry | Jan ’13 | 4th Quarter '13 | T&M Industry Team | 1 per quarter to be facilitated
Industry Commodity/Asset profile (Outsource) | Jan ‘13 | 3 rd Quarter '13 | T&M MOSH Learning Hub Team | Acceptance dependant on Proposal to MHSC

## Slide 17
T&M Planning for Oct 2012- Dec 2013
Leading the change to zero harm
Open cast
Industry Team
February 2013
Team Training
March 2013
Coal Sector
Khutala Rollout
Dec 2013 >
Tech Work Group Forum Sessions
April 2013
Hard Rock Sector
AGA PDS Direct Inquiries
April 2013
Fist Adopters Mine Commitment
April 2013
Pre- Workshop Planning
April 2013
Pre- Workshop Planning
April 2013
Detail Adoption Plan
May 2013
Tech. Work Group Forum Sessions
May 2013
Planning Workshop
June 2013
Pre Planning Workshop
April 2013
2nd T&M Planning Workshop
May 2013
Leading Practice Identification/Mine Visits
Jun/Jul 2013
LB & BC Plans
May 2013
PDS COPA 6 Weekly - Ongoing -Starting April 2013

## Slide 18
T&M Planning for 2013
Leading the change to zero harm
 |  | T&M Team Year Plan 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December
 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 3 |  |  |  |  |  |  |  | 2 | T&M Coal Industry Meeting |  |  |  |  | 1 |  |  |  |  |  |  |  |  | 
 | 4 |  | 1 |  | 1 |  |  |  | 3 |  |  |  |  |  | 2 |  |  |  |  |  | 1 |  |  | 
 | 5 |  | 2 |  | 2 |  |  |  | 4 |  | 1 |  |  |  | 3 |  |  |  |  |  | 2 |  |  | 
 | 6 |  | 3 |  | 3 |  |  |  | 5 |  | 2 |  |  |  | 4 |  | 1 |  |  |  | 3 |  | 1 | 
 | 7 |  | 4 |  | 4 |  | 1 |  | 6 |  | 3 |  | 1 |  | 5 |  | 2 |  |  |  | 4 |  | 2 | 
 | 8 |  | 5 | Kuthala Meeting | 5 | Kuthala Meeting | 2 | Kuthala Meeting | 7 |  | 4 | T&M Gold Industry Meeting | 2 |  | 6 |  | 3 |  | 1 |  | 5 |  | 3 | Kuthala Meeting
 | 9 |  | 6 | AGA MOSH Presentation - Moab Kgotsong & Kopanang | 6 | Planning Meeting | 3 |  | 8 |  | 5 |  | 3 |  | 7 |  | 4 |  | 2 |  | 6 |  | 4 | T&M Coal Indusrty Meeting
 | 10 |  | 7 | SACMA Council Meeting | 7 | Diversity Training | 4 | AMMSA - ED/W | 9 |  | 6 | SACMA Council | 4 |  | 8 |  | 5 | AMMSA - ED/W | 3 | AMMSA - FS/C | 7 | AMMSA - ED | 5 | 
 | 11 |  | 8 |  | 8 |  | 5 |  | 10 | AMMSA - Central Council Meeting | 7 |  | 5 |  | 9 |  | 6 |  | 4 | SACMA Council | 8 |  | 6 | 
 | 12 |  | 9 |  | 9 |  | 6 |  | 11 |  | 8 |  | 6 |  | 10 |  | 7 |  | 5 |  | 9 |  | 7 | 
 | 13 | Meeting with M. Bester/Ronnie v. Rooyen | 10 |  | 10 |  | 7 |  | 12 |  | 9 |  | 7 |  | 11 |  | 8 |  | 6 |  | 10 |  | 8 | 
 | 14 | LPAG Meeting | 11 |  | 11 |  | 8 |  | 13 | SACEA Limpopo Meeting | 10 |  | 8 |  | 12 |  | 9 |  | 7 |  | 11 |  | 9 | 
 | 15 | Risk Meeting | 12 | AGA MOSH Presentation - Savuka & GNM | 12 | T&M Gold Industry Meeting | 9 |  | 14 | Kuthala Meeting | 11 | Kuthala Meeting | 9 | Kuthala Meeting | 13 | Kuthala Meeting | 10 | Kuthala Meeting | 8 | T&M Gold Industry Meeting | 12 | Kuthala Meeting | 10 | 
 | 16 |  | 13 | PDS HR Copa & MCC Meeting | 13 |  | 10 |  | 15 |  | 12 | T&M Coal Indusrty Meeting | 10 |  | 14 |  | 11 | T&M Coal Indusrty Meeting | 9 |  | 13 |  | 11 | 
 | 17 | Monthly MOSH Meeting | 14 |  | 14 | SACEA Coucil Meeting | 11 |  | 16 | Monthly MOSH Meeting | 13 | Monthly MOSH Meeting | 11 | SACEA Council Meeting | 15 | Monthly MOSH Meeting | 12 |  | 10 | SACEA Council/AMMSA Central Coucil | 14 |  | 12 | 
 | 18 |  | 15 |  | 15 |  | 12 |  | 17 |  | 14 |  | 12 |  | 16 |  | 13 |  | 11 |  | 15 |  | 13 | 
 | 19 |  | 16 |  | 16 |  | 13 |  | 18 |  | 15 |  | 13 |  | 17 |  | 14 |  | 12 |  | 16 |  | 14 | 
 | 20 |  | 17 |  | 17 |  | 14 |  | 19 |  | 16 |  | 14 |  | 18 |  | 15 |  | 13 |  | 17 |  | 15 | 
 | 21 |  | 18 |  | 18 |  | 15 |  | 20 |  | 17 |  | 15 |  | 19 |  | 16 |  | 14 |  | 18 |  | 16 | 
 | 22 | T&M Management Meeting | 19 | Open Cast Workshop | 19 |  | 16 | Kuthala Meeting | 21 |  | 18 |  | 16 | T&M Gold Industry Meeting | 20 | T&M Gold Industry Meeting | 17 |  | 15 | Kuthala Meeting | 19 | T&M Gold Industry Meeting | 17 | 
 | 23 | CM&EE Meeting | 20 | Kuthala Meeting | 20 |  | 17 |  | 22 | CM&EE Meeting | 19 |  | 17 |  | 21 |  | 18 |  | 16 |  | 20 | CM&EE Meeting | 18 | 
 | 24 |  | 21 | Monthly MOSH Meeting | 21 | Monthly MOSH Meeting | 18 | Coal Safe/Monthly MOSH Meeting | 23 | SACEA North Meeting | 20 |  | 18 | Monthly MOSH Meeting | 22 |  | 19 | SACMA District- South /North & Monthly MOSH Meeting | 17 | Monthly MOSH Meeting | 21 | Monthly MOSH Meeting | 19 | Monthly MOSH Meeting
 | 25 |  | 22 |  | 22 |  | 19 |  | 24 |  | 21 |  | 19 |  | 23 |  | 20 |  | 18 |  | 22 |  | 20 | 
 | 26 |  | 23 |  | 23 |  | 20 |  | 25 |  | 22 |  | 20 |  | 24 |  | 21 |  | 19 |  | 23 |  | 21 | 
 | 27 |  | 24 |  | 24 |  | 21 |  | 26 |  | 23 |  | 21 |  | 25 |  | 22 |  | 20 |  | 24 |  | 22 | 
 | 28 |  | 25 |  | 25 |  | 22 |  | 27 |  | 24 |  | 22 |  | 26 |  | 23 |  | 21 |  | 25 |  | 23 | 
 | 29 | T&M Gold Industry Meeting - Risk Discussion | 26 | Behavioural Conference | 26 | Kuthala Meeting | 23 | T&M Gold Industry Meeting | 28 |  | 25 |  | 23 | Kuthala Meeting | 27 | Mining Lekgotla | 24 |  | 22 |  | 26 |  | 24 | 
 | 30 | AGA MOSH Presentation - Mponeng & Tau Tona | 27 | Behavioural Conference | 27 |  | 24 |  | 29 |  | 26 |  | 24 | CM&EE Meeting | 28 | Mining Lekgotla/Eastern District Tripartite Meeting | 25 | CM&EE Meeting | 23 | T&M Coal Indusrty Meeting | 27 | Eastern District Tripartite Meeting | 25 | 
 | 31 | T&M Coal Indusrty Meeting | 28 | Behavioural Conference | 28 | T&M Coal Industry Meeting | 25 | SACMA/SACEA District - South | 30 |  | 27 |  | 25 | T&M Coal Indusrty Meeting | 29 | Mining Lekgotla | 26 |  | 24 |  | 28 |  | 26 | 
 |  |  |  |  | 29 |  | 26 |  | 31 | Easthern District Tripartite Meeting | 28 | SACMA District - South, North, Limpopo | 26 |  | 30 |  | 27 |  | 25 |  | 29 |  | 27 | 
 |  |  |  |  | 30 |  | 27 |  |  |  | 29 |  | 27 |  | 31 |  | 28 |  | 26 |  | 30 |  | 28 | 
 |  |  |  |  | 31 |  | 28 |  |  |  | 30 |  | 28 |  |  |  | 29 |  | 27 |  |  |  | 29 | 
 |  |  |  |  |  |  | 29 |  |  |  |  |  | 29 |  |  |  | 30 |  | 28 |  |  |  | 30 | 
 |  |  |  |  |  |  | 30 |  |  |  |  |  | 30 |  |  |  |  |  | 29 |  |  |  | 31 | 
 |  |  |  |  |  |  |  |  |  |  |  |  | 31 |  |  |  |  |  | 30 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 31 |  |  |  |  |