## Slide 1: Noise Adoption Team
19th September 2013

## Slide 2
Contents
Key activities/highlights of the month
Lowlights
Key lessons learnt
Future activities

## Slide 3
Key Team activities for the Month (Aug/Sep 2013)
No | Highlights (Achievements, Industry Interactions)
1. | HPD_TAS Adoption Finalizing Sasol (Coal fraternity) 11 Sep 2013 – Sasol Sigma Colliery - MOSH Adoption & LP Induction Pilot shaft identified Impala Adoption 19 Aug 2013 – Adoption Team meeting – the way forward 04 Sep 2013 – Adoption Team - Mosh Induction Training Adoption team ownership establishment Lonmin 28 Aug 2013 – New OH leadership MOSH Adoption & LP Induction 03 Sep 2013 – Mine Adoption Team Induction BECSA 12 Sep 2013 – Adoption Team – Induction Training (poor attendance) ARM 13 Sep 2013 – Modikwa – Noise Interviewer Training (Independent LB&BC) TRP & Nkomati – Implementing customized LB&BC plans Glencore Xstrata Western Limb Implementing customized LB&BC plans

## Slide 4
Key Team activities for the Month (Aug/Sep 2013)
No | Highlights (Achievements, Industry Interactions)
2. | Verification exercise for potential LP (Impala, Shaft Sinkers, Glencore) Final verification to be presented to the Industry Team Meeting – 02nd October 2013 Customized HPD System - Impala Platinum Lashing Unit Shaft Sinkers OAE Verification – Glencore Xstrata Mototolo Platinum

## Slide 5
Key Team activities for the Month (Aug/Sep 2013)
No | Highlights (Achievements, Industry Interactions)
3. | Industry wide “Buy quiet” Initiative 21 Aug 2013 – CM&EE and GEE Mini workshop Nominations of industry task teams (TOR)
No | Lowlights
1. | 23 July 2013 – BECSA cancellation of HPD induction training . 12 Aug 2013 – BECSA – Cancellation of Adoption team training – Lack of stakeholders EXXARO – Slow adoption
Lowlights of the month (Aug/Sep 2013)

## Slide 6
Key lessons learnt
No | Key Lessons learnt
1. | COPA’s Necessity of COPA’s for HPD_TAS ?
No | Future activities
1. | 19 Sep 2013 – Lonmin HPD_TAS Verification - NRR Derating Applicability 20 Sep 2013 – MVS Milestone workshop 25 Sep 2013 – Tri partite meeting Mototolo 26 Sep 2013 – Sponsor meeting 02 Oct 2013 – Industry meeting 08 Oct 2013 – The Art of Hearing Conservation Conference South Deep – Visit?
Important Future activities