## Slide 1: MOSH Falls of Ground Team Leading Practice Adoption Team Activity Report
September 2013

## Slide 2
Contents
Mission and Values reminder
Progress update – key indicators
Highlights
Challenges
Key lessons learnt

## Slide 3
Leading the change to zero harm
Mission and Values - MOSH
To facilitate the adoption of leading practice through a people oriented process to significantly improve occupational health and safety in the minerals industry
Our ultimate goal is the provision of working conditions that are free from harmful effects
Values

## Slide 4
J 12 | J 12 | A 12 | S 12 | O 12 | N 12 | D 12 | J 13 | F 13 | M 13 | A 13 | M 13 | J 13 | J 13 | A 13 | S 13 | O 13 | N 13 | D 13
FOG Adoption Team Planner
Prevention of All Uncontrolled Falls of Ground
COAL COPA (Coal Specific Practices)
Plan
NC COPA (EE&MS, TARP)
Hard Rock COPA (N&B’s, TARP)
Eastern Limb COPA (EE&MS, TARP)
Coal industry workshops to identify Leading Practices were held for underground and surface
The workshops were not well attended
Three leading practices have emerged.
Coal Mining industry adoption team has a core group that will drive process forward
Feedback given to SACMA
2014 Planning Workshop – 14 November 2013 at Glenburn Lodge
Planning for about 50 delegates, E upper and above. Already had some good responses
Delegates to guide us for the 2014 progress planner and LP Adoption Plan
N Cape COPA has been formed
Petra Diamond Mines and
Black Rock (ARM) and
Wessels (BHP) participating
Next COPA on October 2013 at Finsch
EE&MS
Revisiting adoption at mines and tightening the loose ends
Bosjessruit Colliery have expressed interest in adopting EE&MS. Two meeting held with them.
13 th COPA Meeting was held on the
6 th September 2013 at Randfontein Golf Club.
27 Mines are participating. + 83 % complete for Nets with Bots
TARP is 23%- Most mines completed interviews – 33 mines participating
Next meeting scheduled for 18 October 2013 at Randfontein Golf Club.
Assisting individual mines in 4 regions of Central COPA through additional COPA meetings
Eastern Limb COPA revived
Review EE&MS Quality of Adoption
Progressing with TARP Adoption
13 Mines participating
Good progress by some mines

## Slide 5
Progress for the Month of July / August 2013
No` | Highlights (Achievements, Industry Interactions)
1 | Tripartite forums visited and positively participated
2 | Establishing Presence in the Coal Industry. Two workshops held for the FoG Leading Practice identification. Three LPs identified
3 | Established additional support with COPA members . Visiting them in their respective areas. Lonmin
4 | Good information coming in relative to lives saved through net installations in the narrow reef hard rock stoping environment
5 | Request from mines to help with TARP roll out. Impala, Modikwa, Marula and Phakisa. Meetings and assistance given to these mines from Adoption Team Management.
6 | Preparation of presentation for MineSafe2013
Leading the change to zero harm

## Slide 6
Progress for the Month of August/September 2013
No | Challenge (Issues, Risks, Concerns) | Response - Remedial Action | Due Date | Resp. Person
1 | No continuity of attendees at COPA meetings. Mines do not seem to have established good adoption teams | Lobby MOSH Task Force and Senior Management of Mining Companies for appropriate representation | On going | AvZ DA
2 | Poor reaction to assistance offered to mines who struggle with adoption in their respective mining regions | Take-up with COPA’s and MOSH FOG Industry Adoption Team Members | On going | AvZ DA
3 | Analysis of the rock related safety data for coal, platinum and gold shows little improvement for serious injuries | In considering any new Leading Practices attention must be paid to addressing these issues as rigorously as fatalities | At next LP identification work-shops | AvZ DA
Leading the change to zero harm

## Slide 7
Chart: MOSH FOG Nets with Bolts Adoption Monitor
Percentage of Units with Documents Signed Off | 0.95833 | 0.95833 | 0.95833 | 0.875 | 0.79167 | 0.79167 | 0.875 | 0.875 | 0.70833 | 0.75
Percentage of Units Completed not Signed Off | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Percentage of Units with Work In Progress | 0 | 0 | 0 | 0.125 | 0.20833 | 0.20833 | 0.125 | 0.083333 | 0.25 | 0.20833
Percentage of Units No Action | 0.041667 | 0.041667 | 0.041667 | 0 | 0 | 0 | 0 | 0.041667 | 0.041667 | 0.041667

## Slide 8
Chart: MOSH FOG TARP Adoption Monitor
| LP Review | Implementation Plan | Procedure Amended | MM Interviews | LB Plan | BC Plan | Risk Assessment | Lesson Plans | Management Reviews | Roll Out Plan
Percentage of Units with Documents Signed Off | 0.76471 | 0.47059 | 0.41176 | 0.11765 | 0.058824 | 0.029412 | 0.058824 | 0.058824 | 0.058824 | 0.058824
Percentage of Units Completed not Signed Off | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Percentage of Units with Work In Progress | 0.14706 | 0.11765 | 0.17647 | 0.17647 | 0.17647 | 0.20588 | 0.058824 | 0.058824 | 0.058824 | 0.058824
Percentage of Units No Action | 0.088235 | 0.41176 | 0.41176 | 0.70588 | 0.76471 | 0.76471 | 0.88235 | 0.88235 | 0.88235 | 0.88235