## Slide 1
1
Approximately Right, Not Precisely Wrong
Lessons learnt from facilitating the HPD TAS Adoption
October 2013

## Slide 2
2
Introduction
Objective
  To share experiences and key learning's in facilitating the HPD TAS adoption process
  Highlight opportunities to enhance the MOSH process
Context
  Lessons / experience from wide spread adoption phase only
  Major Steps Included
    Committing and deciding to adopt
    Setting up Multi disciplinary Adoption teams
    Induction of the Adoption Team (s)
    Agree and sign off the implementation plan

## Slide 3
3
Introduction
Context
  Major Steps Included (cont.)
    Identify the Interviewers & Interviewee
    Train the Interviewers
    Mental Model Interviews
    Leadership Behaviour & Behaviour Communication Plans
    Process Roll-out plan in place
  Presentation about 10- 20 % anomalies of the 300 Interview results

## Slide 4
4
Lessons Learnt
  Conclusions based on analysing about 300 Interviews from Adopters
Timelines – Lead times only
  Deciding to adopt - 1month to 1yr 6 months
  Setting up Multi disciplinary Adoption teams – 3 weeks vs. 3weeks to 2 Months
  Induction of the Adoption Team (s) – 1 week vs. 1 week
    - Agree and sign off the implementation plan -
  Identify the Interviewers & Interviewee 1week vs. 1 week to 1 month
  Train the Interviewers - 1 week vs. 1 week to 1month
  Mental Model Interviews - 1 Month vs. 1 Month to 2 Months
  LB & BC Plans - 1 Month vs. 1 Week (Generic plans for “old” customers)

## Slide 5
Competency of Interviewers
No standardized way of accessing their competency
Most of the times we (MOSH) were not present during the actual interviews
Simple application of 5 Whys - to solicit the root problem
Some questions were not answered.
Identification of Interviewers & Interviewee
Integrity Issues
No vertical split of the interviewees – Interviews up to shift boss level (even when emphasized during training)
Labour unrest
Some responses were a “copy and paste” exercise
Suspiciously same answers from different people / occupations but same handwriting
Destruction of original copies
Mitigating Competency issues
Did not use suspiciously contaminated data
Supplied Generic LB & BC
Actual doing of the LB & BC
Appeal to principal s for advice – MOSH Task force
Mitigating the vertical split issue
Mitigating Integrity Issues
Lessons Learnt
Engaged concerned companies and they admitted
Did not use suspiciously contaminated data
Supplied Generic LB & BC
Appeal to principals for advice – MOSH Task force

## Slide 6
No new insights
(Direct Enquiries)
No coding were done
Same knowledge aspects listed
Interviewer competence is key
Limited buy in if only few are interviewed
Poor Communication
Despite direct enquiries no proper LB & BC plans were formulated because interviewers could not translate responses into messages and modes.
Selection of interviewers to be formalized.
Training and EXPERIENCE required –process to be substantially lengthened, interviewer testing to be included.
Little value for major effort, can it be justified
Is direct enquiries the best way to ensure buy in for the population we are working with?
Leveraging of Unions and other trustworthy agencies
Lessons Learnt
Do we need to rethink what we want to achieve and how to best do it.
Specialized communication service providers exclusively
Everybody wanted to be heard.
To interview 12000 people take time, to code will take many months.
Labor structures not involved
Implications for MOSH process

## Slide 7
7
Conclusions
Wide Spread adoption phase can take more than 2 years for a practice that should take 4 weeks. Can industry afford the progress resulting from this pace – lost opportunity for improved health performance
Interviewer competence is not knowledge only
Interviewers must be trusted by workers – No silver bullet
Far more emphasis is needed on communication modes and messages

## Slide 8
8
Conclusions
Direct Enquiries ≠ buy in
Direct Enquiries is a specialist process
Behavioural communication is a specialist process
Ineffective direct enquiries is very costly