## HPDTAS Adoption Tracker
| 2013-10-16 | MOSH HPD TAS Adoption Monitor Programme
| Mining House | Number | Name of Mine/ Shaft | Company | Name of Manager | Name of Project Leader | E-mail Address of Project Leader | Telephone Number | Do you have a FOG Risk associated with nets with bolts? | Do you have FOG Risk Controls in place | Do you have a Procedure on the application of Bolts with Nets | Is your FOG related LTIFR<0,05 | Have you considered the Adoption of the Leading Practice on Nets with Bolts | Yes, we want to Adopt the Leading Practice on Nets with Bolts | No, we do not want to Adopt the Leading Practice on Nets with Bolts | Setting up Multi disciplinary Adoption Teams | Induction of the Adoption Team (s) | Agree on the Implementation Plan | Identify the interviews & Interviews | Train the Interviewers | Mental Model Interviews | Leadership Behaviour Plan | Behaviour Communication Plan | Risk Assessment | Training Lesson Plans | Management Review Process | Roll-out plan in place | Challenges | Highlights | Number of People to cover | Number of People covered | COPA Participation
| ARM |  | Black Rock | [12 empty] | IP | [12 empty] | Cooperative and high level involvement |  |  | No
|  |  | Modikwa | [12 empty] | Com | Com | Com | Com | Com | Com | IP | IP | NS | NS | NS | NS | The roll out of the LB&BC Plans. Poe interactions completed during March 2014 | Cooperative and high level involvement | 5896 |  | YES
|  |  | Nkomati | [12 empty] | Com | Com | Com | Com | Com | Com | IP | IP | NS | NS | NS | NS | The roll out of the LB&BC Plans. Poe interactions completed during March 2014 | Cooperative and high level involvement | 3128 |  | YES
4 |  |  | Two Rivers | Harmony |  | Rusiano Tsoka | rusiano.tsoka@harmony.co.za | 829271018 | y | Y | Y | Y | Y |  |  | Com | Com | Com | Com | Com | Com | IP | IP | NS | NS | NS | NS | The roll out of the LB&BC Plans. Poe interactions completed during March 2014 | Cooperative and high level involvement | 3486 |  | YES
| EXXARRO |  | Arnot | Anglo Gold Ashanti | Francois Naude |  | fnaude@anglogoldashanti.com | 713635097 | y | y | y | y | y |  |  | IP | [7 empty] | NS | NS | NS | NS | Raise concerns with group HSEC/GEE | Project Manager Resigned - New project Manager on board | 1400 |  | YES
|  |  | Grootegeluk | Harmony |  | Marius Van der Merwe | marius.vandermerwe@harmony.co.za | 0723684289/0574524445 | y | y | y | y | y |  |  | IP | [7 empty] | NS | NS | NS | NS | Raise concerns with group HSEC/GEE |  | 2000 |  | YES
|  |  | Leeuwpan | [12 empty] | IP | [7 empty] | NS | NS | NS | NS | Raise concerns with group HSEC/GEE |  | 500 |  | YES
|  |  | Matla 1 | [24 empty] | Raise concerns with group HSEC/GEE |  |  |  | YES
|  |  | Matla 2 | [24 empty] | Raise concerns with group HSEC/GEE |  |  |  | YES
|  |  | Matla 3 | [12 empty] | Com | Com | Com | Com | Com | [7 empty] | Raise concerns with group HSEC/GEE |  | 2500 |  | YES
|  |  | North Block Complex - Glisa and Strathrae coal mines, Eerstelingsfontein and Belfast coal projects | [24 empty] | Raise concerns with group HSEC/GEE |  | 1621 |  | YES
8 |  |  | Tshekodeni | Harmony | Rudi Phillis | Tienie Landman | Tienie.Landman@Harmony.co.za | 579167111 | y | y | y | y | y |  |  | IP | IP | IP | [9 empty] | Raise concerns with group HSEC/GEE |  | 680 |  | YES
| IMPALA |  | General | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 336 |  | YES
|  |  | Laboratories | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 48 |  | YES
|  |  | Medical Services | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 108 |  | YES
|  |  | Minpro | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 1469 |  | YES
|  |  | Opencast | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 207 |  | YES
|  |  | Processing | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 641 |  | YES
|  |  | Services | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 4955 |  | YES
|  |  | Shaft 1 | Xstrata Alloys |  | Phil Garner | pgarner@xstrata.co.za | 829219441 | y | y | y | y | y |  |  | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 4565 |  | YES
|  |  | Shaft 11C | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 32 |  | YES
|  |  | Shaft 14 | Anglo Gold Ashanti | Randel Rademan |  | crrademann@anglogoldashanti.com | 187005450 | y | y | y | y | y |  |  | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 4803 |  | YES
|  |  | Shaft 16 | Harmony |  | Velaphi Waganda | velaphi.waganda@harmony.co.za | 579074114 | y | y | y | y | y |  |  | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 1046 |  | YES
|  |  | Shaft 17 | Harmony |  | Warren Freeman | Warren.Freeman@harmony.co.za | 847016876 | y | y | y | y | y |  |  | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 427 |  | YES
|  |  | Shaft 2 | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 689 |  | YES
|  |  | Shaft 20 | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 2677 |  | YES
|  |  | Shaft 4 | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 1755 |  | YES
|  |  | Shaft 5 | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 480 |  | YES
|  |  | Shaft 6 | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 1195 |  | YES
|  |  | Shaft 7A | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 1419 |  | YES
|  |  | Shaft EF | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 759 |  | YES
|  |  | Shaft10 | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 3181 |  | YES
|  |  | Shaft11 | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 6966 |  | YES
|  |  | Shaft12 | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 3746 |  | YES
|  |  | Shaft7A | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 1244 |  | YES
|  |  | Shaft8 | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 980 |  | YES
|  |  | Shaft9 | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 2126 |  | YES
|  |  | SMLT | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 637 |  | YES
|  |  | Tailings | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 237 |  | YES
|  |  | Toll | Anglo Gold Ashanti | Andre van Jaarsveld | Danny Davis | ddavies@anglogoldashanti.com | 187008963 | y | y | y | y | y |  |  | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 8 |  | YES
29 |  |  | UG2 | [12 empty] | Com | Com | Com | Com | Com | IP |  |  | NS | NS | NS | NS |  | Labour unrest impacts on interviews | 196 |  | YES
1 | NORTHAM |  | Zondereinde Platinum | Impala | Mathias Sithole |  | Mathias.sithole@implats.co.za | 829431572 | y | y | y | y | y |  |  | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS | Active participation from unions | Good cooperation | 9116 |  | YES
| GLENCORE XSTRATA - ALLOYS - EASTERN CHROME MINES |  | Helena | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS | The roll out of the LB&BC Plans | Good cooperation | 941 |  | YES
|  |  | Magareng | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS | The roll out of the LB&BC Plans | Good cooperation | 910 |  | YES
|  |  | Shared Services | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS | The roll out of the LB&BC Plans | Good cooperation | 340 |  | YES
|  |  | Thorncliffe | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS | The roll out of the LB&BC Plans | Good cooperation | 946 |  | YES
5 |  |  | UG 2 | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS | The roll out of the LB&BC Plans | Good cooperation | 17 |  | YES
| GLENCORE XSTRATA - ALLOYS - WESTERN CHROME MINES |  | Horizon | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS | The roll out of the LB&BC Plans | Good cooperation | 563 |  | YES
|  |  | Kroondal | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS | The roll out of the LB&BC Plans | Good cooperation | 969 |  | YES
|  |  | Rietvlei | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS | The roll out of the LB&BC Plans | Good cooperation | 49 |  | YES
|  |  | UG 2 | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS | The roll out of the LB&BC Plans | Good cooperation | 334 |  | YES
5 |  |  | Waterval | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | NS | NS | NS | NS | The roll out of the LB&BC Plans | Good cooperation | 745 |  | YES
| GLENCORE XSTRATA -PLATINUM - EASTERN MINES |  | Mototolo Borwa | [12 empty] | Com | Com | Com | Com |  |  |  |  | NS | NS | NS | NS | To get the correct target group after several attemps | 22 Nov 13 interviewer training | 842 |  | YES
2 |  |  | Mototolo Lebowa | [12 empty] | Com | Com | Com | Com |  |  |  |  | NS | NS | NS | NS |  |  | 1321 |  | YES
1 | GLENCORE XSTRATA - PLATINUM - WESTERN MINES |  | Eland | [20 empty] | NS | NS | NS | NS |  | No reply on various e-mails
| GLENCORE COLLIERIES |  | Goedgevonden Complex Opencast | [25 empty] | Decision pending | 962
|  |  | Impunzi Complex Surface | [25 empty] | Decision pending | 1434
|  |  | Twee Fontein Complex UG | [25 empty] | Decision pending | 2163
4 |  |  | Optimum Complex UG | [25 empty] | Decision pending
| SASOL |  | Bosjiespruit | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Company Internal COPA meeting held on 5th Marc 2014
|  |  | Brandvlei | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Company Internal COPA meeting held on 5th Marc 2015
|  |  | Middelbult | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Company Internal COPA meeting held on 5th Marc 2016
|  |  | Secunda | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Company Internal COPA meeting held on 5th Marc 2017
|  |  | Sigma | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Company Internal COPA meeting held on 5th Marc 2018
|  |  | Syferfontein | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Company Internal COPA meeting held on 5th Marc 2019
|  |  | Twistdraai | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Company Internal COPA meeting held on 5th Marc 2020
|  |  | Shondoni | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Company Internal COPA meeting held on 5th Marc 2021
|  |  | TEP | [12 empty] | Com | Com | Com | Com | Com | Com | Com | Com | [5 empty] | Company Internal COPA meeting held on 5th Marc 2022
10 |  |  | Forbes Coal | [25 empty] | Company Internal COPA meeting held on 5th Marc 2023
69 | Mining Houses | 10 | Total Operations | [25 empty] | Total Labour Force | 89795
|  | Numbers | No Progress (NP) | [12 empty] | 9 | 13 | 13 | 14 | 16 | 17 | 46 | 46 | [6 empty] | 179590
|  |  | In progress (IP) | [12 empty] | 5 | 1 | 1 | 0 | 0 | 29 | 3 | 3
|  |  | Completed (COM) | [12 empty] | 55 | 55 | 55 | 55 | 53 | 23 | 20 | 20
|  | Percentage | No Progress (NP) | [12 empty] | 13.04% | 18.84% | 18.84% | 20.29% | 23.19% | 24.64% | 66.67% | 66.67%
|  |  | In progress (IP) | [12 empty] | 7.246% | 1.449% | 1.449% | 0% | 0% | 42.03% | 4.348% | 4.348%
|  |  | Completed (COM) | [12 empty] | 79.71% | 79.71% | 79.71% | 79.71% | 76.81% | 33.33% | 28.99% | 28.99%
Note on D9: JDeBeer01: First meeting was not with the mine adoption team, but with Occ hygienist
Note on D10: JDeBeer01: First meeting was not with the mine adoption team, but with Occ hygienist
Note on D14: JDeBeer01: First meeting was not with the mine adoption team, but with Occ hygienist
Note on D64: JDeBeer01: Team establishment will take place on 23 April 2013
Note on D65: JDeBeer01: Team establishment will take place on 23 April 2013
Note on D66: JDeBeer01: Team establishment will take place on 23 April 2013
Note on D67: JDeBeer01: Team establishment will take place on 23 April 2013
Note on D68: JDeBeer01: Team establishment will take place on 23 April 2013
Note on D69: JDeBeer01: Team establishment will take place on 23 April 2013
Note on D70: JDeBeer01: Team establishment will take place on 23 April 2013