## Sheet1
Activity | Tasks | Responsibility | Planned Date | Actual Date | Due Date Performance
Source Elimination - Current machines | Collaborate with T& M Team and CM& CCs | HG | End Aug 2012
| Workshop on possible LP from the other five sources | HG | End Oct 2012
| Noise source Modeling work by University of Pretoria | JDB | End Aug 2012
Source Elimination - Expansion projects and new mines | Prepare a discussion doc/ pres. For the MOSH taskforce | Team | End Sept 2012
| Discuss the proposed workshop with the MOSH Taskforce | Team | Mid Oct 2012
| Obtain a list of design personnel from the MOSH Taskforce | Team | Mid Nov 2012
| Drilling selection criterion for Future Mines | Team | End Sep 2012
HPD TAS | First Draft Assessment Tool | JDB | End Aug 2012
| Draft Assessment Tool | Team | Mid Sept 2012
| Present the assessment tool to the industry workshop | Team | End Sept
| Assist the adopter and Implementers | Team | Dec 2012
| Facilitate Interest group activities | Team | 14 Nov 2012
Simple Leading practice booklet | Compile summary of the practices and contact personnel | DC | End Aug 2012
| Design the SLP usage tracking mechanism | JDB | Mid Sept 2012
| CoM to Design the booklet | Team | Mid Oct 2012
1st Industry Team Meeting - Orientation | Finalise the venue, agenda & Send invite letters | Team | 26 Sept 2012
| Finalise Presentations | Team | Mid Sept 2012
2nd Industry Team Meeting | Organise and facilitate the team meeting | Team | 14 Nov 2012
Industry Team Workshop | Organise & facilitate a workshop to Identify the new LP | Team | 13 Feb 2013
4th Industry Team Meeting | Meeting to discuss the progress of the documentation phase | Team | 13 Mar 2013
5th Industry Team Meeting | Meeting to discuss the progress of the demonstration phase | Team | 15 May 2013
6th Industry Team Meeting | Meeting to discuss the COPA formation and post demo | Team | 14 Aug 2013
Note on B22: Workshop Discussion Points o MOSH Process o Team vision o Adoption of the expert model o Buy quiet policy o ‘Actual’ cost of noise o Meeting dates and agenda for the year
Note on B25: Workshop Discussion Points o Progress on source elimination initiatives (the T&M and CM& CC initiative) o HPD Closure Strategy o Discussion on the Noise Level Targets for the next two, five and ten years o List of potential leading practices
Note on B27: Workshop Discussion Points o Identification of the new leading practice