| ##### STRICTLY CONFIDENTIAL |  | PRELIMINARY |
| --- | --- | --- |

MINUTES OF THE NOISE ADOPTION TEAM MEETING HELD AT THE CHAMBER OF MINES ON WEDNESDAY 30 MAY 2012 AT 09H00 IN THE LEARNING HUB BOARDROOM 4TH FLOOR.

PRESENT:	Dick Coutts (DC) 	        - Adoption team manager

Jose de Beer (JDB) 	        - Adoption team assistant manager (Chairperson and Scribe)

Hlangabeza Gumede (HG) - Principal Specialist (Noise)

ABSENT:	None

APOLOGIES:	None

|  |  | RESPON. PERSON | DUE DATE |
| --- | --- | --- | --- |
| 1. | OPENING, WELCOME, APOLOGISE AND APPROVAL OF PREVIOUS MEETING MINUTES JDB opened and welcomed members at the weekly meeting. The previous minutes dated 23 May 2012 were approved without changes. | Team | Noted |
| 2. | CONFIRMATION OF AGENDA - The agenda was approved as tabled. - The Emergency Procedure, evacuation route and assembly points were not tested and are planned for the next Noise team meeting. | Team | 30 May ‘12 |
| 3. 3.1 3.2 3.3 3.4 3.5 3.6 3.7 3.8 3.9 3.10 3.11 3.12 3.13 3.14 3.15 3.16 3.17 3.18 3.19 | MATTERS ARISING (Previous Minutes) Industry Workshop: HG discussed a “draft” presentation to the team with the aim to reach the target audience for the Aug 2012 workshop. “Suite of simple leading practices” DC is negotiating with stakeholders. SLP management will also be discussed during the 2012 workshop on the way forward with these practices. Action: # Feedback on progress is required at the next Noise team meetings. # Sasol Sponsor telecon: DC contacted Christa Booth and awaits a date for August 2012. Buy Quite Policy: DC presented a “draft” to the team which will be reviewed by the team in the final stages. Action: - Progress is required at next meeting. ARM Mining Demo’s Nkomati and Two Rivers JDB awaits new dates from their coordinators for June 2012 after a telecon and e-mail sent. Sasol Statistical data. Awaits statistical data from Inus to share on improvement on SASOL Noise Improvement Plans and initiatives for future activities. Action: - If no reply is received this request will be closed as it an operational issue. Lonmin outreach Rustenburg DC Awaits feedback regarding future training sessions and interaction. MMPA May 2012 Conference Presentation JDB awaits feedback from conference coordinators and Phindiwe Fatuse for key learning’s and sharing with the team. 6th June 2012 - DMR visit and Mining Legotla HG to cancel or postpone this scheduled DMR meeting due to the Mining Legotla which is taking place on the same day. Action: - HG will attend this occasion on behalf of the noise team. 6th June 2012 - Shaft Sinkers invite JDB and DC will attend the Shaft Sinkers Engineering meeting as scheduled by Dirk Bleeker. Action: - DC and JDB to question the audience whether Shaft Sinkers will adopt and if they foresee any obstacles for not adopting etc. 7th June 2012- Mooi Nooi Mining Exhibition Duncam Adams will attend as technical expert. 7th June 2012- NWR Tripartite meeting Rustenburg HG or DC to attend. 13th June 2012 Kriel – Arnold Theron The date for the HPD_TAS_Tool demo was confirmed Action: - HG /JDB to attend. An agenda was requested by JDB Flexible HPD’s JDB circulated the info required to the Noise team and to Xstrata head office. Osborn Crusher info JDB-The info was received any anyone can scrutinize if needed. Mining Charter Info The team completed the spreadsheet to the best of their knowledge and it was submitted to SM for finalization. Goldfields Mining Exhibition Letter HG completed the letter and was sent of the name list as per request from SM. Task Force workshop Letter HG completed the draft letter for the planned workshop. It was discussed and approved by the team. Action: - HG to discuss with SM before submission to task force members Expert Model The revised and “draft” expert model was tabled by DC for discussion. Action: - DC to finalise for discussion at next Noise team Meeting. | Team Team DC DC Team DC JDB Team JDB DC JDB HG Team Team JDB & DC Team Team Team Team Team HG Team HG Team Team DC | Noted Noted Pending Pending Aug’ 12 Noted 13 Jun ‘12 Pending Noted 13 Jun ‘12 Pending Pending 1 Jun ‘12 Noted Noted 6 Jun ‘12 Noted Noted Noted Noted Noted Done Noted 6 Jun ‘12 Noted Noted 13 Jun ‘12 |
| 4.0 4.1 4.2 4.3 4.4 5. 5.1 5.2 5.3 5.4 5.5 5.6 5.7 | GENERAL Strategic Communications feedback – Douw Cronje The team will submit their contribution on 31st May 2012 Month end report The team took cognisance to complete individual reports and to circulate it to one another before submission to SM. Industry Interaction - M&R - JDB await confirmation on meeting requirements from Trevor Schultz - TWP and Basil Read- Awai info from Dirk Bleeker - Atlas Copco - Wilhelm Visser – Await invite - Shat Sinker Industry meeting 31st May 2012 – This was postponed by Shaft Sinkers due no reply from their management. 25th July 2012Eastern district tri Partite meeting JDB will attend NOISE ADOPTION MEETING SCHEDULES 2012: Venues and times might change JUN; Wed; 06, 13, 20, 27 June @ 10H30 at COM. JUL; Wed; 04, 11, 18, 25 July @ 10H30 at COM. AUG; Wed; 01, 8, 15, 22, 29 August @ 10H30 at COM. SEP; Wed; 05, 12, 19, 26 September @ 10H30 at COM. OCT; Wed; 03, 10, 17, 24, 31 October @ 10H30 at COM. NOV; Wed; 07, 14, 21, 28 November @ 10H30 at COM. The highlighted dates is for SM to attend if available. MOSH ADOPTION TEAM MEETINGS 2012 –. JUN; Thu; 21 June @ 07h30 at COM. JUL; Thu; 19 July @ 07h30 at COM. AUG; Thu; 16 August @ 07h30 at COM. SEP; Thu; 20 September @ 07h30 at COM. OCT; Thu; 18 October @ 07h30 at COM. NOV; Thu; 15 November @ 07h30 at COM. GEE MONTHLY MEETINGS 2012 JUL; Fri; 13 July @ 09H00 at COM. AUG; Fri; 10 Aug @ 09H00 at COM. OCT; Fri; 12 Oct @ 09H00 at COM. NOV; Fri; 09 Nov @ 09H00 at COM. INDUSTRY MEETINGS 2012 JUL; Wed; 25 July @ 09H00 at COM. SEP; Wed; 26 Sep @ 09H00 at COM. NOV; Wed; 28 Nov @ 09H00. TASK FORCE MEETINGS 2012 JUN; Fri; 22 June @ 07H30 at COM. AUG; Fri; 17 Aug @ 07H30 at COM. OCT; Fri; 19 Oct @ 07H30 at COM. JUN; Fri; 01 Jun @ 07H30 at COM. SEP; Fri; 07 Sep @ 07H30 at COM. DEC; Fri; 07 Dec @ 07H30 at COM. OH &SPC MEETINGS 2012 JUL; Fri; 20 July @ 07h30 at COM. SEP; Fri; 21 Sep @ 07H30 at COM. NOV; Fri; 23 Nov @ 07H30 at COM. EASTERN DISTRICT TRIPARTITE FORUM MEETINGS 2012 JUL; Wed; 25 Jul @ 10H00-12h00 at ECM (Eastern Chrome Mines). OCT; Wed; 31 Oct @ 10H00-12h00 at Xstrata Thorncliffe. NORTH WESTERN (NW) DISTRICT TRIPARTITE FORUM MEETINGS 2012 JUN; Thu; 07 June @ 07H00-10H00 at Xstrata Platinum Eland Mine - (Rodney O’ Reily). JUL; Thu; 05 July @ 07H00-10H00 at Northam Platinum - (Danny Gonsalves). AUG; Wed/Fri; 1-3 Aug @ Mine Safe 2012. SEP; Thu; 06 Sep @ 07H00-10H00 at Anglo American at Bathopele – (Dawie van Aswegen). OCT; Thu; 04 Oct @ 07H00-10H00 at Impala Platinum – (Bond Malunga). NOV; Thu; 01 Nov @ 07H00-10H00 at Lonmin Hossy Shaft – (Grant Webber). DEC; Thu; 06 Dec @ 07H00-10H00 at Xstrata Western Chrome Mines (Richard Vermeulen). JAN ‘13; Thu; 03 or 10 Jan @ 07H00-10H00 at Anglo American Platinum Siphumelele Mine– (Chris Moller). FEB ‘13; Tue; 07 Feb @ 07H00-10H00 at Impala Platinum-12# and 12N (Riaan Swanepoel). MAR‘13; Thu; 07 Mar @ 07H00-10H00 at Lonmin Platinum Shaft - (Christo Horn). | Team Team Team Team Team | Noted Noted Noted Noted Noted |

| 6.0 6.1 | Adjournment and next meeting Adjournment took place at 12H10. The next Noise Adoption meeting will be held on 16th June 2012 (Due to Legotla and Shaft Sinkers meeting) at 09 H00 to 13H30 on the 4th Floor Learning Hub Boardroom. | Team | Noted |
| --- | --- | --- | --- |

These minutes are still in draft and will be signed as a correct record of proceedings as soon as comment is received.

_________________________________________		______________________________________

SCRIBE	DATE

_________________________________________ 	_____________________________________

CHAIRPERSON	DATE