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MINUTES OF THE NOISE ADOPTION TEAM MEETING HELD AT THE CHAMBER OF MINES ON WEDNESDAY 30 MAY 2012 AT 09H00 IN THE LEARNING HUB BOARDROOM 4TH FLOOR.
PRESENT:	Dick Coutts (DC) 	        - Adoption team manager 
	Jose de Beer (JDB) 	        - Adoption team assistant manager (Chairperson and Scribe)
	Hlangabeza Gumede (HG) - Principal Specialist (Noise)
	
ABSENT:	None	
APOLOGIES:	None	
	
	
	RESPON. PERSON
	DUE DATE

	1.

	OPENING, WELCOME, APOLOGISE AND APPROVAL OF PREVIOUS MEETING MINUTES 
JDB opened and welcomed members at the weekly meeting. The previous minutes dated 23 May 2012 were approved without changes. 
	
Team
	
Noted

	2.

	CONFIRMATION OF AGENDA
· The agenda was approved as tabled. 
· The Emergency Procedure, evacuation route and assembly points were not tested and are planned for the next Noise team meeting. 
	
Team 
	
30 May ‘12
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	MATTERS ARISING (Previous Minutes)
Industry Workshop:  
HG discussed a “draft” presentation to the team with the aim to reach the target audience for the Aug 2012 workshop.

“Suite of simple leading practices”
DC is negotiating with stakeholders. SLP management will also be discussed during the 2012 workshop on the way forward with these practices.
Action:  
· Feedback on progress is required at the next Noise team meetings.

Sasol Sponsor telecon:   
DC contacted Christa Booth and awaits a date for August 2012.

Buy Quite Policy: 
DC presented a “draft” to the team which will be reviewed by the team in the final stages.
Action:  
· Progress is required at next meeting.

ARM  Mining Demo’s Nkomati and Two Rivers
JDB awaits new dates from their coordinators for June 2012 after a telecon and e-mail sent. 

Sasol Statistical data.
Awaits statistical data from Inus to share on improvement on SASOL Noise Improvement Plans and initiatives for future activities.
Action:  
· If no reply is received this request will be closed as it an operational issue.


Lonmin outreach Rustenburg
DC Awaits feedback regarding future training sessions and interaction. 

MMPA May 2012 Conference Presentation
JDB awaits feedback from conference coordinators and Phindiwe Fatuse for key learning’s and sharing with the team.

6th  June 2012 - DMR visit and Mining Legotla
HG to cancel or postpone this scheduled DMR meeting due to the Mining Legotla which is taking place on the same day. 
Action:  
· HG will attend this occasion on behalf of the noise team.

6th June 2012 - Shaft Sinkers invite
JDB and DC will attend the Shaft Sinkers Engineering meeting as scheduled by Dirk Bleeker.
Action:  
· DC and JDB to question the audience whether Shaft Sinkers will adopt and if they foresee any obstacles for not adopting etc.

7th June 2012- Mooi Nooi Mining Exhibition
Duncam Adams will attend as technical expert.

7th June 2012- NWR Tripartite meeting Rustenburg
HG or DC to attend.

13th June 2012 Kriel – Arnold Theron
The date for the HPD_TAS_Tool demo was confirmed
Action:  
· HG /JDB to attend. An agenda was requested by JDB

Flexible HPD’s
JDB circulated the info required to the Noise team and to Xstrata head office.

Osborn Crusher info
JDB-The info was received any anyone can scrutinize if needed.

Mining Charter Info
The team completed the spreadsheet to the best of their knowledge and it was submitted to SM for finalization.

Goldfields Mining Exhibition Letter
HG completed the letter and was sent of the name list as per request from SM. 

Task Force workshop Letter
HG completed the draft letter for the planned workshop. It was discussed and approved by the team. 
Action:  
· HG to discuss with SM before submission to task force members 


Expert Model
The revised and “draft” expert model was tabled by DC for discussion.
Action:  
· DC to finalise for discussion at next Noise team Meeting.
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	GENERAL 
Strategic Communications feedback – Douw Cronje
The team will submit their contribution on 31st May 2012

Month end report 
The team took cognisance to complete individual reports and to circulate it to one another before submission to SM.

Industry Interaction
· M&R - JDB await confirmation on meeting requirements from Trevor Schultz
· TWP and Basil Read- Awai info from Dirk Bleeker
· Atlas Copco - Wilhelm Visser – Await invite
· Shat Sinker Industry meeting 31st May 2012 – This was postponed by Shaft Sinkers due no reply from their management.

25th  July 2012Eastern district tri Partite meeting 
JDB will attend


NOISE ADOPTION MEETING SCHEDULES 2012: Venues and times might change
	JUN
	Wed
	06, 13, 20, 27 June @ 10H30 at COM

	JUL
	Wed
	04, 11, 18, 25 July @ 10H30 at COM

	AUG
	Wed
	01, 8, 15, 22,  29 August @ 10H30 at COM

	SEP
	Wed
	05, 12, 19, 26 September @ 10H30 at COM

	OCT
	Wed
	03, 10, 17, 24, 31 October @ 10H30 at COM

	NOV
	Wed
	07, 14, 21, 28 November @ 10H30 at COM

	
	
	The highlighted dates is for SM to attend if available

	

	MOSH ADOPTION TEAM MEETINGS 2012 –

	JUN
	Thu
	21 June @ 07h30 at COM

	JUL
	Thu
	19 July @ 07h30 at COM

	AUG
	Thu
	16 August @ 07h30 at COM

	SEP
	Thu
	20 September @ 07h30 at COM

	OCT
	Thu
	18 October @ 07h30 at COM

	NOV
	Thu
	15 November @ 07h30 at COM



GEE MONTHLY MEETINGS 2012
	JUL
	Fri
	13 July @ 09H00 at COM

	AUG
	Fri
	10 Aug @ 09H00 at COM

	OCT
	Fri
	12 Oct  @ 09H00 at COM

	NOV
	Fri
	09 Nov @ 09H00 at COM



INDUSTRY MEETINGS 2012
	JUL
	Wed
	25 July  @ 09H00 at COM

	SEP
	Wed
	26 Sep @ 09H00 at COM

	NOV
	Wed
	28 Nov @ 09H00



TASK FORCE MEETINGS 2012
	JUN
	Fri
	22 June @ 07H30 at COM

	AUG
	Fri
	17 Aug @ 07H30 at COM

	OCT
	Fri
	19 Oct @ 07H30 at COM

	JUN
	Fri
	01 Jun @ 07H30 at COM

	SEP
	Fri
	07 Sep @ 07H30 at COM

	DEC
	Fri
	07 Dec @ 07H30 at COM



OH &SPC MEETINGS 2012
	JUL
	Fri
	20 July @ 07h30 at COM

	SEP
	Fri
	21 Sep @ 07H30 at COM

	NOV
	Fri
	23 Nov @ 07H30 at COM



EASTERN DISTRICT TRIPARTITE FORUM MEETINGS 2012
	JUL
	Wed
	25 Jul @ 10H00-12h00 at ECM (Eastern Chrome Mines)

	OCT
	Wed
	31 Oct @ 10H00-12h00 at Xstrata Thorncliffe



NORTH WESTERN (NW) DISTRICT TRIPARTITE FORUM MEETINGS 2012
	JUN
	Thu
	07 June @ 07H00-10H00 at Xstrata Platinum Eland Mine - (Rodney O’ Reily)

	JUL
	Thu
	05 July  @ 07H00-10H00 at Northam Platinum - (Danny Gonsalves)

	AUG
	Wed/Fri
	1-3 Aug @ Mine Safe 2012

	SEP
	Thu
	06 Sep @ 07H00-10H00 at Anglo American at Bathopele – (Dawie van Aswegen)

	OCT
	Thu
	04 Oct @ 07H00-10H00 at Impala Platinum – (Bond Malunga)

	NOV
	Thu
	01 Nov @ 07H00-10H00 at Lonmin Hossy Shaft – (Grant Webber)

	DEC
	Thu
	06 Dec @ 07H00-10H00 at Xstrata Western Chrome Mines (Richard Vermeulen)

	JAN ‘13
	Thu
	03 or 10 Jan @ 07H00-10H00 at Anglo American Platinum  Siphumelele Mine– (Chris Moller)

	FEB ‘13
	Tue
	07 Feb @ 07H00-10H00 at Impala Platinum-12# and 12N (Riaan Swanepoel)

	MAR‘13
	Thu
	07 Mar @ 07H00-10H00 at Lonmin Platinum Shaft - (Christo Horn)
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	6.0
6.1


	Adjournment and next meeting
Adjournment took place at 12H10. The next Noise Adoption meeting will be held on 16th June 2012 (Due to Legotla and Shaft Sinkers meeting) at 09 H00 to 13H30 on the 4th Floor Learning Hub Boardroom.
	Team



	Noted






These minutes are still in draft and will be signed as a correct record of proceedings as soon as comment is received.

_________________________________________		______________________________________
SCRIBE	DATE

_________________________________________ 	_____________________________________
CHAIRPERSON	DATE
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