| ##### STRICTLY CONFIDENTIAL |  | PRELIMINARY |
| --- | --- | --- |

MINUTES OF THE NOISE ADOPTION TEAM MEETING HELD AT THE CHAMBER OF MINES ON WEDNESDAY  17th  OCTOBER 2012 AT 10:30 IN THE LEARNING HUB BOARDROOM 4TH FLOOR.

PRESENT:	Dick Coutts (DC) 	          -  	Adoption team manager (Chairperson)

Jose de Beer (JDB) 	          -  	Adoption team assistant manager (Chairperson/Scribe)

Hlangabeza Gumede (HG)   - 	Principal Specialist (Noise)

ABSENT:	None

APOLOGIES:	None

|  |  | RESPON. PERSON | DUE DATE |
| --- | --- | --- | --- |
| 1. | OPENING, WELCOME, APOLOGISE AND APPROVAL OF PREVIOUS MEETING MINUTES JDB opened and welcomed members at the weekly noise team meeting. The previous minutes dated 05 October 2012 were tabled and approved with minor changes. | Team | Noted |
| 2. | CONFIRMATION OF AGENDA - The agenda was accepted as tabled and some additions were made under general. | Team | Noted |
| 3. 3.1 3.2 3.3 3.4 3.5 3.6 3.7 3.8 3.9 3.10 4.0 4.1 4.2 4.3 4.4 4.5 4.6 4.7 4.8 4.9 4.10 4.11 4.12 4.13 4.14 4.15 4.16 4.17 4.18 4.19 5. 5.1 5.2 5.3 5.4 5.5 5.6 5.7 5.8 | MATTERS ARISING (Previous Minutes) Source elimination repository initiatives: - The changes were done in PDF format and circulated to LM for web-site purposes. Action: - DC confirmed that it was circulated to LM - A follow up is to be done # Sasol Sponsor telecon: This meeting is confirmed with Mr. Pieter Steenkamp on 06 November 2012 at 15:00 in the Sasol Rosebank offices in Johannesburg. Action: - A draft noise team presentation is expected at the next noise team meeting for scrutiny by the team and for finalization for presentation at our sponsor meeting on 6th November 2012. Buy Quite Policy Update: The final document was circulated via Maria Rodriquez to industry. Action: - Feedback is awaited from industry by end of October 2012. - Comments and feedback will be used as an agenda item for the next industry team meeting planned for 14 November 2012 Annual Plan/Scope/ Progress/Feedback The annual plan was tabled and the Noise team is on Par with the required actions. Xstrata Kroondal Interaction We await feedback and an invite from Themba Nkosi as per e-mail dated 17 Oct 2012. Impala & Noise team interaction The noise team awaits invite from Anton Botha or James van Rensburg as per e-mail received from Impala. Action: - Mr SM is notified with this delay. - Douw Cronje will be invited for interview training purposes University of Pretoria A follow up letter was submitted by HG for noise reduction research and the assistance on the five noise sources on the drill. Action: We are awaiting interaction and feedback from the Professor. Xstrata Kroondal & Impala visit 03 Oct 12 This visit was cancelled on very short notice. Action: - Xstrata invited all to engage and visit to Impala on 26 October 2012 to experience noise clipper leading practices implemented. - The noise adoption team agreed that Xstrata can engage as per JDB’s e-mail Slow adoption spreadsheet 130 reasons for slow adoption were captured and classified on a spreadsheet as requested by Industry Action: - HG did the classification to pinpoint similar issues. - 8 Classifications ito perceptions and reasons for slow adoption were done etc. - Noise Team Learning Hub can only improve on communication - Reasons for slow adoption as discussed at the industry meeting are available. Expert Model The expert model was circulated to industry for comment. Action: Await feedback from industry by 31st October 2012 as these comments will be used for the 14 November 2012 Industry meeting. GENERAL Paint on ventilation fan Action: AE indicated that info is lacking. Cost of Noise The real cost of noise must still be shared by AE. Action: - The template developed by DC to be used for future NIHL cost - We are awaiting comments from industry by 31 October 2012 in this regard. Hydro power/compressed air circular DC requested to share some info with the team wrt work that he did and it also caters for “Greenfield” projects. Action: Standing Agenda point for now. HPD_TAS_Tool (Interest groups) The team developed a tracking report for full adopters, partial adopters and implementers etc. Action: - JDB and team to add to comment ito of tracking as per spreadsheet including time, dates, request, action, and follow etc. - Weekly updates are required to allow monthly verifications and feedback. - The documents will be saved monthly as per new revision for the specific month etc. - Updates as per comment was as agreed by all. Future Noise team meetings It is required to have scheduled dates to invite AE with the Noise team or other meetings as per contract Action: - HG will schedule and provide meeting dates for future interaction with AE and the Noise team from October 2012 onwards - The team to take note of the most important meeting dates as per activity register and annual plan (Jan/Feb 2013) Activity register This is verified at each meeting and will be a standing agenda item ito our strategic plan. Industry Visibility POV - Comments and suggestions were made. Action: - These and were captured on a team working document for visibility improvement. - Feedback on actions required from each team member will be done on a weekly basis for the interim. Hosting and Future forums Alwyn Pretorius from Harmony is prepared to host the next industry meeting on 14th November 2012 at Randfontein Golf Club. Action: - DC to confirm the arrangements - Next Noise team meeting: - A draft agenda and presentations to be prepared for 24th October 2012. The main Theme will be the HPD TAS Tool for 14 Nov 2012 industry meeting. Training Criteria on LP’s A need was identified to train industry on the criteria to identify leading practices as everybody claims that they have a LP. Action: - The team decided to pay attention to this request during the first industry meeting and interaction in 2013 Industry team Feedback report The spreadsheet done was changed into a word format. Action: - JDB - Change into Action log sheet info action (See GEE action list) Xstrata presentation 14 Nov 2012 Xstrata Eastern Mines volunteered to do a presentation on the “Hearing Coach” they have implemented as well as AAE’s. ( Auto Acoustic Emissions) Action: - JDB- A write up document was submitted to Xstrata Eastern Mines to obtain the write up before a decision will be made for 14 November 2012 presentation purposes. - JDB - To follow up with Xstrata Eastern Mines Future diary Planning - The team took cognisance of future tripartite meetings - JDB to attend CSIR session on 07 November 2012 on behalf of the noise team Dwarsrivier Chrome Mine Dwarsrivier requested a tracking template similar to use than the FOG team. Action: This will be tailor - made to suit the needs of the Noise team Sep/Oct- Noise team Monthly report This was reviewed and the changes will be done for submission to SM Noise team Monthly Mosh Presentation 18 Oct 2012 The presentation was reviewed and corrected for 18 October 2012 Delmas Coal Tri-Partite meeting and future meetings Jan 2013 JDB- Feedback was given and the 2013 tri partite meeting schedule is awaited Mosh Task Force meeting/Presentation 19 Oct 2012 CCM presentation will be used GEE feedback DC- GEE’s acknowledged that the 2008 milestones were not met. Action: Monthly feedback from noise team is requested. TB HIV Aids meeting: HG – Gave feedback and all have a mutual feeling that is a complex problem as with NIHL MEETING SCHEDULES 2012 NOISE ADOPTION MEETING SCHEDULES 2012: Venues and times might change OCT; Wed; 24, 31 October @ 10H30 at COM. NOV; Wed; 07, 14, 21, 28 November @ 10H30 at COM. MOSH ADOPTION TEAM MEETINGS 2012 –. NOV; Thu; 15 November @ 07h30 at COM. GEE MONTHLY MEETINGS 2012 NOV; Fri; 09 Nov @ 09H00 at COM. INDUSTRY MEETINGS 2012 NOV; Wed; 14 Nov @ 09H00. TASK FORCE MEETINGS 2012 OCT; Fri; 19 Oct @ 07H30 at COM. DEC; Fri; 07 Dec @ 07H30 at COM. OH &SPC MEETINGS 2012 NOV; Fri; 23 Nov @ 07H30 at COM. EASTERN DISTRICT TRIPARTITE FORUM MEETINGS 2012 OCT; Wed; 31 Oct @ 10H00-12h00 at Xstrata Thorncliffe. NORTH WESTERN (NW) DISTRICT TRIPARTITE FORUM MEETINGS 2012 NOV; Thu; 01 Nov @ 07H00-10H00 at Lonmin Hossy Shaft – (Grant Webber). DEC; Thu; 06 Dec @ 07H00-10H00 at Xstrata Western Chrome Mines (Richard Vermeulen). JAN ‘13; Thu; 03 or 10 Jan @ 07H00-10H00 at Anglo American Platinum Siphumelele Mine– (Chris Moller). FEB ‘13; Tue; 07 Feb @ 07H00-10H00 at Impala Platinum-12# and 12N (Riaan Swanepoel). MAR‘13; Thu; 07 Mar @ 07H00-10H00 at Lonmin Platinum Shaft - (Christo Horn). | Team DC JDB Team HG Team Ind Team Team JDB Team HG Team HG Team Team Team Team Team Team HG Team Team Team Ind. Team AE AE Team Ind. Team DC Team Team Team Team Team HG HG Team Team Team Team Team Team DC Team Team Team Team JDB Team JDB JDB Team Team Team Team Team Team Team Team HG Team Team HG Team | Noted 17 Oct ’12 17 Oct ‘12 Noted 24 Oct ‘12 Noted 31 Oct ‘12 24 Oct ‘12 Noted Pending Noted 17 Oct ‘12 Noted 17 Oct ‘12 Pending Noted 26 Oct ‘12 Noted 17 Oct ‘12 Done Noted Noted Noted Noted 31 Oct ‘12 Noted Pending Pending Noted 31 Oct ‘12 Noted Pending Noted Weekly Weekly Monthly Noted Pending Pending Noted Noted Noted Noted Weekly Noted 24 Oct ‘12 Noted 2013 Pending Noted 24 Oct ‘12 Noted 24 Oct ‘12 18 Oct ‘12 Noted Noted Noted Pending Noted 17 Oct ‘12 Noted Noted 19 Oct ‘12 Noted Pending Noted Noted |
| 6.0 6.1 | Adjournment and next meeting Adjournment took place at 14H 10. The next Noise Adoption Team meeting will be held on 24th October 2012 at 10H00 at the Learning Hub Boardroom 4th Floor. | Team | Noted |  | Noted |

These minutes are still in draft and will be signed as a correct record of proceedings as soon as comment is received.

_________________________________________		______________________________________

SCRIBE	DATE

_________________________________________ 	_____________________________________

CHAIRPERSON	DATE