| ##### STRICTLY CONFIDENTIAL |  | PRELIMINARY |
| --- | --- | --- |

MINUTES OF THE NOISE ADOPTION TEAM MEETING HELD AT THE CHAMBER OF MINES ON THURSDAY 5th  JULY 2012 AT 12:50 H00 IN THE LEARNING HUB BOARDROOM 4TH FLOOR.

PRESENT:	Dick Coutts (DC) 	-  Adoption team manager (Chairperson)

Jose de Beer (JDB) 	-  Adoption team assistant manager (Scribe)

Hlangabeza Gumede (HG) - Principal Specialist (Noise)

ABSENT:	None

APOLOGIES:	None

|  |  | RESPON. PERSON | DUE DATE |
| --- | --- | --- | --- |
| 1. | OPENING, WELCOME, APOLOGISE AND APPROVAL OF PREVIOUS MEETING MINUTES JDB opened and welcomed members at the weekly noise team meeting. The previous minutes dated 27 June 2012 were tabled and not approved. | Team | Noted |
| 2. | CONFIRMATION OF AGENDA - The agenda was accepted as tabled. | Team | Noted |
| 3. 3.1 3.2 3.3 3.4 3.5 3.6 3.7 3.8 3.9 3.10 3.11 3.12 4.0 4.1 4.2 4.3 4.4 | MATTERS ARISING (Previous Minutes) Industry Workshop: The 15th August 2012 ambitious targets are on par. Action: # All agreed that Douw Cronje must be involved on decisions and interaction regarding the workshop.helheld with Dr. Balfout and Dr, Kan # The workshop agenda needs to be finalized with all stakeholders. - An updated Industry and task force member list is still required from SM. HG and DC will follow up as the invites is to be send out before the next Noise team Meeting. - Need to invite task force members per letter - Task force to nominate industry team members to join the learning hub for noise etc. “Suite of simple leading practices” This will be reviewed at the 2012 Workshop. # Sasol Sponsor telecon: DC awaited confirmation from Christa Booth as per 28 May 2012 e-mail received Buy Quite Policy: The noise team will stick to the term “Buy Quiet” as it is known term nationally and internationally. More work is still to be done and weekly feedback on progress is required. Action: - This document will be discussed at the August 2012 workshop. ARM Mining Demo’s Nkomati and Two Rivers New dates were received from Tsietsi Letana for 17 & 18 July 2012. Action: - Finalization amongst noise team was done. - Dr. Sizwe Phakati to arrange his own interaction for the mentioned dates. Lonmin outreach Rustenburg/Awareness DC ± 120 employees undergone noise awareness training Action: - One session is left (19th July 2012) - DC to obtain attendance registers for record purposes DMR visit HG – Meeting was postponed to a later stage. Action: - HG - Approach DMR for another appointment during July 2012 - LTIFR, DIA’s and NIHL reporting to be part of DMR agenda Expert Model DC added info as discussed with the team. (Hyperlinks is the way forward) Action: - JDB to discuss if needed with the Sasol visit. Mining commodities interviews Interviews to be conducted before 31 July 2012. Action: - JDB- We have to obtain Xstrata info from Douw as this was already done at Kroondal - It will not be a good idea to overlook them Xstrata as they are not on the interview commodity list. - JDB will conduct interviews at Sasol on 10 July 2012 HPD TAS_Tool DC- it was suggested that we need to get members to register at the August 2012 workshop to register and to form possible COPA’s. Action: - DC-Be prepared to have enrolment and registration form available Industry Interaction - CSIR Dr Anita Edwards- This was a valuable meeting and key learning’s were recognized. The next meeting will be held on 26th July for further infarction and the aim to have Anita as a speaker at our workshop. Action: Maintain relationships with all of the people below - M&R - JDB to contact Trevor Schultz for a possible meeting - TWP and Basil Read- Await info from Dirk Bleeker - Atlas Copco - Wilhelm Visser – Await invite SAMCHEM JDB – A first familiarization meeting was held with Hunadi Setati in Centurion Pretoria. These are new stakeholders having approximately eight opencast mines dealing with aluminium and Ceramic commodities Action: - A demo meeting is scheduled for 13 July 2012 to share the Mosh and Learning hub background. - The HPD_TAS_Tool and training material will also be shared. GENERAL 2011/2012 Chamber of Mines Annual Report (Highlights / Achievements, Lowlights & Challenges for the reporting period) Action Each noise team member to write to HG for consolidation 11 July LP documentation #50 Workshop – Team to comment on the documentation DC circulated Feedback – John Steward Investigation Team to comment before 12 July 2012 on the documentation Stanford Malatji circulated on behalf of Dr. John Steward. Tripartite schedule Noise team to take note of the schedule Chris Legodi circulated for attendance purposes. | Team Team Team HG & DC DC DC Team Team Team JDB Team DC HG HG DC JDB Team Team Team Team DC Team Team Team Team HG & JDB Team Team Team Team | Noted Noted Pending Pending Pending Pending Pending Jul ‘12 Noted 6 Jul ’ 12 Noted Pending Pending Pending Done Noted Pending Pending Noted Pending Pending 26 Jul ‘12 Noted Noted Noted 13 Jul ‘12 Pending 11 Jul ‘12 11 Jul ‘12 Noted |
| 5. 5.1 5.2 5.3 5.4 5.5 5.6 5.7 5.8 | MEETING SCHEDULES NOISE ADOPTION MEETING SCHEDULES 2012: Venues and times might change JUL; Wed; 11, 18, 25 July @ 10H30 at COM. AUG; Wed; 01, 8, 15, 22, 29 August @ 10H30 at COM. SEP; Wed; 05, 12, 19, 26 September @ 10H30 at COM. OCT; Wed; 03, 10, 17, 24, 31 October @ 10H30 at COM. NOV; Wed; 07, 14, 21, 28 November @ 10H30 at COM. MOSH ADOPTION TEAM MEETINGS 2012 –. JUL; Thu; 19 July @ 07h30 at COM. AUG; Thu; 16 August @ 07h30 at COM. SEP; Thu; 20 September @ 07h30 at COM. OCT; Thu; 18 October @ 07h30 at COM. NOV; Thu; 15 November @ 07h30 at COM. GEE MONTHLY MEETINGS 2012 JUL; Fri; 13 July @ 09H00 at COM. AUG; Fri; 10 Aug @ 09H00 at COM. OCT; Fri; 12 Oct @ 09H00 at COM. NOV; Fri; 09 Nov @ 09H00 at COM. INDUSTRY MEETINGS 2012 JUL; Wed; 25 July @ 09H00 at COM. SEP; Wed; 26 Sep @ 09H00 at COM. NOV; Wed; 28 Nov @ 09H00. TASK FORCE MEETINGS 2012 AUG; Fri; 17 Aug @ 07H30 at COM. OCT; Fri; 19 Oct @ 07H30 at COM. JUN; Fri; 01 Jun @ 07H30 at COM. SEP; Fri; 07 Sep @ 07H30 at COM. DEC; Fri; 07 Dec @ 07H30 at COM. OH &SPC MEETINGS 2012 JUL; Fri; 20 July @ 07h30 at COM. SEP; Fri; 21 Sep @ 07H30 at COM. NOV; Fri; 23 Nov @ 07H30 at COM. EASTERN DISTRICT TRIPARTITE FORUM MEETINGS 2012 JUL; Wed; 25 Jul @ 10H00-12h00 at ECM (Eastern Chrome Mines). OCT; Wed; 31 Oct @ 10H00-12h00 at Xstrata Thorncliffe. NORTH WESTERN (NW) DISTRICT TRIPARTITE FORUM MEETINGS 2012 JUL; Thu; 05 July @ 07H00-10H00 at Northam Platinum - (Danny Gonsalves). AUG; Wed/Fri; 1-3 Aug @ Mine Safe 2012. SEP; Thu; 06 Sep @ 07H00-10H00 at Anglo American at Bathopele – (Dawie van Aswegen). OCT; Thu; 04 Oct @ 07H00-10H00 at Impala Platinum – (Bond Malunga). NOV; Thu; 01 Nov @ 07H00-10H00 at Lonmin Hossy Shaft – (Grant Webber). DEC; Thu; 06 Dec @ 07H00-10H00 at Xstrata Western Chrome Mines (Richard Vermeulen). JAN ‘13; Thu; 03 or 10 Jan @ 07H00-10H00 at Anglo American Platinum Siphumelele Mine– (Chris Moller). FEB ‘13; Tue; 07 Feb @ 07H00-10H00 at Impala Platinum-12# and 12N (Riaan Swanepoel). MAR‘13; Thu; 07 Mar @ 07H00-10H00 at Lonmin Platinum Shaft - (Christo Horn). | Team | Noted |

| 6.0 6.1 | Adjournment and next meeting Adjournment took place at 13H 35. The next Noise Adoption meeting will be held on 11th July 2012 at 10 H00 to 13H00 on the 4th Floor Learning Hub Boardroom. | Team | Noted |
| --- | --- | --- | --- |

These minutes are still in draft and will be signed as a correct record of proceedings as soon as comment is received.

_________________________________________		______________________________________

SCRIBE	DATE

_________________________________________ 	_____________________________________

CHAIRPERSON	DATE